CARE International and Vision Eritrea

Emergency Drought Assistance:

Land Preparation and Seed Distribution

In Debub Zone, Eritrea

1 May 2001 – 30 January 2002

Final Report

1 May 2001 – 30 January 2002

Submitted to USAID/OFDA Eritrea

28 February 2002

# I.	EXECUTIVE SUMMARY

Final Report

Organization:	CARE International in Eritrea	Date:		30 Sep 2001

Mailing Address:	P O Box 6561	Contact Person:	Liz Sime

Asmara	Telephone:		291-1-151282

Eritrea	Fax:		291-1-151282

E-Mail:		caretl@eol.com.er

Program Title:	Emergency War and Drought Assistance

Cooperative Agreement/Grant No.:	AOT-G-00-00-00254-00

Country(ies)/Region(s):	Eritrea, Debub Zone

Disaster/Hazard:	War and Drought

Time Periods Covered by This Report:	1 May 2001 to 30 January 2002

The Goal of this project is to improve the level of food security of the war and drought-affected populations in the targeted areas of Debub zone.

The Objective is that by September 2001, 4000 farm families in the target areas will harvest sufficient cereal food crops for their annual requirements.

This project is focusing on the recently returned populations from IDP (Internally Displaced Persons) camps in Debub zone.  The two target sub-zones are Senafe and Tsorona.

Tractor plowing began in early May and was completed by mid September 2001.  A total of 5,677 hectares were plowed for 7,120 beneficiary families in Senafe and Tsorona sub-zones.

Seed distribution began in mid June and was completed by the end of July 2001.  A total of 1,886 quintals of seed (1 quintal = 100 kg) were distributed to 3,587 beneficiary families in Senafe and Tsorona sub-zones.  This seed was sufficient to plant 2,703 hectares.  In Tsorona sub-zone, 536 quintals of teff were distributed to 1,787 beneficiary families.  In Senafe sub-zone 1,194 quintals of barley and 156 quintals of wheat were distributed to 1,800 beneficiaries.

Monitoring of field activities is being carried out by Vision Eritrea and CARE twice per month to each sub-zone.  A monitoring checklist form is used to document observations on rainfall status, appearance of the crop, crop damage from pests, crop stand density and uniformity, and the crop timing.  Good rainfall in June, July, and August, with timely plowing and planting, has resulted in successful establishment and good crop growth.  The harvest of wheat and barley should contribute significantly to the annual food requirements of the beneficiary families.  Teff as a cash crop will increase the income of families planting this crop in Tsorona sub-zone.  Data collection in target areas is conducted by enumerators trained by Vision Eritrea and monitored by the sub-zonal Ministry of Agriculture.

CARE has built a successful partnership with two implementing partners, the local NGO Vision Eritrea, and the Ministry of Agriculture.  These partnerships began in the Northern Red Sea zone emergency drought project, and continue in this project to build capacity in project planning, management and monitoring through practical application and training within this project.

TABLE OF CONTENTS

I.	EXECUTIVE SUMMARY	2

II.  	PROJECT GOAL AND OBJECTIVES	7

A.  	Introduction And Background	7

1.  	Background and History	7

2.  	Location	7

3.  	Problems	7

4.  	Intervention	7

5.  	Cooperating Agencies	7

6.  	Capacity Building	8

B.  	Project Goal	8

C.  	Project Objective(s)	8

D. 	Measurement Indicators	8

III.  	SIGNIFICANT PROJECT DEVELOPMENTS	8

A.  	Target Area Description	8

1.  	Locations	8

2.  	Physical – Environmental Conditions	9

3.  	Target locations	9

B.  	Project Establishment	10

1.  	Agreement signed between CARE / VE / MOA	10

2.  	Planning meetings with MOA	10

3.  	Workplans	10

C.  	Surveys	10

1. 	Introduction	10

2.  	Methodology	10

3.  	Results	11

D.  	Land Preparation	11

1.  	Introduction	11

2.  	Methodology	11

3.  	Results	13

E.  	Seed Distribution	14

1. 	Introduction	14

2.  	Methodology	14

3.  	Results	16

F.	Data Analysis Methodology	17

G.	Impact on Food Security	19

1.	Limitations and importance of water	19

2.	Total Crop Production of Beneficiary Farm Families	21

3.	Food Security - Impact Indicators	24

a.	Level of food security at the household level	24

b.	The level of surplus sales	26

c.	The reduction in food aid requirements	27

H.	Crop Production Statistics	28

1.	Plowing	28

2.	Source of Seed	28

3.	Planting	31

4.	Harvest	33

5.	Pests and Crop Quality	35

6.	Farmer Needs	36

I.	Livestock	37

J.	Socio-Economic Profile of Surveyed Families	40

K. 	Partnerships	42

1.  	Introduction	42

2.  	Vision Eritrea	42

3.  	Ministry of Agriculture	42

L.  	Monitoring	43

M.  	Impact	43

1.  	Factors affecting impact	43

2.  	Determining Impact	43

IV.  	PROBLEMS ENCOUNTERED AND CORRECTIVE PROCEDURES	44

V.  	FINANCIAL REPORT	44

LIST OF TABLES

Table  1	Number of target families and family members, and total population of target subzones

Table  2a  	Kebabis and number of villages receiving project tractor plowing

Table  2b  	Planned and Actual plowing in the two target sub-zones

Table  3a  	Kebabis and number of villages receiving project seed

Table  3b  	Planned and Actual seed distribution in the two target sub-zones

Table  4    	Number of farmers, villages and kebabis surveyed in each subzone

Table  5    	Crop water availabilty during project year

Table  6    	Total tons of crop harvested

Table  7    	Calculated value (USD) of crops produced

Table  8    	Crop production percent increase of 2001 over 2000

Table  9    	Profit (USD) on harvest after costs of plowing and seed

Table 10   	Food needs and responses to a shortage

Table 11   	Average number of quintals produced per family

Table 12   	Percent of annual crop food requirements met from the crop harvest

Table 13   	Percent of farm families producing sufficient crop for annual needs

Table 14   	Sale of crop harvest

Table 15   	Food needs, production, and deficit in tons

Table 16   	Percent of farmers planting project and non-project plowing done during 2000

Table 17   	Method of non-project plowing done by tractor and oxen

Table 18   	Percent of farmers that obtained seed from the different sources

Table 19   	Percent of farmers planting project an dnon-project seed in 2001

Table 20a   	Average amount of seed (kg) planted per farmer in 2001

Table 20b	Average planting rate (kg/ha) each type of distributed seed

Table 20c	Percent of total seed planted coming from project and non-project sources, and quality of project seed

Table 21   	Percent of farmers planting each type of crop

Table 22   	Average number of hectares planted per farmer

Table 23   	Percent of farmers harvesting crops (of those that planted the crop)

Table 24   	Percent of hectares of crop harvested that were planted

Table 25   	Average quintals per hectare crop production from planted fields

Table 26   	Average quintals per hectare crop production from harvested fields

Table 27a   	Crop growth rating

Table 27b	Problems seen in the monitoring visit

Table 27c	Pest problems reported by farmers

Table 27d	Quality of harvested crop

Table 28   	Requested needs of farmes

Table 29   	Percent of families owning livestock

Table 30   	Percent of familieswith each of four tyhpes of livestock

Table 31   	Distribution by type of livestock

Table 32   	Number of animals per family for each animal type

Table 33   	Source of livestock feed ikn 2000

Table 34   	Family statistics

Table 35   	Family death statistics during past three years

LIST OF FIGURES

Figure 1	Average elevation of target subzones, with Asmara as a reference

Figure 2 	Seasonal rainfall patterns in Debub Zone at different elevation

Figure 3	Annual rainfall variation in Debub Zone at different elevations

Figure 4	Average yearly rainfall in project target subzones

Figure 5	Average monthly rainfall in project target subzones

Figure 6	Relationship between crop water availability rating and production

LIST OF APPENDICES

Appendix  1  	Map of Target locations

Appendix  2  	Agreement between CARE/Vision Eritrea and the Ministry of Agriculture

Appendix  3  	Baseline Survey Form

Appendix  4  	Plowing Data Recording Sheet Example

Appendix  5  	Flow Chart of Field Documentation

Appendix  6  	Plowing and Seed Distribution Data by Location

Appendix  7  	Seed Distribution Data Recording Sheet Example

Appendix  8  	Checklist Form for Monitoring Visits

# II.  	PROJECT GOAL AND OBJECTIVES

## A.  	Introduction And Background

### 1.  	Background and History

The Eritrean war for independence began in 1961, and ended in 1993 with formal recognition by the United Nations.  During the first five years of independence, Eritrea made significant progress in rehabilitation of the various economic sectors, including agriculture.  A border dispute between Eritrea and Ethiopia erupted in 1998, and escalated into a war which lasted for three years.  In the year 2000, a Cessation of Hostilities agreement was signed by both countries.

### 2.  	Location

Eritrea is situated in the Horn of East Africa. It is bordered by Ethiopia to the south, Sudan to the west, Djibouti to the southeast, and the Red Sea to the east.  The State of Eritrea has six administrative zones, with each zone comprised of several sub-zones.  The areas along the border with Ethiopia were severely affected by the most recent conflict.  These include the zones of Debub and Gash Barka.

### 3.  	Problems

As the result of the recent three years of conflict, most of the families in the border sub-zones of Debub were forced to move from their homes.  Many of these displaced families relocated to IDP camps situated further into the country.  Those families that did stay were affected by two years of low rainfall, with a resultant failure of crops and death of livestock.

Most farmers from the border areas had not been able to plant in 2000 as they were living in IDP camps.  Following the cessation of hostilities, many of the displaced families began returning to their homes, in May of 2001, in hopes of establishing crops in their fields before the June rains.  However, the short time between their return and the planting deadline, and their inability to plow (lack of equipment, oxen, cash) and plant (lack of seed) presented a major obstacle to the returning farmers.  If they did not get their fields planted and harvested this season, they would have to wait until the following year, and would be dependent on food aid for yet another year.

### 4.  	Intervention

To take advantage of this very important opportunity of crop production by the returning IDPs, CARE, Vision Eritrea (a local Eritrean NGO), the Ministry of Agriculture, and USAID began discussions of possible interventions.  The most feasible appeared to be one similar to that just completed in the Northern Red Sea zone in response to drought, that is, provision of tractor plowing and seed to the farmers.

### 5.  	Cooperating Agencies

As the working relationships in Northern Red Sea zone was excellent, the cooperating agencies continued to be CARE, Vision Eritrea, and the Ministry of Agriculture.

### 6.  	Capacity Building

During implementation of the Northern Red Sea zone project, CARE worked closely with Vision Eritrea in project management, activity monitoring, report writing, data analysis, and financial management.  CARE and Vision Eritrea also worked with the Ministry of Agriculture in data collection and reporting.  In the current project, capacity building has continued and expanded in all of the above areas.

## B.  	Project Goal

The Goal of this project is to improve the level of food security of the war and drought-affected populations in the targeted areas of Debub zone.

## C.  	Project Objective(s)

The Objective is that by September 2001, 4000 farm families in the target areas will harvest sufficient cereal food crops for their annual requirements.

## D. 	Measurement Indicators

The measurement indicators will focus on crop production and food security.  These indicators are:

- The number of farmers receiving assistance

- The number of hectares of land plowed

- The amount of seed distributed

- The amount of harvest of cereal crops by the farmers

The indicators will be measured using the data from documentation of plowing and seed distribution, the baseline, and the impact surveys.

# III.  	SIGNIFICANT PROJECT RESULTS

## A.  	Target Area Description

### 1.  	Locations

The target sub-zones were selected by the MOA in consultation with local government, as areas to where farm families were returning from the IDP camps, and where successful farming had been practiced prior to displacement.  The two sub-zones selected were Senafe and Tsorona, both on the border of Ethiopia.  Specific areas within the two sub-zones were further defined, prior to plowing and seed distribution, as the locations of return by IDPs became more clear.  The estimated population of the two sub-zones is approximately 80,000.

### 2.  	Physical – Environmental Conditions

Geographically, the two sub-zones are located in the highlands and western escarpment of Eritrea, at elevations of 5,000 to 7,000 feet.  Senafe, at the higher elevations, has annual mean temperature of 23C, while Tsorona, at the lower elevations, averages 27C.

The rainy season of the two sub-zones is from May through September, with the peak occurring in July and August.  Total annual rainfall in Senafe ranged from 296 mm to 779 mm during the years 1992 through 1999.  Total annual rainfall in Tsorona ranged from 380 mm to 490 mm during the years 1997 to 1999.

### 3.  	Target locations

The country of Eritrea is made up of six zones, each zone contains several sub-zones and each sub-zone includes several kebabis.  A kebabi is the smallest administrative structure in the governmental system, and is made up of several villages.

Within the two target sub-zones of Senafe and Tsorona, specific kebabis were selected that were priority for resettlement by returning IDPs.  Priority was determined by the number of people returning, the availability of land, and the production potential.  The number of target kebabis and activities in each sub-zone is listed below, and the locations are shown on the map of Debub zone (Appendix 1).

- 1 kebabi in Senafe sub-zone			Tractor plowing only

- 3 kebabis in Senafe sub-zone			Seed distribution only

- 6 kebabis in Tsorona sub-zone		Tractor plowing only

- 8 kebabis in Tsorona sub-zone		Seed distribution and Tractor plowing

The number of beneficiary families and individuals in the project target subzones is shown in Table 1.  This can be compared with the most recent estimates of total population, provided by the Ministry of Agriculture, of the two target sub-zones.

Table 1     Number of target families and family members, and total population of target subzones

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Number of |  |  |  |  |  |  |  |
| Target Families |  |  |  | 9,842 |  | 2,290 | 7,552 |
| Target Individuals |  |  |  | 52,173 |  | 12,413 | 39,760 |
| Total Families |  |  |  | 34,580 |  | 24,070 | 10,510 |
| Total Individuals |  |  |  | 121,035 |  | 82,605 | 38,430 |

## B.  	Project Establishment

### 1.  	Agreement signed between CARE / VE / MOA

A working agreement between CARE/Vision Eritrea and the Ministry of Agriculture was developed and signed by all parties (Appendix 2).  This agreement helped to ensure that the roles and responsibilities of each party were clearly understood and agreed to.

### 2.  	Planning meetings with MOA

Discussions had been held with the MOA, both at the national and zonal levels, during preparation of the proposal, and a general approach had been agreed on.  These discussions continued as the pattern of the returning IDPs became clearer.  Activity planning became more focused, and at the time of project start-up the details had been finalized.

When the final target locations were selected, the appropriate crop types were chosen for those areas.  Arrangement was made for tractors to be sent from other areas to ensure timely completion of plowing.  The process of selecting beneficiaries, and allocation of seed and plowing was agreed on, as was the system for documentation and reporting.

### 3.  	Workplans

Following project approval, a detailed workplan was developed by CARE, which listed the major project activities (discussed later in this report) and sub activities.  Start and end dates for each activity were determined to ensure timely completion, along with the agency responsible.  This workplan is being used both for activity planning and as a checklist for monitoring.

## C.  	Surveys

### 1. 	Introduction

Two surveys of target farmers were conducted during this project, a baseline and an impact.  The baseline survey will be used to determine the starting point for measurement of the impact of this project on food security, and will gather basic information on the socio-economic status of the target farmers.  The impact survey will quantify crop production as a result of this project, and the level of food security of the family as a result of the crops produced.

### 2.  	Methodology

The survey forms used in Northern Red Sea zone worked well, with few problems, and resulted in much useful information on crop production and other socio-economic parameters.  The general format was maintained for Debub zone, with slight modifications to clarify some questions, and with additions or subtractions to reflect the differing conditions in Debub (Appendix 3).  The questions, however, were maintained as close as possible to those of Northern Red Sea zone so that comparisons could be made between the two zones.

The surveys would be conducted by enumerators, trained and supervised by Vision Eritrea and the MOA.  As in the Northern Red Sea zone, the target would be to include 10 percent of the beneficiary farm families, distributed equally throughout the target areas.

The enumerators were selected by the MOA sub-zone and local government representatives, and approved by Vision Eritrea.  To increase the effectiveness of the survey, enumerators were selected that were literate, spoke the local language, and were respected by the communities.  Vision Eritrea conducted a two-day training on survey methods for the MOA and the enumerators on 20-21 July that included one day of reviewing the forms and discussion and the second day of practice in a village.

The baseline survey was conducted from 1 to 10 August.  The head of household was interviewed, or if not present, another adult family member was surveyed in their place.  The data from the survey has been entered into a computer database, and analysis has begun.

The impact survey was conducted on the month of Novermber, 2001. The two surveys were combined and used to measure the impact of the project.  The results are presented in this final report.

### 3.  	Results

## D.  	Land Preparation

### 1.  	Introduction

Traditionally, farmland in the target sub-zones is prepared for planting by draft animals, usually oxen, or by tractor plowing.  Most of the farmers in the target sub-zones had lost their draft animals as a result of the war, internal displacement, and drought.

As part of government services, the MOA will plow land for farmers with its tractors in accessible areas of need if time and finances are available.  When this is done, the MOA charges the farmer some percentage of the total cost.  The agreed rate in Debub is 91 Nakfa per hour.  The MOA subsidizes the remainder (199 Nakfa) of the total actual cost of 290 Nakfa per hour.  Tractor plowing takes from 2 to 4 hours per hectare depending on the field conditions.

This project agreed to pay the farmers’ share of plowing costs for the proposed 4,000 hectares of land (4,000 beneficiaries) in Senafe and Tsorona sub-zones.  The MOA was responsible for plowing the land with its tractors, while CARE and Vision Eritrea developed the record-keeping forms and monitored the activities.

### 2.  	Methodology

The target kebabis within the sub-zones were selected based on the criteria of the number of returning IDPs, the potential for production, and accessibility by tractors for plowing.  Villages within the sub-zones were selected jointly by the MOA zonal and sub-zonal offices, the members of local sub-zone administrations, the kebabi administrators, and the development committees.  All of the selected areas of the target sub-zones are rain-fed with minimal use of river diversion.  The kebabis are listed in Table 2a, along with the number of target villages in each kebabi.

Table 2a   Kebabis and number of villages receiving project

tractor plowing

| Sub-zone | Kebabi | Number of Villages |
| --- | --- | --- |
| Senafe | Mirara | 1 |
| Tsorona | Adihargets Adikeren Dekilefai Dibi Embabarya Endabastifanos Filho Genzebo Gobele Kinin Maichena Sarda Tsorona Una-Andom | 3 2 5 8 5 5 4 4 6 1 7 1 4 8 |

The Village Development Committee established specific criteria for selecting beneficiary families, following guidelines from CARE and Vision Eritrea.  The criteria were returning IDPs, female-headed households, farmers without cash and draft animals, families with young men away from home, poor farmers, and elderly.  The selected family had to be an inhabitant of the kebabi and a full time farmer.  The Village Development Committee selected the recipients and amounts of plowing for each based on the criteria and the amount of funds available.

Record-keeping forms for plowing (Appendix 4) were prepared by Vision Eritrea and sent to the MOA before the plowing started.  These forms were to record the name of the beneficiary, amount of land plowed in hectares, total tractor time in hours, unit price per hour, total price in Nakfa, ID number of beneficiary, and a space for the signature or finger print of the beneficiary.  The beneficiary names were filled in prior to plowing.

Following selection, each beneficiary farmer was informed that their land would be plowed as part of this project, with their cost covered by the project.  The village representative, the MOA sub-zone representative, and the farmers were present at the time of tractor plowing.  The enumerators assisted the MOA in obtaining beneficiary signatures and other required information.

The flow of documentation is diagrammed in Appendix 5.  The MOA sub-zone offices summarized the receipt forms from each kebabi and sent a copy of this summary to Vision Eritrea as a preliminary update.  The original signed forms, along with the summary, were sent to the MOA zonal office.

The zonal office combined all summaries, checked and verified the data, prepared an invoice and other documentation, and sent the entire package, including a request for payment and the original signed sheets, to Vision Eritrea.

Vision Eritrea checked the completeness and accuracy of the documents from the MOA.  If documentation was incomplete, or if errors were found, the documents were returned to the MOA for correction.  When the documents were in order, Vision Eritrea forwarded the package to CARE along with a cover letter verifying accuracy, and a request for payment.

A format was developed by CARE and Vision Eritrea to record and monitor progress of plowing activities.  In one section the unverified data from the sub-zonal summaries was entered.  In the other section the verified data from the request-for-payment package was entered.  By adding the two together, a close approximation of progress could be determined, and was used for monitoring plowing activities.  The format also included cost estimates which were used for budget monitoring.

### 3.  	Results

Plowing began in early May and was completed by the end of July for cereal crops, and by mid September for later planted legumes.

The distribution of plowing and number of beneficiaries by kebabi is summarized in Appendix 6.  The summary by sub-zone of the planned and actual number of hectares plowed is shown in Table 2b.

Table 2b     Planned and Actual plowing in the two target sub-zones

| Sub-zone | Planned Plowing (Hectares) | Actual Plowed (Hectares) | Actual Number of Beneficiary Families | Average Number of Hectares per Beneficiary |
| --- | --- | --- | --- | --- |
| Senafe | 2,000 | 370 | 490 | 0.76 |
| Tsorona | 2,000 | 4,957 | 6,192 | 0.80 |
| Tsorona |  | 350 | 438 | 0.80 |
| Total | 4,000 | 5,677 | 7,120 | 0.80 |

A total of 5,677 hectares of land plowed by the project was verified by 30 September.  In addition, approximately 350 hectares of land has been plowed, but documentation has not been received yet.  The total plowed land is approximately 35 percent more than planned.  This was possible due to a reduction in charges per hectare by the MOA to provide plowed land to more of the returning IDPs.

The distribution of plowed land between the two sub-zones was altered from the original plan for two reasons.  The first is that many more IDPs were returning to Tsorona sub-zone (25,000) than to Senafe (8,000) as determined by the zonal administration.  The second reason is that much of the farmland in Senafe that was suitable for tractor plowing was suspected of being mined with landmines.  For these reasons the majority of land tractor-plowed by this project was in Tsorona sub-zone (5,307 hectares), with less in Senafe sub-zone (370 hectares).  Additional land was plowed in Senafe by oxen in more hilly and isolated areas that were clear of landmines.

The total number of beneficiaries (approx. 7,100) also exceeded the planned of 4,000.  Each beneficiary family received an average of 0.80 hectares of plowing.

## E.  	Seed Distribution

### 1. 	Introduction

Traditionally, farmers save some of their seed from the previous harvest to plant in the following year.  As many of the farmers had been in IDP camps for one or more years, they had not been able to grow crops or save seed.  Other farmers that had stayed in the area had harvested little or no crop because of drought or destruction of their fields.

The MOA was responsible for purchasing and distribution of the seed.  Vision Eritrea and CARE assisted in, and monitored the distribution.  The project seed distribution was, in some cases, in the same locations as the project tractor plowing, while in other cases was in areas that had been plowed by other means.  Seed in some areas was provided by other donors or sources, and was planted in project-plowed fields.  The MOA coordinated to ensure that seed was available to plant in fields as soon as they were plowed, and thus meet the tight deadlines for planting in time for the rains.

Farmers traditionally grow barley, wheat, and legumes in Senafe region, while farmers in Tsorona sub-zone, where the weather is warmer, grow teff, sorghum, maize and legumes.  Sorghum and maize need to be planted earlier as they take a longer time to grow and mature.

### 2.  	Methodology

The criteria for selecting the locations for seed distribution were similar to the criteria for plowing, and were the number of returning IDPs, the potential for production, and the lack of seed availability.  The MOA and local government selected the locations based on these criteria.  Three kebabis in Senafe, and eight in Tsorona were selected, and are listed in Table 3a.

###### Table 3a   Kebabis and number of villages receiving

project seed

| Sub-zone | Kebabi | Number of Villages |
| --- | --- | --- |
| Senafe | Adebagie Chegauro Maiguduf | 6 2 5 |
| Tsorona | Adikeren Dibi Embabaria Endabastifanos Gobele Maichena Sarda Tsorona | 2 5 7 4 3 1 5 4 |

The Village Development Committee and the MOA identified the appropriate crop types.  The crop types and varieties were selected based on the suitability of growth in the target areas and on the preferences of the farmers.

The MOA did not have sufficient quantities of seed in their stores, requiring them to purchase directly from local merchants who had purchased the seed in other parts of the country.  The barley and wheat seed was purchased from farmers in Senafe.  Teff seed was purchased from a trader who had purchased the seed in Tsorona.  Visual quality standards were used by the MOA and the committee.  These included seed size, fullness, integrity of the seed coat, and lack of insect damage.  The price of the seeds was negotiated and determined by the MOA based on the market value.  The MOA paid cash for the acceptable seed.

The MOA used governmental storage facilities, such as schools, in the distribution villages to store the purchased seeds until it was distributed.

The criteria for seed beneficiaries were similar to those for plowing, and were returning IDPs, with female-headed households, poor farmers, elderly, and those that lacked access to seed having priority.  A beneficiary for seed may or may not be the same as for tractor plowing.  Farmers who plowed their land by oxen were also eligible.  Each village committee determined who would be eligible in their community.

The form used for documenting seed distribution and receipt by beneficiaries (Appendix 7) was prepared by Vision Eritrea. These forms included the name of beneficiaries for each village, head of household, ID number, the amount and type of seed received, and a line for a receipt signature or finger print.

The distribution activities were coordinated by the MOA at the sub-zone level.  The distribution was conducted by the MOA, the Village Development Committee, enumerators, Vision Eritrea, and CARE.

At each distribution site several villages could be present on the same day.  The distribution was conducted by village, and the total amount of seed for each village was carried outside the storeroom then distributed to each beneficiary family.  Record keeping was conducted by the MOA and enumerators.

The flow of documentation and review process for seed distribution was the same as for tractor plowing (Appendix 5).

### 3.  	Results

The seed distribution began in mid June and was completed by the end of July 2001.  Barley and wheat seeds were distributed to 3 kebabis in Senafe sub-zone, and teff seed was distributed to 8 kebabis of Tsorona sub-zone.  The distribution of seed and number of families is summarized by kebabi in Appendix 6.  A summary by sub-zone and seed type of the planned and actual amounts of seed distributed is presented in the table 3b.

Table 3b     Planned and Actual seed distribution in the two target sub-zones

|  |  | Planned |  | Actual |
| --- | --- | --- | --- | --- |
| Sub-zone | Seed Type | Number of Hectares to Plant | Amount of Seed in Quintals |  | Number of Hectares Planted | Amount of Seed in Quintals | Number of Beneficiary Families |
| Senafe | Wheat | 805 | 1,047 |  | 120 | 156 | 208 |
| Senafe | Barley | --- | --- |  | 796 | 1,194 | 1,592 |
| Tsorona | Teff | 800 | 240 |  | 1,787 | 536 | 1,787 |
| Tsorona | Sorghum | 1,765 | 211 |  | --- | --- | --- |
| Tsorona | Millet | 630 | 38 |  | --- | --- | --- |
| Total |  | 4,000 | 1,536 |  | 2,703 | 1,886 | 3,587 |

The proposed crop types for the target sub-zones were wheat, teff, sorghum, and millet.  However, as the final target areas were selected based on the number of returning IDPs, and on the lack of early rains in the target areas, the proposed crop types were re-evaluated and more appropriate crop types were selected.  This was also influenced by seed types donated by other agencies.  It was determined that the shorter season crops of wheat and barley were most appropriate for the target areas in Senafe, and teff for target areas in Tsorona.

A total of 1,886 quintals of seed (1 quintal = 100 kg) were distributed to 3,587 beneficiary families.  As wheat and barley are planted at a higher seeding rate (125 and 150 kg/ha) than maize and sorghum (25 and 15 kg/ha), the number of hectares planted from the distributed seed (2,703 hectares) was less than the planned of 4,000 hectares.  The seed was distributed to a total of 3,587 beneficiary families.

There were a total of 916 hectares planted from project seed in Senafe (1,800 beneficiary families) and 1,787 hectares planted in Tsorona (1,787 beneficiary).

Monitoring visits are being made by Vision Eritrea and CARE to each sub-zone on a bi-monthly schedule to observe and record crop growth.  A checklist form (Appendix 8) is being used to document field observations, and includes rainfall and water status, and crop growth parameters.

Rainfall has generally been good, but variable between locations, with some areas receiving less than needed.  Few problems have been seen in the fields or reported by farmers or MOA staff. The time of planting was a little late as the result of delayed rainfall.  However, the general appearance and stand of the crops is good, and most of the fields are mature and close to harvest.

## F.	Data Analysis Methodology

The impact of this project was determined from a baseline (July 2001) and a post-harvest (November 2001) survey that determined the food production and food security situation for the cropping year prior to this project (2000), and for the cropping year of the project (2001).

A total of 592 farmers were interviewed during the baseline survey, and 566 during the post-harvest survey.  This is approximately 6 percent of the 9,842 beneficiary families.  The survey sub-zones, kebabis, villages, and number of farmers surveyed in each are listed in Appendix 7.  Table 4 presents a summary by sub-zone.

Table 4     Number of farmers, villages and kebabis surveyed in each sub-zone

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Mo. |  | Target Areas |  | Senafe | Tsorona |
| Farmers |  |  |  |  |  |  |  |
|  |  | July |  | 592 |  | 238 | 354 |
|  |  | Nov |  | 566 |  | 241 | 325 |
| Villages |  |  |  |  |  |  |  |
|  |  | July |  | 77 |  | 29 | 48 |
|  |  | Nov |  | 64 |  | 27 | 37 |
| Kebabis |  |  |  |  |  |  |  |
|  |  | July |  | 15 |  | 4 | 11 |
|  |  | Nov |  | 15 |  | 4 | 11 |

The information received from the two surveys was entered into separate databases, the data was sorted by village, kebabi and subzone, sub-totals and averages calculated, and analyzed further by calculating percentages and other meaningful values.  The data presented in this report are averages at the sub-zoba level.  Data and averages at the kebabi, village and individual level is available in the CARE office.  The year referred to in the tables is the year of planting, for example (2000 = Plant in 2000 and Harvest in 2001).

Selected crop production statistics from the survey sub-sample for 2000 and 2001 were extrapolated to the total of 9,842 target beneficiaries to estimate the impact on the entire target area.

The data reported here is as reported by the farmers during the surveys, and is based on their best estimates of field size and production quantities.  Therefore, variability does exist, but error is minimized by focusing on averages.  Differences and trends are readily apparent in the summarized data.

## G.	Impact on Food Security

### 1.	Limitations and importance of water

In the semi-arid environment of Eritrea, crop production is largely dependent on the availability of water to the crop at the times that it is needed.  In debub zone this water comes primarily from local rainfall.

Rainfall data for Debub Zone was provided by the Ministry of Agriculture for the years 1992 through 2000.  Preliminary rainfall data for 2001 has also been provided, but for some locations is not as yet complete.  The rainfall data is presented below in graphical form.  The actual values are presented in Appendix 8 in a summarized form.

The seasonal rainfall patterns in Eritrea vary depending on the elevation, the distance inland, and geological structures.  Average elevetion of Senafe and Tsorona are 2,565m and 1,489m respectively.

The total annual rainfall varies widely from year to year.  The overall 9-year average is 255 mm.  The average for 1999 was 143 mm and for 2000 was 171 mm.  An average minimum water requirement for crops, from either rainfall or collecting runoff, would be 400 – 600 mm, depending on the crop type.  Some years there is sufficient water for good crop growth and production, while other years there is insufficient, and crops fail.  This pattern is clearly seen in Figure 1 for the three different elevation ranges.

Figure 1	Average yearly rainfall in project target subzones.

No rainfall records of Tsorona are available for the years of 1992 to 1996.  Eventhough rainfall in Tsorona was quite low compared to Senafe, it was quite the same with the zonal average.

The average monthly rainfall of the target zone (Debub) is shown in Figure 2.

Figure 2	Average monthly rainfall in project target subzones.

Debub zone receives good rainfall in the month of July and it is the same for the areas under this zone especially for the target subzones (Senafe and Tsorona).

Farmers were asked to rate three components (as good, fair, poor) of crop water.  These were rainfall, the water supply system they were using (spate diversion, river overflow, rainfall), and the water status of their field (good, fair, poor).  The ratings of good, fair, and poor were given a score of 3, 2, and 1 respectively.  Averages were calculated by subzone and a percentage was calculated of the total possible score (3.0).  These percentages are presented in Table 5.  An average of the three was calculated to estimate the overall water availability to the crop.

Table 5     Crop water availability during project year (as a percentage of scores given by farmers) ( I – 15)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Rainfall |  |  |  | 34 |  | 34 | 34 |
| Water System |  |  |  | 60 |  | 33 | 75 |
| Field Water Status |  |  |  | 47 |  | 36 | 55 |
| Average Water Availability |  |  |  | 47 |  | 34 | 55 |

To summarize, wide variability exists in rainfall over different areas of North Red Sea Zone, both from year to year, and also during the growing season of any individual year.  As the average yearly rainfall is so close to the minimum crop requirement, any fluctuation, either in total amount or in distribution throughout the year, can be disastrous to crop production, and ultimately food security.  The long-term strategy, from a crop production point of view, to increase food security must include assuring the availability of water to crops.

### 2.	Total Crop Production of Beneficiary Farm Families

The surveys included only a sub-sample (6 percent) of the target beneficiaries.  Selected statistics and results were extrapolated to estimate the results of the entire target population.  The total number of beneficiaries, as well as the total population of the target subzones, was shown in Table 1.  The data results extrapolated from the survey were used to calculate the total crop production of the 9,842 beneficiary farm families, and the cash value of the crop.  The results are presented in Tables 6-9.

The total teff, barley, wheat, maize, sorghum and legume crop harvested in 2000 was 824 tons, while in 2001 there were 2,039 tons harvested.  The differences between crops and between subzones can be seen in Table 6.

Table 6     Total tons of crop harvested (Extrapolated)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Year |  | Target Areas |  | Senafe | Tsorona |
| Teff |  | 2000 |  | 442 |  | 0 | 442 |
|  |  | 2001 |  | 993 |  | 0 | 993 |
| Barley |  | 2000 |  | 240 |  | 240 | 0 |
|  |  | 2001 |  | 429 |  | 429 | 0 |
| Wheat |  | 2000 |  | 95 |  | 95 | 0 |
|  |  | 2001 |  | 158 |  | 158 | 0 |
| Maize |  | 2000 |  | 47 |  | 0 | 47 |
|  |  | 2001 |  | 254 |  | 0 | 254 |
| Sorghum |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 114 |  | 0 | 114 |
| Legume |  | 2000 |  | 0 |  | 0 | 0 |
|  |  | 2001 |  | 2 |  | 2 | 0 |
| Finger Millet |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 144 |  | 0 | 144 |
| Total Seven Crops |  | 2000 |  | 823 |  | 334 | 489 |
|  |  | 2001 |  | 2,095 |  | 590 | 1,505 |

The total value of the harvest, at market prices, in US dollars was 544,670 for 2000 and 1,154,120 for year 2001.  Values for individual crops and subzones is shown in Table 7.

Table 7     Calculated value (USD) of crops produced (Extrapolated)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Year |  | Target Areas |  | Senafe | Tsorona |
| Value of Crop (USD) |  |  |  |  |  |  |  |
| Teff |  | 2000 |  | 229,157 |  | 0 | 229,157 |
|  |  | 2001 |  | 515,023 |  | 0 | 515,023 |
| Barley |  | 2000 |  | 53,300 |  | 53,300 | 0 |
|  |  | 2001 |  | 95,440 |  | 95,440 | 0 |
| Wheat |  | 2000 |  | 22,404 |  | 22,404 | 0 |
|  |  | 2001 |  | 37,421 |  | 37,421 | 0 |
| Maize |  | 2000 |  | 12,138 |  | 0 | 12,138 |
|  |  | 2001 |  | 65,883 |  | 49 | 65,834 |
| Sorghum |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 33,893 |  | 0 | 33,893 |
| Legume |  | 2000 |  | 0 |  | 0 | 0 |
|  |  | 2001 |  | 952 |  | 952 | 0 |
| Finger Millet |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 64,089 |  | 0 | 64,089 |
| Total Seven Crops |  | 2000 |  | 316,999 |  | 75,704 | 241,295 |
|  |  | 2001 |  | 812,701 |  | 133,862 | 678,839 |

The percent increase in crop production and cash value of year 2001 over year 2000 is shown in Table 8.  There was an overall increase of 181 percent.

Table 8     Crop production percent increase of 2001 over 2000 (Extrapolated)

|  |  | Average |  |  |  |  |  |  |  | Finger |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | of All Crops |  | Teff | Barley | Wheat | Maize | Sorghum | Legume | Millet |
|  |  | 155 |  | 125 | 79 | 67 | 443 | --- | --- | --- |
| Percent Increase |  |  |  |  |  |  |  |  |  |  |

The average profit for the farmer was determined for the hypothetical case if the farmer had paid for seed and tractor plowing (Table 9) and sold all of the harvest.  Averaged over all locations in 2001 the farmer would have made a profit ($13), highest in Tsorona ($14) and lowest in Senafe ($9).  This is compared with an average profit of only $3 in 2000, with Tsorona as the only subzone where farmers averaged a profit.

Table 9     Profit (USD) on harvest after costs of plowing and seed (Extrapolated)

|  |  | Planting |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Year |  | Target Areas |  | Senafe | Tsorona |
| Teff |  | 2000 |  | 35 |  | -21 | 36 |
|  |  | 2001 |  | 40 |  | -21 | 40 |
| Barley |  | 2000 |  | -11 |  | 5 | -50 |
|  |  | 2001 |  | 11 |  | 11 | --- |
| Wheat |  | 2000 |  | 0.7 |  | 0.7 | --- |
|  |  | 2001 |  | -5 |  | -5 | --- |
| Maize |  | 2000 |  | -15 |  | -11 | -15 |
|  |  | 2001 |  | -4 |  | -10 | -4 |
| Sorghum |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 2 |  | -10 | 2 |
| Legume |  | 2000 |  | -12 |  | -12 | --- |
|  |  | 2001 |  | -10 |  | -9 | -24 |
| Finger Millet |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 31 |  | --- | 31 |
| Average Profit per Farmer of All Crops |  | 2000 |  | 7 |  | 3 | 8 |
|  |  | 2001 |  | 32 |  | 4 | 40 |

### 3.	Food Security - Impact Indicators

The impact of this project on the target population was planned to be measured by three criteria.  These were:

- The level of food security attained at the household level.

- The level of surplus sales.

- The reduction in food aid requirements.

Each of these will be discussed in the following three sections, and data presented in Tables 10-15 to demonstrate success in meeting the above criteria.

#### Level of food security at the household level

The annual food needs as reported by farmers, and their responses to a food shortage during 1998-2000 as a result of war and drought, were determined from the baseline survey and are summarized in Table 10.

Table 10     Food needs and responses to a shortage (BL2 – 31-33)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Average Yearly Grain Food Requirement (Quintals) |  |  |  |  |  |
| Per family |  |  |  | 8.7 |  | 9.4 | 8.3 |
| Per person |  |  |  | 1.7 |  | 1.8 | 1.6 |
| Percent of Families Migrating for Work or Food |  |  |  |  |  |
|  |  |  |  | 2.5 |  | 2.9 | 2.3 |
| Percent of Families Selling Property to Buy Food |  |  |  |  |  |
|  |  |  |  | 36 |  | 35 | 37 |
| Average Value (Nakfa) of Property Sold Past Year to Purchase Food |  |  |
|  |  |  |  | 1,675 |  | 1,122 | 2,032 |

The yearly requirement of cereal grain for food was reported by farmers to be an average, for the two sub-zones, of 8.7 quintals per family and 1.7 quintals per person.  There was, however, no much difference between sub-zones.  This is seen clearly when comparing the food requirement per person, which takes into account the possible differences in family size.  The highest per person need of 1.8 quintals was in the subzone of Senafe, and the lowest per person need of 1.6 quintals in the subzone of Tsorona.

Two of the coping mechanisms of the families to this food shortage were quantified in the survey.  These two responses were:  to move from their home location in search of work or food, and to sell personal property for cash to buy food.

An average of 2.5 percent of all target families reported migrating for work or food during the year prior to the project.  The response was quite different in the two sub-zones.  The lowest migration rate (2.3%) was for farmers in the Tsorona area.  The highest migration rate (2.9%) was in Senafe.

An average of 36 percent of families reported selling personal property to buy food.  This was the lowest in Senafe (35%) and the highest in Tsorona (37%).  The average value of the property sold, of those that sold property, showed a same pattern to the above two observations.  The highest value (2,032 Nakfa/US$151) was reported in Tsorona, while Senafe was with an average value of 1,122 Nakfa.

Food security for most of the residents of rural Debub Zone depends on crop production or other agricultural activities such as raising livestock.  Those that grow crops either save the harvest for food or sell the crop for cash which is later used to buy food.  Many farmers save some for food and seed, and sell the remainder.

The amount produced by a family determines to a large extent the level of food security that they will experience for the coming year.  Some farmers grow only one type of crop, the type dependent on environmental conditions and preferences.  Other farmers will grow more than one crop type to spread and reduce the risk of complete crop failure.

The average amount of crop produced per family that planted the crop is shown in Table 11 for the planting years of 2000 and 2001 (project year).

Table 11     Average number of quintals produced per family (BL1 – 2-9)

|  |  | Total |  |  |  |  |  |  |  | Finger |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year |  | of all crops |  | Teff | Barley | Wheat | Maize | Sorghum | Legume | Millet |
| 2000 |  | 1.3 |  | 1.6 | 1.4 | 0.9 | 0.5 | 2.8 | --- | --- |
| 2001 |  | 2.3 |  | 1.5 | 1.9 | 0.7 | 0.9 | 0.7 | 0.1 | 1.1 |
| Percent Increase |  | 85 |  | -8 | 38 | -19 | 79 | -74 | --- | --- |

During 2000 the average production per family was 2.0 quintals, well below the average food need of 8.7 quintals.  The average production for year 2001 was 2.4 quintals, quite higher than the previous year.  This is a 17 percent increase over year 2000.  The greatest percent increase was seen in maize, while the least was seen in sorghum.  This is not surprising as maize is less tolerant of a water shortage (drought) than sorghum which is more drought resistant.

The level of food security from crop production can be looked at in two ways.  The first is on a location/area basis, the second is on a family basis.

The percent of annual crop food requirements, on an overall area basis, that was met from the crop harvest is summarized in Table 12 for the two years.  This is calculated by dividing the production by the needs.

Table 12     Percent of annual crop food requirements met from the crop harvest (Extrapolated)

|  |  | Planting |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Year |  | Target Areas |  | Senafe | Tsorona |
| Percent of Annual Needs |  |  |  |  |  |  |  |
|  |  | 2000 |  | 10 |  | 16 | 8 |
|  |  | 2001 |  | 24 |  | 27 | 24 |

In 2000 the production met only 24 percent of the needs, while in 2001 the production met 26 percent of the needs

The second analysis of food security groups the individual families according to the level of food security that they reached.  For this analysis the percent of needs met by production was calculated for each individual surveyed.  They were then categorized into 3 levels, those that produced between 0 and 50 percent of their needs, those that produced between 51 and 99 percent, and those that produced 100 percent or more of their needs.  The percent of farmers that were in each category are shown in Table 13 for both years.

Table 13     Percent of farm families producing sufficient crop for annual needs (Extrapolated)

|  |  |  | Percent of Needs: |  | 0-33 % | 33-66 % | >=66 % |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Percent of Farmers |
| 2000 |  |  |  |  |  | 81 |  | 12 |  | 8 |
| 2001 |  |  |  |  |  | 65 |  | 27 |  | 8 |

In 2000 four percent of farmers produced sufficient crop to meet their needs, 8 percent from 51-99 percent of their needs, and 88 percent produced less than 50 percent of their needs. During the year 2001, in comparison, three percent met their needs, while 13 percent produced from 5,99 percent of their needs, and only 84% produced less than 50 percent. Eventhough the overall increase in full sufficiency of the year 2001 is quite the same to the year of 2000, there is an increasing trend in 51-99 percent of the needs and decreasing trend in less than 50 percent.

#### The level of surplus sales

The percent of farmers that reported that they did or would sell some of their crop was less than 1 percent in 2000 i.e., 0.4 but no dat was collected for the year of 2000.

Table 14     Sale of crop harvest (I – 14)

|  |  | Planting |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Year |  | Target Areas |  | Senafe | Tsorona |
| Percent of Farmers that Sold or Will Sell Some Grain Crop Harvested |  |  |
|  |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 0.4 |  | 0.0 | 0.6 |
| Average Quantity (Q) of Crop Sold or Will Be Sold per Farmer that Sold or Will Sell |  |
|  |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 3.00 |  | 0.00 | 3.00 |

The average quantity of crop sold per farmer for 2001 was 0.01 quintals and no data obtained for 2000. This is likely because only two farmers in Tsorona, in 2001 that produced wanted to seel crops. The other farmers in the two subzones wanted to eat or save for the coming farming season.

#### The reduction in food aid requirements

The results in Table 15 were calculated from the reported annual food needs of the family and the reported crop production of the farmers.

Table 15     Food needs, production, and deficit in tons (Extrapolated)

|  |  | Planting |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Year |  | Target Areas |  | Senafe | Tsorona |
| Food Need |  | 2000 |  | 8,582 |  | 2,153 | 6,236 |
|  |  | 2001 |  | 8,582 |  | 2,153 | 6,236 |
| Food Produced |  | 2000 |  | 823 |  | 334 | 489 |
|  |  | 2001 |  | 2,095 |  | 590 | 1,506 |
| Food Deficit |  | 2000 |  | -7,759 |  | -1,819 | -5,748 |
|  |  | 2001 |  | -6,487 |  | -1,564 | -4,731 |

The food produced in the year of 2001 was more than enough to fulfill the amount of food needs (4,266 tons being as a surplus).  In the year of 2000, there was 7,890 as a food deficit.  This food surplus will help the farmers to save for the coming farming season or sell to bring additional income.

## H.	Crop Production Statistics

The crop production data presented in Tables 16 – 26 provide statistics on plowing, source of seed, crops planted, and crop harvest, of the farmers in the survey subsamples.  They describe the general farming practices in these areas.  Although the data will not be discussed in detail in this report, it is hoped that this information will be useful for the Ministry of Agriculture and other agencies, including the Food Security Working Group in planning future activities.  Examination of the differences in subzones will provide a general picture of cropping practices that exist in the different subzones.

### 1.	Plowing

The number of farmers having project plowing and plowing from other sources done on their farm was determined from the survey.  This was then calculated as a percent of total farmers surveyed (Table 16).

Table 16   Percent of farmers having project and non-project plowing done on their farms during 2001 (BL1 – 1-2)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Percent of Farmers Having Plowing Done From: |  |  |  |  |  |
| Project |  |  |  | 46 |  | 16 | 67 |
| Non-Project |  |  |  | 68 |  | 100 | 47 |
| Average Number of Hectares Plowed per Farmer by: |  |  |  |  |
| Project |  |  |  | 0.88 |  | 0.75 | 0.90 |
| Non-Project |  |  |  | 0.67 |  | 0.70 | 0.63 |

The non-project plowing was further examined to determine what means (tractor or ox plow) were used by the farmer (Table 17).

Table 17     Percent of non-project plowing done by tractor and oxen (BL1 – 1-2)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Percent of Non-Project Plowing Done by: |  |  |  |  |  |  |
| Tractor |  |  |  | 92 |  | 100 | 82 |
| Oxen |  |  |  | 19 |  | 16 | 23 |

### 2.	Source of Seed

The source of seed for the farmer was determined for the 2000 pre-project planting year (Table 18) for the five major crop types.  The primary source was from saved, followed closely by individual purchase.  The percent of farmers planting saved seed was quite high.

Table 18     Percent of farmers that obtained seed from the following sources in 2000 (BL1 – 7-8)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Teff Seed |  |  |  |  |  |  |  |
| Save |  |  |  | 36 |  | 17 | 37 |
| Purchase |  |  |  | 35 |  | 67 | 34 |
| Assistance |  |  |  | 1 |  | 0 | 1 |
| Borrow |  |  |  | 45 |  | 17 | 46 |
| Barley Seed |  |  |  |  |  |  |  |
| Save |  |  |  | 12 |  | 12 | --- |
| Purchase |  |  |  | 79 |  | 79 | --- |
| Assistance |  |  |  | 1 |  | 1 | --- |
| Borrow |  |  |  | 10 |  | 10 | --- |
| Wheat Seed |  |  |  |  |  |  |  |
| Save |  |  |  | 10 |  | 10 | --- |
| Purchase |  |  |  | 86 |  | 86 | --- |
| Assistance |  |  |  | 0 |  | 0 | --- |
| Borrow |  |  |  | 6 |  | 6 | --- |
| Maize Seed |  |  |  |  |  |  |  |
| Save |  |  |  | 55 |  | --- | 55 |
| Purchase |  |  |  | 35 |  | --- | 35 |
| Assistance |  |  |  | 1 |  | --- | 1 |
| Borrow |  |  |  | 38 |  | --- | 38 |
| Sorghum Seed |  |  |  |  |  |  |  |
| Save |  |  |  | 71 |  | 0 | 75 |
| Purchase |  |  |  | 24 |  | 100 | 19 |
| Assistance |  |  |  | 0 |  | 0 | 0 |
| Borrow |  |  |  | 18 |  | 0 | 19 |
| Average for All Seed |  |  |  |  |  |  |  |
| Save |  |  |  | 54 |  | 80 | 32 |
| Purchase |  |  |  | 31 |  | 15 | 44 |
| Assistance |  |  |  | 2 |  | 1 | 3 |
| Borrow |  |  |  | 26 |  | 12 | 38 |

Some farmers that received project seed in 2000 also planted additional seed from other sources (Table 19).  This was less for wheat than teff and barley. No maize and legume were distributed, all came from other sources.

Table 19     Percent of farmers planting project and non-project seed 2001 (BL1 – 16)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Teff |  |  |  |  |  |  |  |
| Project |  |  |  | 67 |  | 0 | 68 |
| Non-Project |  |  |  | 45 |  | 100 | 44 |
| Barley |  |  |  |  |  |  |  |
| Project |  |  |  | 74 |  | 84 | 0 |
| Non-Project |  |  |  | 50 |  | 44 | 100 |
| Wheat |  |  |  |  |  |  |  |
| Project |  |  |  | 43 |  | 43 | --- |
| Non-Project |  |  |  | 73 |  | 73 | --- |
| Maize |  |  |  |  |  |  |  |
| Project |  |  |  | 0 |  | 0 | 0 |
| Non-Project |  |  |  | 100 |  | 100 | 100 |
| Legume |  |  |  |  |  |  |  |
| Project |  |  |  | 0 |  | 0 | 0 |
| Non-Project |  |  |  | 100 |  | 100 | 100 |

The average amount of seed planted per farmer (project and non-project seed) in 2001 is shown in Table 20a.

Table 20a     Average amount of seed (kg)  planted per farmer in 2001 (BL1 – 9-10,13)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Average Quantity per Farmer (kg) |  |  |  |  |  |  |  |
| Teff Project |  |  |  | 27 |  | 0 | 27 |
| Non-Project |  |  |  | 19 |  | 15 | 19 |
| Project + Non-Project |  |  |  | 27 |  | 15 | 27 |
| Barley Project |  |  |  | 65 |  | 65 | 0 |
| Non-Project |  |  |  | 14 |  | 13 | 16 |
| Project + Non-Project |  |  |  | 56 |  | 61 | 16 |
| Wheat Project |  |  |  | 25 |  | 25 | --- |
| Non-Project |  |  |  | 15 |  | 15 | --- |
| Project + Non-Project |  |  |  | 23 |  | 23 | --- |
| Maize Project |  |  |  | 0 |  | 0 | 0 |
| Non-Project |  |  |  | 19 |  | 6 | 19 |
| Project + Non-Project |  |  |  | 19 |  | 6 | 19 |
| Legume Project |  |  |  | 0 |  | 0 | 0 |
| Non-Project |  |  |  | 13 |  | 13 | 21 |
| Project + Non-Project |  |  |  | 13 |  | 13 | 21 |

The average planting rates of the distributed seed types were presented in the table 20b.

Table 20b     Average planting rate (kg/ha) of each type of distributed seed (BL1 – 19-21)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Average Planting Rate of Each Seed Type |  |  |  |  |  |  |
| Teff |  |  |  | 44 |  | 60 | 44 |
| Barley |  |  |  | 148 |  | 148 | --- |
| Wheat |  |  |  | 99 |  | 99 | --- |

The percent of each crop from all crops (project and non-project) in 2001and the quality of the distributed seed was rated high by the farmers for teff, barley and wheat are presented in table 20c.

Table 20c    Percent of total seed planted coming from project and non-project sources, and quality of project seed (percent from rating by farmers)  (BL1 – 15,17)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Percent of seed |  |  |  |  |  |  |  |
| Teff |  |  |  |  |  |  |  |
| Project |  |  |  | 67 |  | 0 | 68 |
| Non-Project |  |  |  | 33 |  | 100 | 32 |
| Barley |  |  |  |  |  |  |  |
| Project |  |  |  | 86 |  | 89 | 0 |
| Non-Project |  |  |  | 14 |  | 11 | 100 |
| Wheat |  |  |  |  |  |  |  |
| Project |  |  |  | 47 |  | 47 | --- |
| Non-Project |  |  |  | 53 |  | 53 | --- |
| Maize |  |  |  |  |  |  |  |
| Project |  |  |  | 0 |  | 0 | 0 |
| Non-Project |  |  |  | 100 |  | 100 | 100 |
| Legume |  |  |  |  |  |  |  |
| Project |  |  |  | 0 |  | 0 | 0 |
| Non-Project |  |  |  | 100 |  | 100 | 100 |
| Quality of Project Seed (Percent from Rating by Farmers) |  |  |  |
| Teff |  |  |  | 99 |  | 100 | 99 |
| Barley |  |  |  | 100 |  | 100 | --- |
| Wheat |  |  |  | 100 |  | 100 | --- |

### 3.	Planting

The following two Tables (21 and 22) describe the percent of farmers planting each crop, and the average hectares of each crop planted.  The source of the seed was not differentiated.  Differences can be seen in the types of crop planted in the different locations.

Table 21     Percent of farmers planting crops (BL1 – 18, I - 2)

|  |  | Planting |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Year |  | Target Areas |  | Senafe | Tsorona |
| Teff |  | 2000 |  | 29 |  | 1.7 | 47 |
|  |  | 2001 |  | 53 |  | 0.8 | 91 |
| Barley |  | 2000 |  | 35 |  | 73 | 9 |
|  |  | 2001 |  | 42 |  | 99 | --- |
| Wheat |  | 2000 |  | 18 |  | 45 | --- |
|  |  | 2001 |  | 40 |  | 95 | --- |
| Maize |  | 2000 |  | 19 |  | 0.8 | 31 |
|  |  | 2001 |  | 33 |  | 2 | 55 |
| Sorghum |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 16 |  | 0 | 28 |
| Legume |  | 2000 |  | 2 |  | 4 | 0 |
|  |  | 2001 |  | 5 |  | 12 | 0 |
| Finger Millet |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 11 |  | 0 | 19 |
| Any of All Crops |  | 2000 |  | 65 |  | 74 | 60 |
|  |  | 2001 |  | 98 |  | 100 | 96 |

Generally barley and wheat are preferred in Senafe and teff in Tsorona.

Table 22     Average hectares per farmer planted (BL1 – 18-24, I – 2-9)

|  |  | Planting |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Year |  | Target Areas |  | Senafe | Tsorona |
| Teff |  | 2000 |  | 0.5 |  | 0.4 | 0.5 |
|  |  | 2001 |  | 0.6 |  | 0.4 | 0.6 |
| Barley |  | 2000 |  | 0.5 |  | 0.4 | 0.7 |
|  |  | 2001 |  | 0.5 |  | 0.5 | --- |
| Wheat |  | 2000 |  | 0.3 |  | 0.3 | --- |
|  |  | 2001 |  | 0.3 |  | 0.3 | --- |
| Maize |  | 2000 |  | 0.5 |  | 0.3 | 0.5 |
|  |  | 2001 |  | 0.5 |  | 0.3 | 0.5 |
| Sorghum |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 0.4 |  | 0.3 | 0.4 |
| Legume |  | 2000 |  | 0.3 |  | 0.3 | --- |
|  |  | 2001 |  | 0.3 |  | 0.3 | 0.5 |
| Finger Millet |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 0.4 |  | --- | 0.4 |
| Any of All Crops |  | 2000 |  | 0.7 |  | 0.6 | 0.8 |
|  |  | 2001 |  | 0.9 |  | 0.8 | 1.0 |

### 4.	Harvest

Percent Harvested of that Planted

Crop production depends not only on the amount of land planted, but also on the amount of planted land that reaches maturity and harvest.  This is determined by many factors including pest damage and water availability.  Table 23 describes the percent of farmers whose planted fields reached harvest.  Table 24 describes the percent of planted land that reached harvest.  As expected, the two are very similar.

Table 23     Percent of farmers harvesting crops (of those that planted the crop)

(BL2 – 50-52,  I – 2-9)

|  |  | Planting |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Year |  | Target Areas |  | Senafe | Tsorona |
| Teff |  | 2000 |  | 74 |  | --- | 76 |
|  |  | 2001 |  | 97 |  | --- | 98 |
| Barley |  | 2000 |  | 73 |  | 87 | --- |
|  |  | 2001 |  | 98 |  | 98 | --- |
| Wheat |  | 2000 |  | 99 |  | 99 | --- |
|  |  | 2001 |  | 98 |  | 98 | --- |
| Maize |  | 2000 |  | 37 |  | 0 | 38 |
|  |  | 2001 |  | 64 |  | 67 | 64 |
| Sorghum |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 71 |  | 0 | 72 |
| Legume |  | 2000 |  | 0 |  | 0 | --- |
|  |  | 2001 |  | 97 |  | 100 | 0 |
| Finger Millet |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 87 |  | --- | 87 |
| Any of All Crops |  | 2000 |  | 79 |  | 86 | 73 |
|  |  | 2001 |  | 98 |  | 98 | 98 |

During 2000 only 85 percent of planted land reached harvest, while 99 percent of land reached harvest in 2001.  Maize had the lowest percent while barley and wheat had the highest percent, reflecting the relative drought resistance of each crop type.

Table 24     Percent of hectares crop harvested that were planted (BL2 – 40-46, I – 25-32)

|  |  | Planting |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Year |  | Target Areas |  | Senafe | Tsorona |
| Teff |  | 2000 |  | 71 |  | 0 | 72 |
|  |  | 2001 |  | 98 |  | 0 | 99 |
| Barley |  | 2000 |  | 63 |  | 84 | 0 |
|  |  | 2001 |  | 99 |  | 99 | --- |
| Wheat |  | 2000 |  | 99 |  | 99 | --- |
|  |  | 2001 |  | 99 |  | 99 | --- |
| Maize |  | 2000 |  | 37 |  | 0 | 37 |
|  |  | 2001 |  | 57 |  | 67 | 57 |
| Sorghum |  | 2000 |  | 0 |  | 0 | 0 |
|  |  | 2001 |  | 74 |  | 0 | 75 |
| Legume |  | 2000 |  | 0 |  | 0 | --- |
|  |  | 2001 |  | 94 |  | 100 | 0 |
| Finger Millet |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 87 |  | --- | 87 |
| Any of All Crops |  | 2000 |  | 85 |  | 87 | 84 |
|  |  | 2001 |  | 99 |  | 99 | 99 |

Production in Quintals per Hectare

Crop production can be calculated based on the land area planted (Table 25), or on the land area harvested (Table 26), depending on what the investigator is interested in looking at.

Table 25     Average quintals per hectare crop production from planted fields (BL1 – 18-24, I – 2-9)

|  |  | Planting |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Year |  | Target Areas |  | Senafe | Tsorona |
| Teff |  | 2000 |  | 3.2 |  | 0.0 | 3.2 |
|  |  | 2001 |  | 2.4 |  | 0.0 | 2.4 |
| Barley |  | 2000 |  | 3.1 |  | 4.2 | 0.0 |
|  |  | 2001 |  | 4.2 |  | 4.2 | --- |
| Wheat |  | 2000 |  | 2.9 |  | 2.9 | --- |
|  |  | 2001 |  | 2.2 |  | 2.2 | --- |
| Maize |  | 2000 |  | 1.1 |  | 0.0 | 1.1 |
|  |  | 2001 |  | 2.0 |  | 0.2 | 2.0 |
| Sorghum |  | 2000 |  | 0.0 |  | 0.0 | 0.0 |
|  |  | 2001 |  | 2.1 |  | 0.0 | 2.1 |
| Legume |  | 2000 |  | 0.0 |  | 0.0 | 0.0 |
|  |  | 2001 |  | 0.3 |  | 0.3 | 0.0 |
| Finger Millet |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 3.2 |  | --- | 3.2 |
| Any of All Crops |  | 2000 |  | 2.8 |  | 3.5 | 2.4 |
|  |  | 2001 |  | 2.6 |  | 3.2 | 2.2 |

If many fields were a failure, as in 2000, there will be a large difference between the two methods.  If most or all fields reached harvest, as in 2001, then there will be little or no difference.

Table 26     Average quintals per hectare crop production harvested fields (BL2 – 40-46, I – 25-32)

|  |  | Planting |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Year |  | Target Areas |  | Senafe | Tsorona |
| Teff |  | 2000 |  | 4.5 |  | --- | 4.5 |
|  |  | 2001 |  | 2.4 |  | --- | 2.4 |
| Barley |  | 2000 |  | 5.0 |  | 5.0 | --- |
|  |  | 2001 |  | 4.3 |  | 4.3 | --- |
| Wheat |  | 2000 |  | 2.9 |  | 2.9 | --- |
|  |  | 2001 |  | 2.2 |  | 2.2 | --- |
| Maize |  | 2000 |  | 3.0 |  | --- | 3.0 |
|  |  | 2001 |  | 3.5 |  | 0.3 | 3.5 |
| Sorghum |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 2.8 |  | --- | 2.8 |
| Legume |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 0.3 |  | 0.3 | --- |
| Finger Millet |  | 2000 |  | --- |  | --- | --- |
|  |  | 2001 |  | 3.7 |  | --- | 3.7 |
| Any of All Crops |  | 2000 |  | 3.3 |  | 4.0 | 2.8 |
|  |  | 2001 |  | 2.6 |  | 3.3 | 2.2 |

### 5.	Pests and Crop Quality

Table 27a     Pest and Natural Problems reported by Farmers

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Percent of Farmers Reporting Damage from: |  |  |  |  |  |
| Insects |  |  |  | 21 |  | 1 | 35 |
| Birds |  |  |  | 3 |  | 0 | 5 |
| Disease |  |  |  | 16 |  | 1 | 27 |
| Animals |  |  |  | 6 |  | 0 | 10 |
| Percent of Farmers Reporting Pest Damage |  | 31 |  | 2 | 52 |
| Percent of Farmers Reporting Weeds |  |  |  |  |  |  |  |
|  |  |  |  | 4 |  | 0 | 6 |
| Percent of Farmers Reporting Damage from: |  |  |  |  |  |
| Hail |  |  |  | 4 |  | 8 | 1 |
| Wind |  |  |  | 3 |  | 6 | 1 |
| Excess Water |  |  |  | 41 |  | 54 | 31 |
| Flood |  |  |  | 20 |  | 6 | 31 |
| Percent of Farmers Reporting Natural Damage |  | 52 |  | 72 | 36 |

The crop quality was rated the average of 53 percent. A total of 24 percent of the farmers reported that they will have sufficient seed to save some for planting next year.

Table 27b     Quality of harvested crop (I – 11,13)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Crop quality - percent rating by farmers |  |  |  |  |  |  |
| Teff |  |  |  | 62 |  | --- | 62 |
| Barley |  |  |  | 56 |  | 56 | --- |
| Wheat |  |  |  | 64 |  | 64 | --- |
| Maize |  |  |  | 47 |  | 67 | 46 |
| Sorghum |  |  |  | 49 |  | --- | 49 |
| Legume |  |  |  | 34 |  | 34 | --- |
| Finger Millet |  |  |  | 58 |  | --- | 58 |
| Percent of farmers who consider quality good enough for Seed |
| Teff |  |  |  | 58 |  | 0 | 58 |
| Barley |  |  |  | 33 |  | 33 | --- |
| Wheat |  |  |  | 33 |  | 33 | --- |
| Maize |  |  |  | 21 |  | 0 | 22 |
| Sorghum |  |  |  | 10 |  | 0 | 10 |
| Legume |  |  |  | 10 |  | 7 | 100 |
| Finger Millet |  |  |  | 5 |  | --- | 5 |

### 6.	Farmer Needs

Farmers were asked what their most pressing needs were (Table 28).  Not unexpectedly, as this was a seed and plowing project, the highest percentage listed plowing and seed distribution.

Table 28     Percent of farmers stating need for the following (BL2 – 38-39)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Percent of Farmers Stating Need for: |  |  |  |  |  |  |  |
| Plowing |  |  |  | 50 |  | 63 | 0 |
| Seed |  |  |  | 16 |  | 18 | 7 |
| Water Diversion |  |  |  | 1 |  | 0 | 7 |
| Oxen |  |  |  | 7 |  | 2 | 29 |
| Other Inputs |  |  |  | 13 |  | 16 | 0 |
| Wells or Pumps |  |  |  | 1 |  | 2 | 0 |
| Other Animals |  |  |  | 11 |  | 0 | 57 |

Next in priority, however, were those needs relating to water, namely water diversion systems and oxen to repair damaged systems.  This was followed by wells or pumps for irrigation.  It is clear that provision of water to crops is high on the list of farmer concerns.

## I.	Livestock

Most target farm families include both crop production and raising livestock in their farming activities.  A total of 74 percent of surveyed farmers reporting owning livestock (Table 29).  This percentage is highest in Senafe (75 percent) and lowest in Tsorona (74 percent).

Table 29     Percent of families owning livestock (BL2 - 25)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Percent of Surveyed Families Owning Livestock |  |  |  |  |  |
|  |  |  |  | 74 |  | 75 | 74 |

The seven common animal types are cattle, donkey, goats/sheep, chicken, camel, bee and horse/mule.  Cattle, donkey, goats/sheep, chicken and bee were highest in Senafe and lowest in Tsorona.  But, camel and horse/mule were only reported in Tsorona and nothing in Senafe.

Table 30     Percent of families with each type of livestock (BL2 – 26)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Percent of Surveyed Families with: |  |  |  |  |  |  |  |
| Cattle |  |  |  | 63 |  | 67 | 60 |
| Donkey |  |  |  | 55 |  | 61 | 50 |
| Goats / Sheep |  |  |  | 37 |  | 44 | 33 |
| Chicken |  |  |  | 9 |  | 11 | 7 |
| Camel |  |  |  | 4 |  | 0 | 7 |
| Bee |  |  |  | 4 |  | 6 | 2 |
| Horse / Mule |  |  |  | 1 |  | 0 | 1 |

The most populous animals, as a percent of the total number of animals reported, were goats/sheep, accounting for 46 percent of all animals (Table 31).  Cattle were next with 32 percent, donkey was with 15 percent, chicken with 7 percent, camel and bee were quite similar with 2 and 11 respectively, and the alst horse/mule was 0.1 percent.

Table 31     Distribution by Type of Livestock (BL2 –27)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Percent of Total Animals that are: |  |  |  |  |  |  |  |
| Goats / Sheep |  |  |  | 44 |  | 53 | 37 |
| Cattle |  |  |  | 31 |  | 23 | 38 |
| Donkey |  |  |  | 15 |  | 14 | 16 |
| Chicken |  |  |  | 6 |  | 8 | 5 |
| Camel |  |  |  | 2 |  | 0 | 3 |
| Bee Hive |  |  |  | 1 |  | 2 | 1 |
| Horse / Mule |  |  |  | 0.12 |  | 0.08 | 0.15 |

The average number of animals per household that has that type of animal is shown in Table 32.  Goats/sheep were the highest, with 5.1 per family and horse/mule were the least with an average of 1.0 per family.  It must be remembered that the target farmers likely put more emphasis on crop production, and these numbers would not be representative of those farmers that emphasize livestock more than crop production.

Table 32     Number of animals per family for each animal type (BL2 – 25)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Average Number of Amimal Type per Family that have Animal Type |  |  |  |
| Goats / Sheep |  |  |  | 5.1 |  | 6.1 | 4.3 |
| Chicken |  |  |  | 3.1 |  | 3.5 | 2.7 |
| Cattle |  |  |  | 2.1 |  | 1.7 | 2.4 |
| Camel |  |  |  | 1.8 |  | 1.0 | 1.9 |
| Bee |  |  |  | 1.6 |  | 1.6 | 1.6 |
| Donkey |  |  |  | 1.2 |  | 1.1 | 1.2 |
| Horse / Mule |  |  |  | 1.0 |  | 1.0 | 1.0 |
| Total |  |  |  | 4.1 |  | 4.6 | 3.8 |

Farmers were asked what the source of feed for their livestock was, and if they migrated to obtain feed (Table 33).  A total of 93 percent reported their source of livestock feed coming from crop residue from their fields, and 87 percent reported obtaining feed from the surrounding areas.

Table 33     Source of livestock feed 2000 (BL2 – 29-30)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Percent of Farmers had Source of Feed from: |  |  |  |  |  |
| Crop Fields |  |  |  | 93 |  | 95 | 92 |
| Surrounding Areas |  |  |  | 87 |  | 100 | 77 |
| Migration |  |  |  | 1 |  | 0 | 2 |
| Purchased Feed |  |  |  | 31 |  | 32 | 26 |
| Percent of Families Migrating for Animal Feed |  |  |  |  |  |
|  |  |  |  | 2.3 |  | 0.6 | 3.4 |
| Average Migration Time Length (Months) |  |  |  |  |  |  |
|  |  |  |  | 4.2 |  | 5.0 | 4.1 |

However, the pattern was reversed for the two sources when considering location.  In Tsorona, crop residue was the primary source, while in Senafe, most feed was obtained from surrounding areas.  Purchasing feed was most common in Senafe than in Tsorona.

The differentiation between the categories of surrounding areas and highlands was not always clear to the surveyed farmers.  Surrounding areas was intended to mean within a few kilometers, and highlands to mean areas that would require travel of days or weeks.  Thus, the data does not correlate well with the responses to questions on migration.

## J.	Socio-Economic Profile of Surveyed Families

The total percent of displaced  families by war was very high (93) and the average displacement time length was almost 12 months (1 year).  The percent of displaced families with livestock was 74 and the percent of non-displaced with livestock was 80 percent. Not much difference between the two subzones was seen (Table 34a).  The average number of livestock per family of displaced families was around 4 and the average number of livestock per family of non-displaced families was 3.2.

Table 34a     Displacement and Livestock (percent of farmers)  (BL2 – 28,34)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Percent of Families Displaced by War |  |  |  |  |  |  |  |
|  |  |  |  | 93 |  | 85 | 99 |
| Average Displacement Time Length (Months) |  |  |  |  |  |
|  |  |  |  | 11.7 |  | 11.4 | 11.9 |
| Percent of Displaced Families with Livestock |  |  |  |  |  |
|  |  |  |  | 74 |  | 74 | 74 |
| Average Number of Livestock per Family of Families Displaced |  |  |  |
|  |  |  |  | 3.9 |  | 4.5 | 3.6 |
| Percent of Families Not-Displaced with Livestock |  |  |  |  |  |
|  |  |  |  | 80 |  | 81 | 75 |
| Average Number of Livestock per Family of Families Not-Displaced |  |  |  |
|  |  |  |  | 3.2 |  | 3.2 | 2.8 |

The average family size for all surveyed farm families was 5.3 (Table 34b).  Senafe and Tsorona reported with 5.4 and 5.3family members respectively. A total of 13 percent of the families were female-headed.  The average family land size was 1.1 hectares, and was least inSenafe with 0.9 ha and most in Tsorona 1.3 ha.

Table 34b     Family statistics (BL2 – 31-32, I – 23)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Average Family Size (Number of Family Members) |  |  |  |  |  |
|  |  |  |  | 5.3 |  | 5.4 | 5.3 |
| Percent Female-Headed households |  |  |  |  |  |  |  |
|  |  |  |  | 13 |  | 18 | 9 |
| Average Family Land Size (Hectares) |  |  |  |  |  |  |  |
|  |  |  |  | 1.1 |  | 0.9 | 1.3 |

Farmers were asked if there had been a death in the family during the last 3 years, and what the cause of death was (Table 35).  A total of 11 percent of families reported a death.

Table 35     Family death statistics during past three years (BL2 – 35-36)

|  |  |  |  | Total Debub |  | Sub-Zone |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target Areas |  | Senafe | Tsorona |
| Percent of Families with Death During Past Three Years |  |  |  |
|  |  |  |  | 4 |  | 4 | 4 |
| Percent of Deaths Reported were in the age of: |  |  |  |  |  |
| <= 5 |  |  |  | 42 |  | 60 | 29 |
| 6 - 16 |  |  |  | 29 |  | 20 | 36 |
| >16 |  |  |  | 29 |  | 20 | 36 |
| Percent of Total Death as a Result of: |  |  |  |  |  |  |  |
| Illness |  |  |  | 69 |  | 60 | 72 |
| Other |  |  |  | 15 |  | 10 | 17 |
| Accident |  |  |  | 9 |  | 10 | 9 |
| War |  |  |  | 7 |  | 20 | 2 |

Of the deaths reported that specified if the death was of below or eaual to the age of 5, or from the age of 6 to 16, or above the age of 16, and the percents were 43, 30 and 30 accordingly.  The cause of most deaths was reported to be from illness of some type (69 percent), 15 percent from others, 9 percent from accident and 7 percent from war.

## K. 	Partnerships

### 1.  	Introduction

Developing partnerships in project implementation, and building the capacity of the partners is a key activity of CARE Eritrea.  This project worked through two partners, Vision Eritrea (a local NGO) and the Ministry of Agriculture, to improve the food security of the war and drought-affected families in Debub zone.

### 2.  	Vision Eritrea

CARE and Vision Eritrea began a working relationship during the recently completed Northern Red Sea Zone Emergency Drought Assistance project. This relationship has continued during the current Debub project, with capacity building activities expanding on those begun earlier.  These activities have focused on more intensive activity planning and monitoring, finance management, and report writing.  CARE staff have worked closely with Vision Eritrea staff in expanding skills in these areas through practical assistance on real project activities.  A formal financial management workshop is scheduled for mid November, and a project planning and management workshop in early December.

### 3.  	Ministry of Agriculture

The Ministry of Agriculture is an important partner in this project, and has taken the lead in planning and implementing the plowing and seed distribution activities on the ground.  The MOA is also directly involved in the survey activities through training and monitoring of the enumerators.  Vision Eritrea is working closely with the MOA to demonstrate and ensure complete and accurate record keeping and accountability.

## L.  	Monitoring

Monitoring of project activities is being accomplished by frequent review of the activity plan, regular visits to field sites, and close examination of all data recording documents.

The activity plan, with start and end dates for each activity, is used as a checklist to ensure timely completion of each activity.  Regular visits to field sites were made during plowing and seed distribution to ensure proper implementation and documentation of these activities.

During the growing season, bi-monthly visits are being made to each sub-zone to observe and monitor crop growth and environmental conditions, and to talk with farmers.  These observations are being documented and will be used to assist in interpretation of crop production data.

## M.  	Impact

### 1.  	Factors affecting impact

Crop production, and ultimately food security of farm families, is determined by several factors.  These are:

- How many hectares were planted (from both land plowed and seed distributed) as a result of this project

- Amount of rainfall

- Crop damage by insects, diseases, birds, etc.

- How many hectares were harvested, both total and per family

- How much crop was harvested per hectare

### 2.  	Determining Impact

The general approach will be to compare crop production of the project year and the previous year with the annual crop food needs.  This data will come from the two surveys.  Following data analysis, the results will be reported and discussed in the final project report.

# IV.  	PROBLEMS ENCOUNTERED AND CORRECTIVE PROCEDURES

Delay of Rainfall – Rainfall and planting in the target areas normally begins in April and continues through August, with harvest in September.  This season the rains did not start until June and would have resulted in the crop types that were originally planned (sorghum and millet) not having sufficient time to mature before the end of the rains.  Barley and wheat, which require a shorter time to maturity, were substituted for sorghum and millet to increase the chances of a successful harvest.

Tractor Problems – The MOA in Debub has a limited number of tractors. Additional tractors were brought in from Gash Barka to assist in completing the plowing in time for planting.  Mechanical breakdowns of MOA tractors resulted in additional delays.  The MOA, therefore, contracted with private tractor owners to provide additional plowing, resulting in timely completion.

Landmines – Landmines were a source of constant concern when plowing fields.  The MOA coordinated closely with local government in selecting field that were considered safe, and no landmine incidents occurred.  This threat did, however, require changes from the original plan in selection of land to be plowed. Some of the more productive farmland could not be included in the plowing this year.

# V.  	FINANCIAL REPORT

Financial report will be submitted by CARE USA headquarters.