CARE International in Vietnam

Increase Local Disaster Risk Management Capacity in Thanh Hoa Province

Final Project Evaluation Report

Richard Rastall, Nguyen Thi Thu Que & Han Van Khoat

Ha Noi, January 2010

Executive Summary

This report documents the findings of an independent evaluation team contracted to review the relevance, efficiency, effectiveness, impact and sustainability of the ‘Increase Capacity for Disaster Risk Management in Thanh Hoa Province’ Project, funded by the European Commission Humanitarian Aid department (ECHO). The project was operational for 16.5 months between September 2008 – January 2010 and its main objective was ‘to improve Disaster Preparedness, Mitigation and Response of coastal communities in Thanh Hoa by enhancing capacities of communities, local government and mass organisations’.

The project was comprised of four key result areas:

- Improved DRM capacity of the provincial, district and commune FSCBs and improved EWS

- Exploration and dissemination of community mitigation options

- Increased awareness amongst communities and school students

- Increased community resilience to disasters through implementation of mitigation options

Overall it is clear that the project was extremely relevant given the vulnerability of coastal communities and the overall impact of disasters on socio-economic development in the province. The project endorsed a highly participatory approach in design and the resultant interventions were generally highly appropriate, and they have ultimately contributed to reducing the vulnerability of coastal communities to natural disasters (especially storms and coastal surges). There was a fault in the design of intervention area 1 as the originally envisaged Early Warning System (EWS) was in fact deemed to be too expensive and inappropriate based on local capacities and needs but otherwise all other activities and result areas were appropriate, relevant and contributed towards the overall goal.

The project has been managed efficiently, using an appropriate project implementation structure which has ensured the delivery of a wide range of important benefits in a relatively short period of time. It is largely due to this implementation structure and the long-standing working relationship between CARE and the authorities and Thanh Hoa that the project was able to adjust to the above oversight in design and re-allocate budgets in a more appropriate manner.

Assessing the impact and effectiveness of the interventions was challenging for the evaluation team since many of the activities have only just been completed and in a number of instances are infrastructure projects or distributions, so it remains to be seen exactly how these will be maintained, used and their specific impacts. This comment is particularly relevant to many of the hard deliverables towards setting up a more effective EWS in result area 1 and construction of evacuation centres, roads, and ships harbours in result area 4.

In result area 2, a key aspect of the project was the introduction of participatory CBDRM processes leading to the development of Disaster Risk Management Plans (DRMPs) for all villages and communes in the target area. The project achieved this through the establishment of a provincial Community-based Disaster Risk Management (CBDRM) training centre at the provincial Red Cross headquarters and the subsequent roll out of CBDRM trainings for Flood and Storm Control Boards at provincial, district and commune levels. It is a great achievement for the project to deliver so many DRMPs and they have now not been approved at district level, however as will be outlined in this report there were some fundamental weaknesses with the CBDRM process and thus there are lessons to be learned for future interventions of type. In particular it would appear that insufficient attention was paid towards the proper training and support of facilitators at the grassroots level and that this in combination with the need for greater clarity and more detailed formats for documenting/reporting the CBDRM process has affected the quality of the DRMPs themselves to some extent which do not seem to provide evidence of the application of the participatory processes taught during the trainings.

The project did however have considerable success in terms of awareness-raising under result area 3. It was evident from interviews and meetings in the field with beneficiaries and stakeholders that the project was having a positive impact in terms of increasing the awareness of local people of disasters, their impacts and what they can do as individuals to prepare for and mitigate these impacts. The Training of Trainers approach adopted by the project seems to have been very effective and its sustainability almost assured by the fact that such activities have now been prioritized in the district Socio-economic Development Plan (SEDP) and furthermore show great potential for replication within Vietnam’s own institutional framework i.e. the role of project partner’s, the WU in performing their mandate are likely to maintain disaster oriented health and safety information sessions under the framework of their usual monthly meetings. Similarly, the high quality IEC materials and trainings of teachers in how to deliver classes and activities for schoolchildren is now incorporated within the provincial syllabus and will therefore continue. This is largely thanks to the active involvement of the Department of Education and Training (DoET) in the project and is a great achievement.

Component 4 concentrated on the provision of mitigation options to the disaster affected communities and was based to some extent on recommendations from technical studies carried out under result area 2 and/or agreed as priorities during the CBDRM planning process. Mitigation options included various installations and construction projects to improve water supply and sanitation, including the provision of water jars to poor households. Many of these were humanitarian benefits deliberately addressing very relevant short term needs. Other deliverables included two short evacuation roads, two evacuation centres, a ships harbour for fishermen and 6 seawater interception sewers. It is rather difficult to assess the full impact and effectiveness of these interventions but they are likely to be of considerable benefit to the communities as a whole. Furthermore it was interesting to note that in the case of the road, the community added-value to the investment by contributing both financially and through in-kind labour to the construction, monitoring and supervision of the activity.

The project also piloted the introduction of certain saline–tolerant rice varieties in all three project communes. Although ideally longer term monitoring of yields is required the early indications are that this has been a highly successful intervention and resolved a major livelihood problem for local farmers with a significant increase in yields as well as substantial increases in profits based on increased productivity, lower production costs and higher market price of the new varieties.

The project achieved an enormous amount in such a short period of time and we can be certain that it is having a positive impact on local coastal communities in terms of reducing their vulnerability to natural disasters. However as with any project it has had its challenges and weaknesses in particular with respect to building capacity in CBDRM planning – this it would appear is something that is going to require further investment and a considerably longer timeframe to change significantly, especially given the nature of top-down development planning and budgeting in Vietnam. The component has however produced a number of very useful lessons learned and this evaluation report includes a range of recommendations for improving this CBDRM planning process. Other key recommendations include suggestions to replicate the project implementation structure, the ToT approach and in particular the involvement of DoET in awareness-raising and training for DRM, and the saline-tolerant rice model. The streamlining of administrative procedures for contracting communities in the construction, monitoring and supervision of infrastructure investments.

Table of Contents

1.	Background	3

1.1	Project Overview	3

1.2	Overview of the Evaluation	3

2.	Description of the Methodologies Used	3

2.1	Overview	3

2.2	Desk Review	3

2.3	Fieldwork	3

2.3.1	Meetings with Project Partners & Stakeholders	3

2.3.2	Household Interviews	3

2.4	Discussions with CARE Project Staff	3

2.5	Data Analysis	3

3.	Evaluation Findings	3

3.1	Relevance of the Intervention	3

3.1.1	The Project Design Process	3

3.1.2	Project Scope, Size and Timeframe	3

3.1.3	Project Implementation Structure	3

3.1.4	M&E Framework	3

3.2	Efficiency	3

3.3	Effectiveness & Impact	3

3.3.1	Result Area 1:  Improved DRM/EWS capacity of provincial, district, commune government FSCB standing Office Staff	3

3.3.2	Result Area 2 – Community Mitigation Studies	3

3.3.3	Result Area 3:  Increased Awareness	3

3.3.4	Result Area 4:  Increased community resilience to disasters	3

3.4	Sustainability	3

4.	Lessons Learned	3

5.	Recommendations	3

Annex 1: Evaluation Work Plan	3

Annex 2:  TORs of the Evaluation	3

Annex 3:  Lists of those Interviewed	3

List of Acronyms

AEC		Agricultural Extension Centre

CBDRM	Community Based Disaster Risk Management

DARD		Department of Agriculture and Rural Development

DIPECHO	European Commission Disaster Preparedness Programme

DMWG		Disaster Management Working Group

DoET			Department of Education and Training

DoIT			Department of Industry and Trade

DRM		Disaster Risk Management

DRR 		Disaster Risk Reduction

DRMP		Disaster Risk Mitigation Plan

EC 			European Commission

EWS			Early Warning System

FSCB		Flood and Storm Control Board

HVCA		Hazards, Vulnerabilities and Capacities assessments

IEC 		Information, Education and Communication

INGOs		International Non-governmental Organisations

JANI			Joint Advocacy Network Initiative

KAB			Knowledge, Attitude and Behaviours

M&E			Monitoring and Evaluation

PC			People’s Committee

PRA			Participatory Rural Appraisals

SEDP		Socio-economic Development Plan

SRC			Spanish Red Cross

SWOT		Strength, Weakness, Opportunity and Threats

ToT			Training of Trainers

WHO			World Health Organisation

WU			Women’s Union

Acknowledgements

The evaluation team would like to acknowledge the help and support provided by the CARE Project Manager Tran Thanh Thuy and CARE DRM Coordinator Marten Mylius who have been very helpful in helping us to complete this evaluation. We would also like to acknowledge the support of local project partners for participating so actively in the review mission in the field and in particular to the staff of Hau Loc District People’s Committee, Red Cross, Health Department, DARD and DoET who assisted the national consultants in the field by conducting interviews with household beneficiaries in order to gain information from a larger sample size.

Disclaimer

This document has been produced with the financial assistance of the European Commission. The views expressed herein should not be taken, in any way, to reflect the official opinion of the European Commission.

.

# Background

## 1.1	Project Overview

CARE International in Vietnam received funding from the Disaster Preparedness budget line of the European Commission Humanitarian Aid Department (ECHO) to implement a project entitled ‘Increase Local Capacity in Disaster Risk Management in Thanh Hoa Province’. The project was implemented between September 2008 and January 2010, primarily focusing on the coastal district of Hau Loc and Da Loc, Hai Loc and Hung Loc communes.

Thanh Hoa province is located in the North Central Coast Region of Vietnam and the rationale for the project was that local communities, particularly in the target district of Hau Loc suffer from the combined impact of storms, floods, drought, landslide, and saline water intrusion (caused by storm surge). These multiple hazards affect the poorer, more marginalized and vulnerable groups disproportionately and have negative repercussions in terms of poverty alleviation and socio-economic development in the province more broadly, Thanh Hoa being one of the poorer provinces in the country. Whilst the provincial and local authorities Disaster Risk Management (DRM) institutions are well established, pre-project needs assessments and discussions revealed that a distinct lack of capacity remains in this crucial area. Specific weaknesses identified included deficiencies in the areas of comprehensive disaster risk management planning and implementation, information management, and Early Warning Systems (EWS) that do not reflect local needs, as well as a general lack of awareness amongst local communities and a resultant lack of proactive autonomous disaster preparedness.

Fig 1:  Thanh Hoa Location

The project therefore sought to address these problems by working with a wide range of project partners and stakeholders including local government and relevant authorities including the People’s Committees (PC), Department of Agriculture and Rural Development (DARD), The Flood and Storm Control Boards (FSCB), and Department of Education and Training (DoET) at all levels (provincial, district and commune levels) and local mass organizations, particularly the Women’s Union (WU) and the provincial Red Cross (RC). A key feature of the project was the highly participatory nature of project planning and implementation, involving communities, local people and in particular those groups within local society most adversely impacted and vulnerable to natural disasters.

Fig 2:  Hau Loc District and Target Communes

The project aimed ‘to improve Disaster Preparedness, Mitigation and Response of coastal communities in Thanh Hoa by enhancing capacities of communities, local government and mass organisations. The project was comprised of four components or result areas:

- Improved DRM capacity of the provincial, district and commune FSCBs and improved EWS

- Exploration and dissemination of community mitigation options

- Increased awareness amongst communities and school students

- Increased community resilience to disasters through implementation of mitigation options

## 1.2	Overview of the Evaluation

The purpose of the evaluation was to assess the outcomes of the activities indicated in the project logical framework and their subsequent contribution towards achieving the project’s overall objective to reduce household vulnerability to natural disasters in Thanh Hoa Province through the enhancement of early warning systems, natural disaster preparedness, and by building the capacity of households, communities, mass organisations, local government (Provincial, District and Commune levels) to reduce the impact of recurrent disasters.  The evaluation was to consider:

- Relevance / appropriateness of the project design, to what extent the project is suited to the particular needs, expectations and priorities of the target communities, local authority, implementing partners and the donor

- Efficiency in use of resources, to what extent the project used the resources in the most economical manner to achieve its objectives

- Effectiveness and quality of project interventions, did the activities achieve satisfactory results in relation to stated objectives.

- Impact, are the results of the intervention ‐ intended and unintended, positive and negative ‐ including the social, economic, environmental effects on individuals, communities and institutions.

- Sustainability, are the activities and their impact likely to continue when external support is withdrawn, and will it be more widely replicated or adapted

The following sections of the report elaborate how a methodology was developed to incorporate the above aspects of the evaluation whilst at the same time remain participatory in nature. The subsequent ‘evaluation findings’ section is also structured around these five key criteria.

# Description of the Methodologies Used

## 2.1	Overview

The evaluation team reviewed project documents in addition to undertaking a field mission (between 23rd – 31st December, 2009) which consisted of discussions and interviews with key project beneficiaries, partners and stakeholders at village, commune, district and provincial level. These primarily entailed collecting qualitative information about project successes, weaknesses and lessons learned as perceived by the partners and stakeholders. It should be noted that the approach and key questions in these discussions differed each time according to the involvement of different stakeholders at the various levels in different activities.

Since the project emphasized DRM capacity development, a short questionnaire was also developed in order to glean in slightly more quantitative terms some analysis of the training received by local authorities and mass organizations.

In addition, the evaluation team also conducted semi-structured household interviews with household level direct and indirect beneficiaries. The interviews followed a questionnaire which collected data on Knowledge, Attitudes and Behaviours (KAB), this being the focus of component 3 whilst also collecting information on the dissemination and impacts of mitigation options as well as community perceptions of the community-based DRM planning process.

## 2.2	Desk Review

The evaluation team began the assignment with a detailed study of information contained in project documents including a desk‐based review of the:

- Project Needs Assessment

- Original Project Proposal to DIPECHO (and subsequent revision based on implementation progress)

- Project Logical Framework (LF) & Work Plan

- Project Activity and Technical Reports

- Project Quarterly and Annual Reports

The information contained in these documents allowed the team to build up a good understanding of the project’s objectives, components, and specific activities as well as an indication of how the project was designed, what alterations or refinements were made, how the money was spent, how partners were involved in project coordination/implementation (institutional arrangements), key issues affecting implementation and specific outputs and/or results/impacts of particular activities.

The review of these documents helped the team to identify the information needed from beneficiaries and stakeholders in order to objectively verify the satisfactory completion of project outputs as well as what the processes were in getting there and the outcomes or impacts of those activities as measured against the intended project purpose and goals.

## 2.3	Fieldwork

### 2.3.1	Meetings with Project Partners & Stakeholders

The project included a number of components and as a consequence worked with different government departments and line agencies and mass organizations from village, commune, district and provincial levels. The team consulted project partners at all levels within the scope of the evaluation mission with the approach differing slightly according to their role and involvement in particular project components and levels of capacity and understanding of project planning and management.

At all meetings, the evaluation team facilitated a group discussion with relevant partners and stakeholders and employed an adapted Strengths, Weaknesses, Opportunities and Threats (SWOT) exercise such that Strengths, Weaknesses and Key Lessons Learned were extracted.  These group discussions were then followed up with more in-depth one-to-one interviews to ensure the evaluation team captured the opinions of all partners and stakeholders and allowed for more detailed discussion of particular components (since different components involved different partners, this may not fully emerge during a group discussion). Participants who had specifically received training by the project also completed a capacity development assessment questionnaire.

Provincial Level: Meetings at provincial level with Provincial PC, DARD, FSCB, DoET and WU representatives covered all project components as well as discussions relating project appropriateness, relevance, institutional arrangements and general project management and delivery. The meetings were followed up with in-depth interviews with:

- FSCB - particularly focused on component/result area 1 i.e. the extent to which FSCB staff had increased capacity and confidence in DRM planning and implementation as a result of the training provided and further on-the-job learning opportunities. How has this affected service delivery elsewhere in the province? What challenges does the FSCB face in rolling out these new approaches and skills? Such questions of impact and sustainability were central to the discussions.

- DoET - focused on result area 3 as this government department was primarily involved in the awareness and education component, although the training provided within result area 1 was also of some interest in order to see to what extent the training and training centre developed and implemented by the project had been embraced by the government line agency responsible for education and public sector training.

- Red Cross – the RC were integral to this project as key partners and particularly important to the success of result area 1 in building the DRM capacity of local authorities and establishing the training centre. The evaluation team focused on gathering information on their experiences of working with CARE as a partner as well as their perceptions on how the training courses and capacity building initiatives went (successes, challenges etc). What does the future hold for continued progress in the field of DRM capacity building? Will there be repeat trainings? Impacts of the training? How is/will the training centre be used?

District Level: Discussions at the district level would be particularly crucial as so often in Vietnam, and in particular for area-based NGO development projects, district level partners and stakeholders are something of a missing link in the process of institutional capacity building. In the experience of the evaluation team, frequently great successes may be achieved at the grassroots (commune/village) level in employing participatory approaches, however their wider uptake and ultimately their sustainability is frequently constrained by the lack of engagement with district level institutions who have not been closely involved in project capacity building and therefore lack the capacity themselves as well as the intimate knowledge of the benefits of such approaches in order that budgets are allocated appropriately and that they are endorsed in the medium to long term. Discussions with district authorities (DARD, District Agricultural Extension Centre (AEC), FSCB, DoET, DoIT and WU) would be similar to above with the province but with an acknowledgement of the role of the district in the institutional hierarchy as coordinators of provincial policy and development plans. In depth interviews were held with:

- FSCB – As with provincial level.

- AEC – This interview particularly focused on result area 2 as this was the only stakeholder really intimately involved with the agricultural study. This interview would extract useful information on local perceptions of the technical study implemented by the project. Was it relevant? Did it teach them anything new? Were the proposed mitigation measures appropriate, realistic and viable options? How have the results been used in redefining government agricultural research and development support programmes? These would all be important questions in determining the success of the intervention.

- DoET – The evaluation team was keen to understand DoET’s role as they organized and supported training for students on DRM (utilizing the trained teachers, trained by the RC). DoET then subsequently integrated the training within the school curricula.

- DoIT – The DoIT were involved in planning for the project’s infrastructural investments such as the ship locks, evacuation centre, and 6 seawater intercepting sewers. Were there any problems with these infrastructural projects and what has been their impact on the community?

- District Health Centre – The project trained health centre and WU staff in order that they could subsequently deliver information sessions on first aid, health and hygiene issues in order that local people are better prepared for disasters and can take action of their own accord to reduce impacts on their families and vulnerability. What has been the impact of these sessions on awareness and health within communities, eg. any reductions in eye infections, diarrhea and other health problems often associated with dirty water?

- WU – the WU was an important project implementation partner and beneficiary and in-depth discussions focused on the quality of training delivered to WU staff and members on DRM and related hygienic practice and disease prevention in result area 1 and the extent to which the provincial WU were aware of the impacts of this Training of Trainers (ToT) initiative and were able to replicate or develop roll-out programmes for non-project beneficiary areas within the district.

Commune/Village Level: Meetings were held with commune officials and a sample of village leaders.  It is at the commune/village level that it is generally possible to see in a greater level of detail project impacts, successes and challenges on the ground. These meetings were highly useful and allowed the evaluation team to focus on very specific activities with people who are generally much more involved with project implementation and have a much greater stake than those at higher levels because these are the people whose direct constituents and friends are genuinely affected by the occurrence of natural disasters. Following the group discussion, in-depth interviews were held with:

- FSCB – As with above, the extent to which capacity in CBDRM and HVCA had been developed. There were a range of interventions however which took place specifically at the commune level and involved the FSCB and thus the interviews also focused on their involvement in and impact of the CBDRM planning process.

- Commune health stations - In order to assess the effectiveness/impact of awareness campaigns on commune health problems and statistics particularly as a key project activity was the information sessions for women on disaster risk management and hygiene and safety.

- WU – Assessing the impacts on women and particularly poor women in the commune.

- Schools – A set of key project activities focused on ToT sessions for teachers so that they could then go and deliver DRM awareness and education sessions in schools. What has been the impact of these sessions in terms of increasing the awareness of schoolchildren?

### 2.3.2	Household Interviews

The evaluation team spent a day on training 6 selected project partner staff from district level in how to carry out a household survey. The training included a classroom session on the general concept of project evaluation, evaluation methods and tools (basic PRA techniques) before presenting the team’s specific approach to this assignment, in particular providing training on how to conduct and complete the household questionnaire and data entry.  With the assistance of these interviewers, the evaluation team intended to interview approximately 60 households. It was stipulated that a high percentage of interviewees should be poor women since these were identified as a particularly vulnerable target group. In this way it was hoped to achieve a reasonable sample size within the relatively short timeframe available for carrying out the evaluation.

The project had no particular baseline dataset and in any case the majority of project interventions either focused on hard deliverables (such as the development of DRM plans, construction of water tanks and other installations, distribution of disaster kits etc) or on interventions intended to build capacity and awareness which are difficult to measure quantifiably i.e. there weren’t any indicators such as increased yields or incomes. Thus the questionnaire design intended to build up an overall picture of community perceptions of the CBDRM planning process, benefits accruing (or not) from the mitigation options and again perceptions of improved knowledge, attitudes and behaviours (KAB) amongst local people with respect to DRM. The questionnaire was designed such that it would create quantitative statistics out of qualitative data such as percentages of people rating the participatory process as poor, average or good. This was intended to add more rigor to the evaluation process as it is otherwise difficult to quantify project impact and success.

It was also intended that the interviews should be semi-structured or at least that particularly interesting or indicative household interviews might lead to further questioning and the elaboration of case studies which are found in this report.

## 2.4	Discussions with CARE Project Staff

Discussions with CARE Project Staff were delayed as much as possible until after the fieldwork phase in order to try and maintain independent objectivity during discussions with partners, stakeholders and beneficiaries in the field – so that the perceptions of the CARE project manager for example did not cloud the evaluation team’s judgement. However, it was clearly very useful to discuss the project’s achievements, challenges, failures and lessons learned with these individuals since no one else knows better what they set out to achieve and to what extent they feel they have achieved this. All staff were extremely cooperative, open and honest and able to put forward objective suggestions on successes and failures. We are extremely grateful to Tran Thanh Thuy and his team for their attitude and helpfulness.

## 2.5	Data Analysis

Much of the data collected during the fieldwork stage was qualitative in nature and therefore it took some time for the evaluation time to study their notes from the field and attempt to draw out the key findings. Some qualitative data was then quantified eg. numbers of training beneficiaries reporting that the quality of training was very good, good, average, poor, very poor. The questionnaires were specifically designed in order that such qualitative data could produce a more rigorous or scientific analysis eg. percentages of beneficiaries reporting utilization of skills taught.

# Evaluation Findings

## 3.1	Relevance of the Intervention

### 3.1.1	The Project Design Process

Overall the project was developed on the basis of CARE’s organizational experience in Hau Loc District and solid working relationship with the local authorities at provincial, district and commune levels. The project design also embraced a participatory approach. This served, to create what has proved on the whole to be an appropriate and relevant intervention.

Prior to the design and start up of the DIPECHO project CARE had been operational in Hau Loc District and had supported a range of humanitarian interventions, focused particularly on the response and recovery of coastal communities from Typhoon Damrey in 2005. CARE also continues to implement a project focused on community-based mangrove rehabilitation. Thus both the mangrove project and the DIPECHO intervention represent a logical and progressive shift away from pure disaster relief, response and recovery towards a longer term vision which builds the local government and communities’ capacities and capabilities for disaster preparedness and risk management. The project design should be praised for attempting to integrate humanitarian assistance with longer term sustainable development.

Unfortunately, the North Central Coast Region and Thanh Hoa province is and will continue to be generally prone to the incidence of tropical storms and tidal surges. Thus the fundamental need to be able to cope with and mitigate such natural disasters autonomously in order to achieve sustainable poverty reduction, development and growth is recognized as a high priority within the provincial socio-economic development plan (SEDP). This is also reflected in national level policy which places an increasingly higher emphasis on DRM, particularly given climate change projections which forecast that Vietnam is likely to be one of the worst-affected countries by climate change and sea-level rise. Thus the DIPECHO intervention aimed to address an underlying cause of the persistence of poverty in one of the country’s poorest districts and an urgent need in accordance with national and provincial priorities.

During the project design process a comprehensive participatory needs assessment was carried out in 2008, involving intensive consultation with relevant authorities (at provincial, district and commune levels), communities and stakeholders. This needs assessment identified institutional weaknesses in early warning systems, government and community capacity for participatory planning for disasters, the need for external support for communities in order to mitigate the impacts of multiple hazards and develop adaptive livelihood and community development strategies.

Thus the overall project was extremely appropriate, relevant and suitable to local needs (based on experience in the locality and identification of salient needs and the participation of local stakeholders at an early stage in design) and consistent with the Vietnam National Strategy for Disaster Prevention, Response and Mitigation to 2020. The appropriateness and relevance of the intervention was unanimously agreed during discussions with project partners, stakeholders and beneficiaries during the evaluation in the field.

The evaluation team would however like to note one weakness in the design. Within component 1 and following consultation with provincial level consultations with the FSCB an advanced EWS was originally proposed, intended to digitally update decision-makers with accurate and detailed hazard maps specifying the length, level of inundation/severity, scale and precise location of floods ands storms in particular. A feasibility study undertaken at an early stage in the project quickly revealed that the establishment of such a system would both take longer than the project timeframe allowed and would be more expensive than budgeted. This system was therefore not established during the project, which instead concentrated on developing a simpler system of enhanced and streamlined information dissemination using traditional loudspeaker systems and radios which ultimately is probably a more locally appropriate intervention. In itself, this is perhaps not such a major design problem and it was certainly overcome in implementation, however further research at design stage would have quickly identified the inappropriateness of this particular activity or sub-component and would have avoided problems of budget re-allocation and subsequent approval during implementation. Therefore, the evaluation team concludes that this specific aspect of the project design could have been more thoroughly assessed at project design stage.

To finish on another strong point, in spite of the above point the project was overall evaluated as having been well-designed (appropriate and relevant) the original project design should also be praised for attempting to complete almost all the activities before the typical storm season (July-September). This would then have left time for assessing the impact of project interventions in terms of how well communities in Hau Loc district coped with the storm season.

### 3.1.2	Project Scope, Size and Timeframe

The project size, scope and timeframe was evaluated to be quite appropriate with all activities completed or near to completion (will be completed by the end of the project) as shall be demonstrated in section 3.2). Given that the project was only 15 months with the possibility of a 1.5 month extension and that by necessity it generally takes around 3 months to establish the project implementation procedures, processes and structures this means that there are often difficulties in trying to implement so many activities in such a short period of time. This project was no exception with numerous activities being hurriedly completed in the final month such as the installation of the EWS radio masts and communication systems and other hard deliverables such as additional water jars. In the case of the latter these were decided upon following budget re-allocations in order to improve disbursement on clearly much needed items for poor and vulnerable households.

The project size and scope are of course limited by the donor’s available funds and conditional ties (i.e. the project length of no more than 15 months). Given this understanding the evaluation team feels that the project’s objective to increase local capacity in DRM was a sensible and appropriately simple one. The project was also split into 4 result areas towards achieving this objective. These result areas were appropriate and addressed specific needs identified in the needs assessment. Naturally the extent to which the project was able to address all of those needs was constrained by the time available and the funds. The project has rightly focused on training, capacity-building, the development of DRMPs and awareness-raising. Component 2 (agricultural and water studies) however also provided the communities and district with important information and a technical basis for addressing two particularly key problems for the target area. Component 4 covered a range of different mitigation options selected as identified priorities in the DRMP process. It would not be possible for the project with a limited budget to provide direct benefits for all households and thus a range of mitigation options were selected which aimed to provide a mix of much needed support to vulnerable groups as well as benefit the communities as a whole. It is the opinion of the evaluation team that a balance of tangible development benefits (such as the construction of roads, a harbor and the running of agricultural pilots) is necessary to maintain the interest and focus of beneficiaries and partners as opposed to purely raising awareness and participating in planning processes. Thus an appropriate combination of result areas emerged, which given the funding constraints, produced a range of activities of approximately the right size and scope.

It is worth mentioning however that the project timeframe was widely critiqued by project partners and stakeholders as being too short. A particular issue that was repeatedly revealed during participatory discussions was the insufficient timeframe for observing impacts of the agricultural pilot models (which would ideally require observation of results over at least 2 harvests) and that they benefitted only a few. The timeframe problem is in a way unavoidable due to the conditions of DIPECHO funding and the comments regarding the agricultural component are inevitable. Although the project could perhaps have focused on a smaller number of activities, the agricultural component certainly rightly remained in order to maintain something of a balance between training, awareness-raising and a tangible livelihood improvement intervention. For such a rural and agriculture dependent community, the piloting of such saline tolerant rice varieties is entirely appropriate and relevant.

The evaluation team believes that a longer timeframe of around 2 – 2.5 years would have been ideal. This would have both allowed for better opportunities to observe project impacts including for example the agricultural pilots but would certainly have been beneficial in terms of consolidating on project outcomes. In particular the CBDRM planning process and the opportunity for reviewing DRMPs a year later and better incorporating DRMPs in socio-economic development planning.

In fact, although there was the general problem of completing all the activities in such a short timeframe, no interviewees could clearly identify a particular activity or component which shouldn’t have been there. Thus the evaluation team feels that this point had to be raised but that overall such comments were inevitable and under the circumstances, actually the project scope, size and timeframe was reasonably well-balanced and appropriate.

### 3.1.3	Project Implementation Structure

The project’s implementation structure was discussed during the group discussions at the various administrative levels.  The project’s implementation is illustrated below in Fig 3.

Fig 3:  Project Implementation Structure

This is a fairly typical arrangement for a development project in Vietnam. It is almost identical to the project implementation structures endorsed on other CARE projects and in particular other DRM initiatives such as those in Binh Dinh (including the previous DIPECHO project). In general it is a very suitable project implementation and coordination mechanism, entirely compatible with the structure of local government and extension services and certainly this appeared to be the impression given during the evaluation mission. The fact that the project operated with a familiar coordination mechanism meant there was an inherent level of understanding of people’s roles and responsibilities allowing for relatively smooth and efficient implementation.

The project would not have been able to achieve nearly so much were it not for this implementation structure, especially given the short time frame of the project. CARE themselves actually provided very little technical guidance to the project and principally acted as facilitators. The evaluation team found this to be an extremely effective approach, solidifying local ownership of the project and at the same time supporting partners to implement locally appropriate interventions aligned with government plans. Through the CBDRM planning, ToT and Farmer Field School approaches, partners also had the opportunity to build their own capacity in terms of pro‐poor service delivery methods.

### 3.1.4	M&E Framework

Monitoring and evaluation (M&E) were clearly considered during the design phase of the project with numerous methods for monitoring of activities, outputs and impacts outlined within the original proposal as well the main project document. The project possessed a logical framework and this provided the basis for monitoring. The project’s logical framework was simple and yet sufficient.

The project’s goal and objectives were sensible and sound, and there were a few simple key selected indicators. For such a short project it does not make sense to complicate things with an over-ambitious logical framework. The evaluation team thus found the logical framework to be prudent especially given the wide range of sources of verification i.e. project results are clearly included in various monthly and quarterly reports as well as specific activity and technical reports (and this final evaluation report). Such monitoring is deemed to be appropriate for a project of this size, scope and timeframe. The evaluation team could see no particular need for a baseline. If the project had contained more livelihood oriented objectives and activities with quantitative indicators such as those intended say to increase incomes, yields, food security, improve health etc then a baseline may have been appropriate – such a project would also have required a considerably longer timeframe in any case in order to see impacts.

The main emphasis of the project focused on capacity building and awareness-raising which are two activities which are extremely difficult to measure effectiveness and impact. In order to measure the impact of training courses and programmes this can be done by carrying out a kind of capacity development assessment such as the evaluation team has carried out here. The evaluation team’s only comment is that perhaps for a project which concentrated so much on awareness-raising it might have been good to carry out a small KAB survey perhaps during the needs assessment stage or at an early stage during implementation and this would have provided a kind of quantitative benchmark against which to measure the impact of awareness raising activities. Similarly within the agricultural activities sub-component perhaps a small questionnaire completed by participating farmers prior to the start of the pilot model intervention may also have helped add a little more quantitative rigor into the M&E of project activities. That said it was only a very small component of the overall project.

Otherwise for the majority of the project’s activities, indications of success are predominantly measured by the completion of outputs (eg. building of road, evacuation centre, distribution of leaflets, posters, emergency kits etc) and qualitative information collected during this and other evaluations of project delivery and in particular the DRM planning process. Given the short duration of the project and the fact that most of these construction activities and distributions have only just taken place it is rather difficult to assess their impact as part of this final evaluation. However, since CARE as an organization remain committed to DRM in Thanh Hoa and elsewhere in Vietnam, it may be worth considering a periodical or ex-post evaluation of how these outputs have been maintained and used (have they actually been used for their intended purpose?) for lessons learned and the improvement of future projects of type.

## 3.2	Efficiency

The project was designed with an extremely appropriate implementation structure and followed on from several years of cooperation between CARE and local partners. This went a long way towards ensuring that a considerable amount could be achieved in a relatively short timeframe. The project management boards submitted monthly and quarterly progress reports to CARE which were followed up with meetings to discuss implementation progress and issues as well as detailed planning for forthcoming activities. This structure allowed for efficient and timely project management overall. Several local partners commented during group discussions that they have very much enjoyed working with CARE and that they have learned from them.

With the above in mind, however, a couple of project management issues were identified. As discussed in section 3.1.2, the fact that the original idea to introduce a digital hazard mapping-based EWS was abandoned meant that budgets had to be re-allocated and a certain amount of component re-design was necessary. As a consequence this delayed project implementation.

Another weakness that emerged during consultations with partners and stakeholders was that certain administrative procedures were lengthy and it was felt that these could be improved in order to improve efficiency. In particular this referred to the procedures relating to procurement for road construction. As a result this particular activity took several months to complete even though the road construction itself only took a matter of weeks to complete. In part, this problem resulted from the decision of the community to provide the labour and monitor the activity, thus requiring more complicated contractual and procurement arrangements as opposed to simply contracting a service provider to undertake the construction. Alternatively another option, which may help to reduce the quantities of administration and paperwork could be to set up output-based contracts with a group of community labourers thus saving the need for timesheets. Lessons can be learned from other disaster projects in Banda Aceh and Sri Lanka where procurement was handled in this fashion, facilitating the process of reconstruction and monitoring.

Otherwise interviews with partners/stakeholders revealed that project activities were generally implemented on schedule and despite the short project timeframe a huge amount has been achieved and this is largely due to efficient project management and delivery. Table 1 below presents project activities and their status (completed or not).

Table 1:  Completion of Project Activities and Outputs

|  | Activity | Status | Remarks |
| --- | --- | --- | --- |
| 1 | Early warning system for the provincial, district and commune levels: |  |  |
| 1.1 | Survey and design the EWS |  |  |
| 1.1.1 | Survey and design | 2 missions completed |  |
| 1.1.2 | EWS workshop | Completed |  |
| 1.1.3 | Generator | Ongoing | Currently being installed at the time of writing |
| 1.1.4 | Computers | Completed |  |
| 1.1.5 | I- COM | Ongoing | This is a communication system for fishermen. Currently being installed at the time of writing |
| 1.1.6 | FM for the boats | Completed |  |
| 1.1.7 | Hand-held loud speakers | Ongoing | Currently being procured and distributed at the time of writing |
| 1.1.8 | Hazard and flood maps | Completed | 23 maps displayed at visible locations in communes. 6 storm tracking maps at provincial, district and at RC centre |
| 1.1.9 | Maps for ships and boats | Completed |  |
| 1.1.10 | Communication system at the commune levels | Ongoing | 01 system/ project commune. Will be completed by end of project |
| 1.2 | Establish CBDRM training center at all levels |  |  |
| 1.2.1 | Establishing training center on CBDRM | Completed | Established at the Provincial RC office |
| 1.2.2 | Develop training material | Completed | Various posters and leaflets developed by JANI project and other materials revised from Binh Dinh project |
| 1.3 | Study tour |  |  |
| 1.3.1 | In Binh Dinh Province | Completed |  |
| 1.3.2 | In Thua Thien Hue and Ha Tinh | Completed |  |
| 1.3.3 | Training on CBDRM | Completed | 420 persons from provincial, district, commune and village levels |
| 1.4 | CBDRM Planning |  |  |
| 1.4.1 | At the village level | Completed | 30 DRR plans of 30 villages have been completed |
| 1.4.2 | At the commune level | Completed | 3 integrated plans have been submitted to the district to review and approve |
| 1.4.3 | At the Province |  | District has submitted plans to province but unknown whether these will be integrated into the SEDP at present |
| 1.5 | Documentation and lesson learnt |  |  |
| 1.5.1 | Documentation | Completed |  |
| 1.5.2 | Lesson learnt | Completed | Consultant team carried out the evaluation of planning process from 24- 31st Dec, 2009 |
| 1.6 | Training for WU head and Nurse Staff on IEC skills on DRM |  |  |
| 1.6.1 | Conducting the training | Completed | 77 persons |
| 1.7 | Final workshop |  |  |
| 1.7.1 | Conducting the final workshop at provincial level | Completed |  |
| 1.8 | Procurement and delivery of equipment for rescue team at the district and commune level |  |  |
| 1.8.1 | Procurement | Completed | Life jacket, walkie-talkie, torch etc |
| 1.8.2 | Delivery | Completed |  |
| 1.9 | Training on first aid for the rescue team at the commune and village level |  |  |
| 1.9.1 | Conducting training | Completed | 221 persons |
| 2 | Study on the Agriculture Models |  |  |
| 2.1 | Study on the Agriculture Models |  |  |
| 2.1.1 | Agricultural solutions study | Completed | Agricultural study provided recommendations for uptake in component 4. |
| 2.2 | Study on clean water solution |  |  |
| 2.2.1 | Clean water solutions study | Completed | The study produced recommendations for appropriate short-term mitigation measures for uptake in component 4 |
| 3 | Training and IEC activities |  |  |
| 3.1 | TOT for teachers |  |  |
| 3.1.1 | TOT for teachers of kinder garden, primary and secondary schools | Completed | 34 persons |
| 3.1.2 | Training for all teachers on communication skills of DRR | Completed | 235 persons |
| 3.2 | Conducting IEC at the schools on DRR |  |  |
| 3.2.1 | Essay at the schools and village | Completed |  |
| 3.2.2 | IEC at the secondary schools | Completed | 3,300 students |
| 3.3 | Delivered IEC document |  |  |
| 3.3.1 | Calendars, leaflets... | Completed | 6,500 calendars, 2,000 leaflets, 100 CDs produced and delivered to community members |
| 3.3.2 | Manuals on CBDRM | Completed | 2,000 sets |
| 3.4 | IEC for women on DRM and environment during disaster and disease |  |  |
| 3.4.1 | IEC at the communities | Completed | 2,720 participants |
| 3.4.2 | Commune contest | Completed |  |
| 3.4.3 | Training on climate change and integration into disaster | Completed | 16 persons |
| 4 | Mitigation measures |  |  |
| 4.1 | First aid kits for schools and villages | Completed | 40 kits, (30 kits for villages and 10 kits for schools) |
| 4.2 | Evacuation House | Completed | 2 houses built in 2 communes |
| 4.3 | Irrigation System | Completed | Hung Loc commune |
| 4.4 | Seawater intercepting sewers | Completed | 6 seawater intercepting sewers |
| 4.5 | Evacuation Road | Completed | 2 km for 2 commune of Hai Loc & Da Loc |
| 4.6 | Water tanks | Ongoing | 200 tanks to 200 poor households |
| 4.7 | Sanitation system for kindergarten | Completed | 1 kindegarten in Hai Loc |
| 4.8 | Ship Locks | Completed | 1 ships lock for 80 ships |
| 4.9 | Water filters | Ongoing | 100 filters for 10 schools, currently being installed at the time of writing |
| 4.10 | Agriculture Model | Completed | 60 farmers from 3 communes piloted saline tolerant rice varieties on 6ha (evenly distributed amongst communes) |
| 4.10.1 | FFS courses | Completed | For 60 farmers in 3 communes (total of 15 sessions) |

## 3.3	Effectiveness & Impact

It has been rather difficult for the evaluation team to fully assess/evaluate the effectiveness and impact of the project due to the project timeframe. A typical problem with these types of humanitarian assistance projects is that many outputs have only just been completed at the time of the final evaluation thus making it difficult to properly assess their impact. However as mentioned above, through our methodology we have tried to introduce tools which aim to try and measure impact quantitatively to some extent. Overall the project appears to have been generally effective, have achieved its purpose and is having a positive impact on local communities who are now much better positioned to prepare for, respond during and recover after various disasters. The following section goes through each of the activities or outputs specified in the logical framework and provides some assessment or analysis on the effectiveness and impact of each intervention.

### 3.3.1	Result Area 1:  Improved DRM/EWS capacity of provincial, district, commune government FSCB standing Office Staff

i)	Technical assistance on early warning and information management system delivered: As has been discussed above the final EWS is somewhat different from that which was originally envisaged for the project. Instead of establishing and developing the high-tech digital hazard mapping database and system, after some deliberation and following the technical assistance study, it was decided that the budget allocated for the EWS would be invested in establishing a radio communication-based EWS and thus addressing identified bottlenecks in the timely and effective dissemination of natural hazard related information.  Before the project and as identified in the needs assessment, a particular area of weakness was the lack of an effective EWS. Currently information relating to hazards and natural disasters is received from regional hydro-meteorology stations and provincial forecasting services, and provincial FSCB then disseminate warning information and instructions for prevention and preparedness to local level government line agencies. The information is delivered to the community through the commune government. The current institutional set-up is appropriate and reasonably effective but faced some bottlenecks caused by the lack of technical equipment or streamlined tracking mechanisms compromising the timely and comprehensive reach to the most vulnerable part of the population.

The EWS improvement project component is in its final stages of completion with a number of the loud speaker masts being erected at the commune centres at the time of writing which means it is impossible for the evaluation team to comment on the action’s effectiveness or impact at this stage. The new system once installed by the project is certainly likely to improve the communication of information and better prepare people at the affected locality in emergency situations. As such the project did well to adjust and the intervention is likely to present the communities in Hau Loc with a significant practical benefit (any additional time of course being beneficial) which does contribute overall towards the project’s objective of reducing vulnerability but it will not have the originally intended effect or impact.

In addition there have been a number of benefits for fishers who have been provided with I-COM systems and radio sets as well as maps which should help them considerably to receive advance warning of approaching storms and leave time to reach the shore safely. Storm hazard maps were also produced and displayed publicly.

ii)	Establish provincial community based disaster risk management training centre:  This activity has been successfully completed. A provincial CBDRM training centre was established at the offices of Thanh Hoa Red Cross with basic equipment provided (computer, furniture, and other basic office equipment) by the project. The concept behind establishing the training centre was that it would then provide numerous trainings for FSCB staff throughout the project (see section (iii) below) and beyond as opposed to the contracting of trainers for these courses. Indeed 9 RC trainers subsequently provided various trainings to several different project beneficiaries (FSCB staff in CBDRMP as well as trainings on disaster related first aid health and hygiene for commune health workers and WU representatives, DRR information session training for school teachers etc) – see Table 2 below.

The training centre also acts as a resource information centre developing and storing materials, manuals, guidelines and other IEC materials on disaster risk management, mitigation and preparedness developed under this and other projects.

This project activity has been a success and it is likely to be sustainable although there are some inevitable question marks regarding operational funding post-project. The centre receives its budget almost entirely from the state which is sufficient to maintain the centre and pay staff salaries but further and wider roll out of the training programmes will be dependent on sourcing additional budgets from both government and external sources. With the increasing prioritization of DRM planning and mitigation activities at national and provincial socio-economic development policy levels, there should however be opportunities for financing and the centre is now in a better position to access those funding streams. Interviews with RC and government staff both anticipated increased government spending on disasters in the coming years and thus the training centre is in a position to play a crucial role in the GoV CBDRM program roll out.

iii)	Organise cross visit and provide training to government staff and Community FSCB:  The project actually provided two study tours (rather than the originally proposed one study tour) for staff from relevant local government departments such as the FSCB. A cross visits made were to Binh Dinh, where participants were able to observe another CARE implemented DIPECHO project drawing to a close. Participants also visited another DRM project in Thua Thien Hue province. Both visits were deemed to be extremely useful and enabled participants to see how other projects in coastal areas had dealt with similar problems. The project’s had similar objectives and activities and this certainly helped participants to gain a good idea of how the project would work during implementation and what some of the anticipated results would be – in particular the benefits of participatory DRM planning. Overall this was a very successful project activity and local partners were then able to put what they learned on the study tour into practice by employing the same processes, structures and systems. The evaluation team believes cross visits and study tours to similar areas/projects are an excellent idea that should be replicated in future DRM interventions to facilitate project delivery.

In addition to the study tours, FSCB staff at all levels were also trained by the Thanh Hoa Red Cross CBDRM Training Centre. The table below presents information on the training provided by the Training Centre during the project.

Table 2:  CBDRM Training Provided by the Training Centre

| Title of Training Course/Content | Date | Participating Institutions | No of courses | No of Participants |
| --- | --- | --- | --- | --- |
| Principles of DRR information management and CBDRM planning | Nov, 2008 | Provincial, district and 3 communes FSCB | 1 | 28 |
| TOT on climate change to key trainers | Nov, 2008 | Province FSCB & THRC | 1 | 16 |
| Principles of DRR information management and CBDRM planning | Dec, 2008 | Provincial, district and commune DARD | 1 | 27 |
| CBDRM Planning | Dec, 2008 | 3-day training for Commune officials | 3 | 94 |
| CBDRM Planning | Dec-Jan 2009 | 2-day training for key village staff in the 3 communes | 8 | 271 |
| TOT to village WU's heads and heath care staff on disaster management and communication skill | Feb-March, 2009 | 5 –day training for commune WU and health station staff | 2 | 72 |
| TOT on DRM to school and nursery school teachers | March, 2009 | Commune and village teachers and nursery school teachers | 1 | 34 |
| First aid training to commune rescue team in Da Loc commune | July, 2009 | 2-day training to rescue teams | 1 | 26 |
| TOTAL |  |  | 18 | 568 |

28 staff from FSCB at all levels participated in CBDRM training courses. The courses were 5 days in length and equipped participants with the necessary skills to be able to carry out the HVCA and facilitate the development of CBDRMPs. Results from the capacity development assessment questionnaire indicate that all participants who received training in CBDRM thought that the training courses were of an appropriate length, the quality of the training materials and trainers was good, and the training content was pitched at the correct level. All participants interviewed reported that they have been able to apply their new skills in their work, indeed the project was designed so that following training, and participants would immediately be involved in CBDRM planning.

Results from a concurrent consultancy to document and assess lessons learned from the CBDRM planning process indicate similar results regarding the standard of trainers and training materials. However their study revealed that district and provincial staff felt that the training was too long meanwhile village and commune level staff only received 2-days worth of training, much of which concentrated on technical terms and definitions rather than practical community facilitation skills. In fact Hoang Van Duong et al made their own pertinent observations on the training course content and materials, stating that the training manuals and materials were rather heavy with academic definitions and terms and could have been more user-friendly.

Thus it would appear that in spite of customer satisfaction with the training delivered further analysis reveals that in fact there was a fairly fundamental problem with the course content and materials. In particular it would appear that the courses have been weighted the wrong way around i.e. the on the ground (village/commune) staff should have had more detailed intensive training on PRA, facilitation and participatory planning techniques meanwhile the district and provincial staff should probably have had the more condensed overview 2-day training.

This activity therefore appears to have been fairly successfully organised and implemented in terms of numbers of people trained and overall satisfaction but some fundamental problems are observed in the training structure and content. In fact the lower level GoV staff should be better and longer trained and empowered to carry out and lead the process in the communes. The real evidence of the activity’s effectiveness and impact lies however with the success of the activity below i.e. the actual CBDRM planning process.

iv)	Participatory planning to develop commune master plan organised by communes:  During the final evaluation mission, the team was accompanied in the field by a separate consultant team tasked by CARE to specifically investigate the strengths and weaknesses and lessons learned from the participatory planning process. Since this is covered in detail in their report, we will not repeat key findings at length here. However, this is one of the most important (if not the most important) aspects of the project, thus some commentary summarizing their key findings and some information from the evaluation team’s own consultations and perspectives.

The project followed a logical 12-step participatory planning process summarized in Fig 4 below:

Fig 4:  The Participatory Planning Process

  - Provincial Orientation Workshop:  Launch the project and orient key stakeholders to the approach

  - Project Management Board Establishment:  PMB established for project implementation

  - CBDRM Training:  Provincial FSCB staff trained in participatory DRR planning methods

  - CBDRM Training:  District FSCB staff trained in participatory DRR planning methods

  - CBDRM Training:  Commune FSCB staff trained in participatory DRR planning methods

  - CBDRM Training:  Village FSCB staff trained in participatory DRR planning methods

  - HVCA Training:  Training on village meeting facilitation skills, priority need assessment and selection in preparation for village meetings for HVCA

  - 1st Village Meeting:  Conduct the HVCA and to draft village DRMPs

  - 1st Commune Planning Workshop:  Present the results of the 1st village meeting and the village draft DRMPs

  - 2nd Village Meeting:  Present feedback from the 1st commune meeting, for finalization of the village DRMP

  - 2nd Commune Planning Workshop:  Present the final village DRMPs, to discuss and finalise the commune’ DRMP

  - Provincial Planning Workshop:  Present the final commune DRMPs for project approval.

At the output level the activity was successful with the production of 30 village DRM plans which were subsequently incorporated into 3 commune DRM plans which have been approved by the district and certain aspects of these plans have also been incorporated into the district SEDP.

It is clear from both the evaluation team’s survey results as well as those from the Hoang Van Duong team that participation levels in these processes were extremely high. The evaluation team’s results regarding the community’s impressions of the process differ slightly from those of the CBDRM planning assessment team’s as is shown below in Fig. 5. Whilst their statistics indicated 72% of interviewees felt that the DRM planning process was very well organized with the active participation of local people and that the plans reflected local needs and priorities, our statistics tell a slightly different story with the majority (80%) stating that it was only ‘quite well organized, allowing the local community to express their views but some people were shy to talk – the plan mostly reflected the needs of the community’. 16% of men thought it was very well organized and 4% thought it was a waste of time, with it being difficult to talk in such meetings and the final plan did not reflect the wishes of the community at all. 6% of women felt the same way (representing 8.5% of the total sample). 12% of women also felt that the DRM planning process was a good idea in theory but in reality it was poorly organized and only really reflected the wishes of a few in the community.

Fig 5:  Community Impressions of the CBDRM Process

This mixture of results are interesting because although they indicate the majority of people are satisfied with the results of the process, from the evaluation team’s results there would appear to be indication that a sufficient proportion of the beneficiaries were not entirely satisfied with the process.

Why would people not be satisfied with the process? Although results from both surveys indicate widespread satisfaction with the DRMPs, a closer inspection reveals that in fact the DRMPs are not much more than wish-lists geared towards longer term socio-economic development, calling for external support as opposed to the detailing of low or no cost preparedness and mitigation measures intended to significantly increase resilience/reduce vulnerability amongst the most vulnerable groups in particular. The DRMPs do not appear to show application of the participatory planning skills and tools taught during the training, if they had then particular vulnerable groups would be specified and particular measures developed with respect to their needs. This leaves the evaluation team to conclude that it is likely that the resultant DRMPs are reflective of a kind of ‘one size fits all’ approach at the village/commune level whereas the intention was that the end product should in fact have detailed measures and specific safety nets in place for those most vulnerable to the ‘shocks’ of natural disasters and the ‘trends’ of their likely increasing occurrence. The problems with the training courses identified above (i.e. the fact that commune/village staff only had 2 days training and largely theoretical) appear to have manifested themselves here and this is perhaps why the DRMPs do not appear to show the full and proper application of participatory processes.

Case Study:

Women Involved in DRM Planning

Mrs Bui Thi Din is 54 years old, and lives in Yen Loc village, Da Loc commune, Hau Loc district.

She is an officer in the Village Women’s Union and has been involved in all activities of the CARE project in the village.

In the past the planning for disaster prevention was done by commune and district staff and no one had the opportunity to participate. Since the CARE project was implemented here she has participated in village meetings and training courses for women in the village and has been especially involved in planning for disaster prevention.

The village worked together to jointly define the types of natural disasters in the community, found out the causes and identified solutions to prevent and mitigate disaster risks.  In particular she recognizes the need to focus on the particular needs of some of the poor women in the village in the difficult local conditions.

‘I understand that we all must take responsibility for being prepared for natural disasters and recovering from their consequences. The CARE project has equipped us with the knowledge to develop plans for natural disaster prevention in the village and for each family’

The evaluators also believe that the DRMPs have suffered due to a poor documentation or reporting of the processes. For future interventions of type it may be necessary to develop a prescribed format for the DRMPs which incorporates sections designed to document processes and the results of particular facilitated group discussions of vulnerable groups.

It is clear that there are certain lessons to be learned from this CBDRM process but the evaluation team does not wish to be overly critical since this was a first attempt experiment at the participatory planning process concept in the province and it has been generally well-received by partners, has flipped the usual top-down planning procedures on their head and allowed for community participation and voice in the development of local plans. As the case study right also shows it has facilitated the greater involvement and participation of women in decision-making processes.

However the HCVA process probably requires more human resources investment at the initial stages to ensure that right tools are used and that the reporting is adequately reflecting the process.

A longer project would have presented the opportunity for consolidating on the CBDRM training provided at the annual review stage of the DRMPs and perhaps at the second attempt been able to better apply participatory tools and as a consequence DRMPs more targeted towards specific interventions for particular intra-community groups. Alternatively, for immediate results, this initial pilot attempt at participatory planning could have been carried out with perhaps less villages/communes but with greater guidance from CBDRM facilitators as opposed to the delivery of training by the RC and subsequent withdrawal from the process of actually doing the participatory work (CBDRM planning). Once commune and village FSCB members have gone through the process once with close guidance and support they may be better placed in terms of their capability to roll out the participatory CBDRM process. As a suggestion the evaluation team probably advocates the latter.

The DRMPs have been approved by Hau Loc district and certain elements have been integrated into the SEDP. This is a good achievement by the project and also illustrates that the district authorities have an appreciation for the planning process and there are now some tangible results with certain DRR activities in particular the awareness raising in school activities being prioritized and funded by the government at the local level. Certain infrastructure projects were also prioritised but their funding is dependent on provincial level approval of the district SEDP and this is unknown at this stage. The fact that these community plans have been incorporated into the district SEDP provides hope that the process will be sustainable and repeated in the years to come. The participatory planning processes is however difficult and takes time as commented by the district FSCB. It requires higher levels of capability and competence at the grassroots levels and crucially in Vietnam it costs money in order to ensure participation. This is a fundamental problem in Vietnam – if people are not paid per diems for their attendance, they will not attend and unfortunately whilst there is a project providing such monies participation can take place, once the project is gone the local government will find it very difficult to find the funds to pay for the participatory process.

Sensibly given the project’s short duration the project never intended to monitor the impact and sustainability of the intervention by including an indicator for the number of non-project communes where this approach had been rolled out. The process has not as yet been rolled out elsewhere and would have been very difficult to achieve.

v)	Document lessons learned from participatory planning process and feedback information to government: This is the study referred to above (Hoang Van Duong et al), the lessons learned from that study and this evaluation report will be shared with government partners. This activity will be successfully completed by project closure.

vi)	Training of Trainers for female staff of commune health care centre and heads of village Women’s Union: The project included a component intended to reduce the vulnerability particularly of poor women and children to disease following disasters and thus endorsed a ToT approach to train commune health workers and WU staff in basic first aid and hygienic practices for disease prevention and the treatment of common diseases and illnesses following disasters. Table 2 above provides a summary of the training courses delivered by the project under this result area.

The ToT courses, trainers and materials were evaluated as being good by training participants during group discussions and capacity assessment questionnaires. Following on from the ToT courses, the project supported a number of information sessions presented by the newly trained trainees.

The household interviews indicated that 100% of women interviewed had participated in at least one information session and had found it to be quite useful and helped them to understand what to do in certain disaster situations.

The intervention is also likely to be sustainable since it is a low cost activity once the training has been provided and now the newly trained trainers will be able to repeat the information sessions and this is easily facilitated during the usual monthly WU meetings at village and commune level. The evaluation team believes this activity to be a positive success and that the ToT approach is highly suitable and an appropriate modality for transferring knowledge, skills and raising awareness, particularly as the activity is carried out with the WU as partners. The WU in Vietnam has a mandate to raise women’s awareness, knowledge and capacity in order to meet the requirements of modern socio-economic development, and assist women in economic development and the building of happy, prosperous, equal and progressive families. ToT training for women in reducing vulnerability to the impacts of disasters on families is therefore particularly appropriate, was recognized as such during consultations in the evaluation mission and it was indicated that such information dissemination meetings facilitated by the newly trained trainers will continue under the existing framework of WU meetings at the commune level.

vii)	Information seminar for provincial PC and provincial FSCB, district PC and district FSCB members: An information seminar was held for PPC and FSCB staff at provincial and district levels. The seminar helped increase knowledge and awareness of DRM and in particular CBDRM approaches. It assisted with the smooth implementation of the project by providing a basic orientation for participants. This activity was successfully implemented.

viii)	Procurement and distribution of emergency items identified: The project provided search and rescue teams with emergency kits consisting of life vests, raincoats, torches, handy loud speakers. In total 338 emergency kits were distributed to search and rescue teams agreed during community consultation. The kits were welcomed by beneficiaries and would be needed during disaster situations. This is a relatively simple project activity that was successfully implemented by the project and met particular humanitarian needs of vulnerable community members. Fortunately the kits have not really been used as yet as Hau Loc district was not particularly badly affected during the 2009 storm season.

Fig 6:  Emergency kits distributed by CARE staff

ix)	Formation of the teams and conducting training on use and maintenance of working equipment and tools and other necessary trainings: Pre-existing emergency teams at village level consisting of 338 people were provided with certain basic equipment in order to assist them in their roles just before, during and after disaster scenarios. Short search and rescue trainings were carried out in drill situations and team members were trained in how to use relevant equipment. This activity was successfully implemented and contributes to the objective of reducing coastal communities vulnerability to disasters through being better prepared.

### 3.3.2	Result Area 2 – Community Mitigation Studies

i)	Conduct technical study on alternative agricultural practices:  A study was carried by a group of local Thanh Hoa-based agricultural experts (Tran Nam Thanh and Le Trong Hai) and a technical report submitted to the project. Therefore this project activity was successfully completed. In fact this report was extremely detailed and proposed the piloting of saline resistant varieties of rice in the three communes. The pilot models as will be discussed in section 3.3.4 appear to have been extremely successful (although again it is a little early to tell).  Thus the evaluation team considers this to be an extremely worthwhile use of project funds and an effective activity with a positive impact on community resilience to disasters.

ii)	Conduct scientific study on drinking water sources: A technical team of experts from the Centre for Development Assistance was contracted to carry out a study on drinking water supply and sources by the project. Detailed scientific investigations on water quality and use practices revealed that access to clean, safe drinking water supplies is a significant problem in the project area with many sources of water affected by storm surges meaning that water sources often have a high saline content. Furthermore many hand dug and drill wells in the target communes are afflicted with a high bacteria content, and levels of E. Coli. manganate, chloride and arsenic above allowable levels. The quality of water is clearly having negative impacts in terms of human health. Certain communes in the project are anticipating being connected to the water supply under the World Bank Second Red River Basin Project and Hau Loc District is also prioritizing other water and sanitation improvement activities in the near future. The limited budget (and timeframe) of the DIPECHO project meant that recommendations sensibly prioritized a range of short-term immediate impact interventions the provision or partial finance of rainwater containers, introduction of standard filtration container, training provision, and information dissemination activities.

These recommendations were taken up within result area 4 of the project and will be discussed in section 3.3.4 of this report, although once again the project timeframe makes it almost impossible to assess the actual impact and effectiveness of the interventions particularly as many households have only recently received their water tanks and other deliverables.

The results from both studies were disseminated to communities and in particular to the relevant local authorities. Particular attention is now being paid to the agricultural pilot models with a stated intention by district DARD and commune agricultural extension staff to try and roll out these models.

### 3.3.3	Result Area 3:  Increased Awareness

i)	IEC material revision and development: The project linked up with another national CBDRM initiative, the Joint Advocacy Network Initiative (JANI) which is a consortium of 14 agencies involved in CBDRM in Vietnam and led by CARE. JANI developed common IEC materials based on previous DIPECHO (and other donor) funded projects elsewhere including the DIPECHO and OFDA projects in Binh Dinh province. Hau Loc district was selected as one of the testing sites for these IEC materials. A technical panel was established to assist the Thanh Hoa RC CBDRM Training Centre review these IEC materials, ensure their suitability to local conditions and distribute them. The evaluation team has reviewed some of them and found them to be appropriate, colourful, informative and well-designed. This project activity has been a success and the impact appears to be positive with widespread acknowledgement of increased levels of community awareness of disasters, their impacts and how to prepare and mitigate from them. The IEC materials have contributed to this.

ii)	Training of Trainers in DRM to school and nursery school teachers: The project supported a ToT approach by training teachers at kindergartens, primary and secondary schools in how to deliver activities and classes on DRM to schoolchildren between the ages of 5-16.

A significant number of teachers have been trained by the Thanh Hoa RC CBDRM Training Centre who developed the materials and this has allowed for widespread dissemination of DRM messages to young people. 34 ToT teachers passed on their knowledge to a further 235 teachers throughout the district. Following training teachers then held 112 DRM classes within schools reaching a total of 3,079 students.

A number of contests amongst schoolchildren were also staged supported by the project and these too have further helped to increase levels awareness amongst young people (one of the more vulnerable groups as identified in the needs assessment).

Overall, this would appear to have been a hugely successful project activity reaching far more beneficiaries than originally planned. Unfortunately the evaluation was not able to interview any students due to the time available but local teachers report that the classes have been enjoyed by students and have served to increase their awareness. A fantastic and perhaps unanticipated outcome of the project is that the provincial DoET has now agreed to integrate the DRM lesson plans and content into the school curricula and extra-curricula activities for 6-16 year olds. This is an important result and one which almost guarantees the sustainability of the intervention. The involvement of the DoET as a stakeholder is notable as all too often training courses and awareness programmes are developed for development projects in Vietnam but the fact that DoET are not involved means that the wider uptake and replication of these interventions is usually very limited. Therefore the project should be praised for facilitating this outcome – it is an excellent idea and should definitely be replicated in other projects focusing on awareness-raising and training for DRM.

iii)	Distribution of public awareness materials to communities: The IEC materials developed by the CBDRM Training Centre were widely distributed within the project area. A total of 8,000 leaflets, 2,000 posters, 2,000 guides, 6500 DRM calendars and 120 VCDs were distributed during the project. Many villagers commented on the usefulness of these materials during household interviews and in many cases the posters are displayed in a prominent place in their households.

As commented previously, the IEC materials were considered to be appropriate and of good quality. They have been successfully distributed and this has helped contribute to the positive influence the project has had in terms of raising community awareness.

iv)	Women’s information sessions: Following the training provided to WU staff in component 1, the project intended to roll out information sessions for women, as an identified particularly vulnerable group. A total of 34 information sessions for a total of 2,720 women were held in addition to various competitions, contests and the night dramas in particular were regarded as an enormous success, proving to be extremely popular and an effective communication method. Holding activities at night is a good idea and should be replicated elsewhere as it allows many women to attend that would not be able to do so during the day due to their heavy work load. Such night activities can have a more relaxed, fun and social atmosphere conducive to getting a message across.

Once again these information sessions and other activities have contributed positively to one of the project’s strongest success areas i.e. increased awareness.

- 3.3.4	Result Area 4:  Increased community resilience to disasters

Result area 4 was by necessity only loosely defined in the original proposal as the specific activities were to be defined by the two technical studies carried out under result area 2 as well as the subsequent participatory planning process in result area 1. Thus mitigation measures intended to increase community resilience to disasters were developed on the basis of the previous components and then planned and implemented under this component. Interventions were intended to benefit the communities at large as well as provide specific benefits for particularly vulnerable groups within the communities.

- Establish quality monitoring and implementation plan: Once the mitigation measures had been developed a joint implementation board consisting of commune level project partners and CARE developed an implementation and monitoring plan for the activities. Table 1 above presented all the agreed mitigation measures that were supported by the project in each commune and their implementation status.

As the table above shows the project has been able to support a wide range of activities and in spite of the limited budget been able to provide a number of useful hard deliverables which are likely to assist the communities considerably in being prepared for disasters. The project was able to reallocate unspent budget lines, in order to finance a wider range of benefits than originally anticipated.

This evaluation will not review in detail every single installation but will focus on a couple of the more significant ones and the processes involved. Since many of these mitigation measures have only just been installed it is extremely difficult for the evaluation team to be able to evaluate their effectiveness and impact. It is however assumed that the provision of water tanks and filter systems and other deliverables will have a positive impact for households previously unable to collect rainwater or reliant on contaminated water sources.

Evacuation Centre: One of the most important construction activities in Hai Loc and Hung Loc communes was the construction of an evacuation centre (see Fig 7 left). DWF France as a specialized agency in typhoon resistant construction was consulted to provide feedback on the technical drawings. During the strengths, weaknesses and lessons learned activities during the consultation meetings it was noted that several stakeholders mentioned that these evacuation houses were too small. This is perhaps an indication that the budget has been perhaps spread a little too thinly in order to try to keep everyone happy, rather than concentrating on a few key outputs. Still, the evacuation centre has been well constructed on time and will provide a safe house during storms and other natural disasters particularly for the old and poor living close to the sea dyke.

Fig 7:  Commune Evacuation Centre built by the project

Evacuation Roads: Evacuation roads were constructed in Hai Loc and Da Loc communes (total distance of 2km). These roads were clearly important to the communes in providing particularly those most affected by storm surges with a route out of the typically affected areas. Beyond this, the roads are used on a daily basis by the commune’s population and help to meet their transport infrastructure needs even during good weather. Meetings with project stakeholders during the evaluation mission revealed that the communities particularly appreciated the opportunity to be involved in the construction, supervision and monitoring of the construction activity. However perhaps due to the participatory nature of the activity, it took a long time to complete and was particularly delayed by cumbersome administration and procurement procedures. The fact that the community was so involved is praiseworthy but a recommendation may be to make these administrative procedures less cumbersome and more straightforward.

Fig 8:  Evacuation road constructed by the project

Case Study:  Water Tanks Provided to Poor Households

Dinh Thi Tam, (38), lives in Truong Nam village, Hai Loc commune, Hau Loc district.

The area where I live is often threatened by disasters such as storms, floods, and drought as well as salinity and environmental pollution.  I have a husband and two small children and as a family we depend on salt production.  My husband is weak and we struggle with a low income.  Since the CARE project came, I have been involved in village meetings to identify needs, participated in trainings and information sessions on disaster prevention and response.

The lack of available clean water is still one of the greatest difficulties for my family because our area is located on saline soils and we need a large tank to catch rainwater for daily use.  Being poor we have still had to use water from our hand-dug well for many years. This could also be a reason for our poor health.  CARE has provided a number of poor households like mine with 2m³ tanks.  We can now store rainwater for daily use.  We are very grateful to CARE for paying attention to poor households like us and hope that with this tank we will be able to use clean water and have less health problems.

Water Tanks: 200 poor households were provided with water tanks. Whilst it was commented that the water tanks were too small by some interviewees meaning that they are not able to store sufficient quantities of rainwater, this was still a relevant short term intervention for which beneficiaries are grateful and it should provide these households with a cleaner supply of drinking water for a large part of the year. This can be considered as an important interim measure before the communes are connected to the water supply as planned in the near future as part of the forthcoming World Bank financed Second Red River Delta Rural Water Supply and Sanitation Project scheduled to begin implementation in 2011. The case study on the right illustrates one such household’s experience.

Ships Lock: A ships lock was constructed in Da Loc commune providing a safe harbor for up to 80 fishing vessels. This is clearly of significant benefit to the livelihood of some of the poorest in the community – the small scale near shore fishers.

Case Study:  Saline Tolerant Rice Varieties

Nguyen Van Thay (60 years old), lives in Tay Hoa village, Hung Loc commune, and was one of the farmers participating in the saline-tolerant rice pilot models.

His household of 6 people has 8 sao of agricultural land and like many in the area they derive most of their income from agricultural production. Before 2005, he was able to produce about 300kg/sao/crop. Storm #5 broke the sea-water dyke in 2005, the soil became saline and the yield was dramatically reduced by over half. His children had to find other work in order to support the household.

‘We could not find a way to overcome the salinity problem. In 2009, with the support of the project, he became a pilot demonstration farmer.

We received training from district agricultural staff on new farming methods, mainly on compliance with technical steps from land preparation to planting and tending. With this new method of cultivation, production costs have been markedly reduced, for example, it requires only 4kg of rice seeds instead of 6kg as before, Urea fertiliser 9kg instead of 12kg before, while the yield of the model increases. The latest crop of my family achieved 400kg/sao.

We are very excited about the success of the model. A field workshop was held for people to visit the model and share experiences. Everyone realized that this new mode of production should be applied widely and all people should commit to apply the model to the new crop.’

Fig 9:  Ships lock – a safe haven for fishing vessels

Agricultural Pilots: One of the most successful interventions of the project was the saline-tolerant rice pilots. The models followed the recommendations of the technical study on agricultural solutions and were piloted on 2ha in each commune and involved 20 farmers in each commune. Table 3 below shows the different models adopted in each commune.

Table 3:  Saline Tolerant Rice Trials

| Commune | No of ha | No of Farmers | Model |
| --- | --- | --- | --- |
| Da Loc | 2 | 20 | 838 |
| Hai Loc | 2 | 20 | N46/KD18 |
| Hung Loc | 2 | 20 | N46/KD18 |
| TOTAL | 6 | 60 |  |

The evaluation team conducted interviews with a small sample of the farmers who participated in the agricultural pilots. The results from this survey as well as an activity report from the District Agricultural Extension Centre provide a preliminary indication that the trials appear to have been a huge success. Table 4 and Fig 10 overleaf illustrates results from these trials.

The graph shows the increased productivity of the new varieties whilst the table presents data from the District Agricultural Extension activity report and illustrates how there are some savings made due to the lower costs of production, especially with regard to the quantity of seeds, pesticides and fertilizers with the new rice varieties and techniques. However, the new varieties appear to have also increased production by around 25% on average. In addition, the new N46 variety has a significantly higher price at market i.e. 5,000 VND/kg compared with 3,500 VND/kg of the existing/traditional variety.

Fig 10:  Rice yields of saline tolerant varieties

The cumulative result of larger yields, higher market value and reduced production costs means that the average farmer should theoretically almost triple his profit margins. Whether it works out to quite this extent in practice remains to be seen and should continue to be monitored over a longer timeframe than has been possible so far. Nonetheless the potential for a significant improvement in food security and incomes should mean local livelihoods are less vulnerable to the impacts of natural disasters. Cash is often the most important asset during such periods of instability as it can be readily and flexibly converted into other forms of capital (especially purchasing food, medicines and other essential items) before, during and after disasters.

Table 4:  Costs of Production and Profits from New Rice Varieties

| No | Title | Unit | Pilot (N46 rice) |  |  | General (KD 18 rice) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Amount | Cost | Total (VND) | Amount | Cost | Total (VND) |
| I | Total Production | kg | 6,540 | 5,000 | 32,700,000 | 5,200 | 3,500 | 18,200,000 |
| II | Total expenses | Ha |  |  | 19,601,850 |  |  | 13,680,000 |
| 1 | Material | Ha |  |  | 7,081,850 |  |  |  |
| 1.1 | Seed | kg | 80 | 16,000 | 1,280,000 | 80 | 12,000 | 960,000 |
| 1.2 | Manure (muck) | kg | 751 |  | 4,481,850 | 751 |  | 4,474,000 |
|  | Ure | kg | 183 | 6,700 | 1,226,100 | 220 | 6,700 | 1,474,000 |
|  | Phosphorus | kg | 425 | 2,950 | 1,253,750 | 20 B,NPK | 80,000 | 1,600,000 |
|  | Calcium | kg | 143 | 14,000 | 2,002,000 | 100 | 14,000 | 1,400,000 |
| 1.3 | Pesticide | Ha |  |  | 1,320,000 |  |  | 1,680,000 |
| 2 | Labour | Day | 280 | 40,000 | 11,200,000 | 300 | 40,000 | 12,000,000 |
| III | Profit |  |  |  | 13,098,150 |  |  | 4,520,000 |

Based on the apparent success of the models almost everyone interviewed stated that they will be applying the new production methods and rice varieties (including those who did not participate directly in the pilots). Whilst there really should be a longer timeframe of 2-3 growing seasons in order to properly assess the effectiveness and impact of this model, the early indications are that this particular mitigation measure is likely to have a very significant and widespread positive impact on the livelihoods of disaster prone communities in the project area and thus reduce vulnerability considerably.

Part of the success of the models should also be attributed to the form of knowledge transfer. The evaluation team has experience of other CARE livelihoods and DRR interventions which have also applied the same Farmer Field School (FFS) concept. In almost all instances it has been a marked success. One of the reasons for the success of the approach is that it places onus on the community to select appropriate demonstration farmers, who are usually competent, distinguished and respected members of the community. Usually they are not the poorest households but this is an important factor since they are the ones who may have slightly more ability to take on the risks if the demonstration crop fails. As such these individuals have a greater potential for applying the new techniques properly and an ability to pass on the knowledge i.e. these farmers such as Mr Thay (see the case study above) become the teachers.

The FFS also endorses a highly practical approach, with extension workers spending considerable face time with participants in the fields, providing practical demonstrations and training sessions to participating farmers. This approach differs markedly from the usual extension approach in Vietnam which are almost always very theoretical, classroom-based lectures. The practical approach definitely assists farmers considerably in being able to remember, understand and apply the techniques effectively. Thus the evaluation team concludes that the FFS approach should continue to be endorsed as a highly appropriate modality of knowledge transfer, and in this case further roll out or replication of the saline-tolerant rice variety models would be a highly appropriate activity.

Fig 11:  The FFS approach in action in Hau Loc

## 3.4	Sustainability

The sustainability of project interventions has been mentioned to some extent in the preceding section but is discussed more specifically here. Overall, the majority of the project’s interventions are deemed to be sustainable in particular the interventions focused on awareness-raising. Some concerns relating to the sustainability of the participatory CBDRM approach and related capacity building/training programmes are expressed here:

- The regional training centre has been established but there are concerns that they may be constrained in terms of rolling out repeat trainings and training courses for other districts by the lack of operational budgets. To remain optimistic, the province’s prioritization of disaster prevention and preparedness in its socio-economic development plan means that the Thanh Hoa RC remain hopeful that they will secure funding from central levels in order to maintain the centre and its FSCB training programmes. They will however still require support in seeking further external assistance for this.

- The sustainability of the CBDRM planning process is somewhat threatened by the continued existence of two DRMPs at the commune level i.e. the participatory plan developed by the project and the traditional FSCB budget for DRM. There is a need for integration of the two planning processes to create one plan in order to avoid confusion and furthermore to ensure the sustainability of community plans, as otherwise it will be the government top-down plan that will be prioritized. This said the project has done extremely well to develop 30 village plans and 3 commune master plans which have subsequently been approved at district level. Local partners have appreciated the process and recognized its benefits and thus there are some positive indications of sustainability for participatory planning in Hau Loc district. In itself this is quite an achievement within the short project timeframe. As mentioned previously, a longer project timeframe would have served to consolidate, improve and reinforce the participatory DRM planning process.

- The ToT approach adopted for the training of commune health workers and WU staff has helped significantly to guarantee the sustainability of this intervention area. It was widely expressed during the evaluation trip that information sessions in particular those for poor women will be able to continue using the trained trainers and using the framework of the usual monthly WU meetings.

- The project has addressed the sustainability issues related to maintenance of stock (I-COM, walkie-talkies, radio, loudspeakers, torches etc) and equipment in component 1 through the provision of training in this regard.

- The interventions associated with result area 3 (raising awareness) appear to be extremely sustainable due to the ToT approach adopted by the project with commune health workers, school teachers and WU members now all able to deliver information sessions. The sustainability of these interventions is virtually guaranteed as women’s information sessions will continue within the normal structure of monthly WU meetings at the commune and village levels and in the case of disaster related IEC for school children, the DoET has now approved plans to integrate DRM lesson plans, teaching materials and content into the syllabus. Result area 3 has been executed very well, has proved a good model for replication and exhibits significant potential for sustainability.

- Another massively successful project component was the piloting of saline tolerant rice varieties. Based on the success of the models with the pilot farmers and the visibility of the models, it was clearly evident to the evaluation team in the field that everyone interviewed was unanimously interested in the new techniques and varieties and would be using them in future. The commune and district agricultural extension authorities also expressed significant interest in further monitoring of the plots with the expectation of promoting their roll out in the near future. Thus the introduced rice varieties appear to have resolved a significant livelihood problem for poor farmers in the area and the sustainability of this intervention seems assured.

- The project has also supported the construction of various disaster mitigation infrastructure projects including roads, a harbour and evacuation houses. It is extremely difficult for the evaluation team to assess the sustainability of these outputs since they have only just been completed. No major problems were reported during construction and it can be expected that these outputs will be of use to communities for some time to come. It is however noted that frequently the maintenance of such infrastructures is typically undervalued in commune budgets and whilst there were assurances otherwise, this is always a problem in Vietnam. In this case though the project has by involving the community in the construction of these infrastructures (and the partial payment for them), seen that local people perhaps have a greater stake and say in making sure that they are properly maintained.

The fact that the villagers helped to pay for (either in terms of a financial or an in-kind payment through labour) in itself is an important point. Villagers voted at a meeting as to whether they should contribute more to add value to the CARE investment, with a greater than 50% vote for additional contributions, the village would then commit with people making contributions of roughly 100,000 VND/adult (the amount was a voluntary contribution, not an enforced amount by commune/village leaders) and poorer villagers were able to make in-kind contributions through labour. Many of the more vulnerable members of the community including elderly, disabled or very poor did not have to contribute. In total these additional contributions represented approximately 10% of total costs of construction. This is an unanticipated benefit from the project with the final output improved by the added-value from the community. It shows initiative on the part of project partners at the local level and helps to ensure that there is a greater sense of ownership of project results.

# Lessons Learned

The following section identifies 10 lessons learned following the evaluation team’s field visit and based on the key findings above.

Project Design

- Research project interventions: Proposed project interventions should be thoroughly researched and vetted with project partners at all levels and other projects operating in similar sectors in the same area at project design stage. This point is made with particular reference to the original EWS envisaged for the project. The project did include a feasibility study but even before it got to this stage it should have been possible to determine the appropriateness of this activity. The fact that the originally conceived EWS was considerably more expensive and would have taken a much longer timeframe to realize meant that one of the project’s key result areas was significantly affected. The project managed to adapt to this and have introduced a simple and sound information dissemination system into the project area. However this inevitably entailed substantial adjustments to the budget, all of which of course have to be conceptualized, researched and eventually approved – this takes up valuable time for a project which only has a timeframe of 15 months (eventually extended to 16.5 months).

- Participatory Design Process: Other than the oversight with respect to the EWS, the project was on the whole, well-designed and this is largely thanks to the participatory processes employed during the design stage. Certainly the participatory needs assessment is a valuable tool in shaping the project according to local needs.

- Project Timeframe: It was widely commented that the project was too short. The evaluators believe that a reasonably appropriate mix of humanitarian assistance and longer term rural development assistance was achieved – there needs to be a balance between developing plans and raising awareness and actually providing certain tangible livelihood improvement mitigation measures. On the other hand it is difficult to achieve and/or observe impacts on livelihoods in such a short timeframe. The project would likely have achieved an even greater impact in two particular areas with a longer timeframe; 1) a longer timeframe would have allowed for the opportunity for consolidating the participatory CBDRM planning process at year 1 review stage and 2) a longer timeframe would have allowed for a greater opportunity to see impacts of the agricultural pilot models. It should be noted that neither of these activities should particularly involve substantial increases in cost.

- Baseline and monitoring indicators: The project was always going to have a significant focus on raising awareness and building capacity and this was known at a very early stage (even prior to the needs assessment), thus in order to provide a better framework for project evaluation, the needs assessment could have incorporated a KAB element in the household interviews which would then in turn provide a useful baseline for measuring project impact.  In fact a fairly standard livelihood survey across a range of livelihood indicators (including incomes, poverty ranking, agricultural production, access to clean water, health care, health problems, disaster impacts) would be extremely useful towards creating a quantitative benchmark even if it is of a limited sample size. It is noted that the needs assessment comprised household interviews in any case, so why not keep such information recorded in a simple excel format and this would serve as a baseline.

- Project implementation structure: The project adopted a very appropriate project implementation structure, very familiar to local partners and beneficiaries and this assists with project delivery in such a short timeframe. Future interventions of this type should follow this model.

The Participatory Planning Process

- A greater focus on capacity building at the grassroots levels: One of the most important lessons learned from the project relates to the participatory planning process, particularly as this was one of the key result areas. As is discussed in Hoang Van Duong et al’s report, district and provincial level partners within the FSCBs felt that the training was too long, meanwhile the grassroots practitioners at commune/village level only received 2-3 days training on CBDRM processes and much of this was focused on technical terms, definitions and theory. It would appear that the trainings have thus been the wrong way around i.e. commune and village FSCB staff require further and more intensive training with practical opportunities for practicing PRA and community facilitation techniques, whilst district and provincial staff only need an overview of this process (since they will not be on the ground practitioners) as well as knowledge of how to interpret the results of the participatory process and translate them into action (organizational and management skills and budget allocation). The fact that the on the ground staff were not fully trained is probably the main reason behind why the resulting DRMPs do not appear to fully reflect the needs of specific vulnerable groups within the community.

- Targeted planning with vulnerable groups: The CBDRM planning process has not appeared to fully recognize the different levels of access to power and voice within a community. This is reflected to some degree in the results from the evaluation team’s questionnaires, where it is apparent that not all are completely satisfied with the process. It was also noted that there was no segregated planning with different groups eg. a women’s group and/or other vulnerable groups. Without the use of these participatory planning tools the resultant plans will indeed reflect the village’s voice as a whole but it will tend to be the more powerful actors within the community that will talk in the meetings leading to the identification of the overall needs of the majority (with a tendency for these to be longer term socio-economic development aspirations) rather than perhaps what may often appear to be the somewhat trifling concerns of the poor and vulnerable. Certainly there is enough evidence to suggest from the evaluation teams questionnaires and qualitative information from discussions that a lot of people still remained shy and found it difficult to talk in these meetings.

Raising Awareness

- The ToT Approach:  The project has clearly placed a considerable emphasis on awareness raising and has been it would appear extremely successful in doing so. One of the features of the awareness raising approach has been to channel messages through schools and the WU and it has done this through a ToT approach. The evaluation team believed this to be an extremely efficient use of project funds that utilizes existing opportunities in the Vietnamese societal and institutional structure to great effect. In particular the fact that the DoET in the province is now incorporating the DRM lessons for schoolchildren developed by the Training Centre into the school syllabus is a great achievement. Involving the DoET so closely in the project has been an excellent idea and appears to be leading to an extremely sustainable outcome and with maximized impact.

Mitigation Measures

- Successful saline tolerant rice varieties: Under result area 2, the project sponsored an agricultural solutions study focused on trying to resolve problems faced by local farmers in the target area. The recommendations from this study proposed the utilization of particular saline tolerant rice varieties which were subsequently taken up in pilot trials under result area 4. Results from these trials in all 3 communes appear to have been a resounding success, seemingly resolving a significant livelihood problem for local people and providing a very appropriate mitigation measure for farmers affected by the salinity of soils in the project area (caused by coastal storm surges). A slightly longer period is still required in order to fully monitor and assess the effectiveness and impact of the new rice varieties over another 2-3 seasons, however early indications are extremely positive with farmers experiencing an average of 21% increase in yields as well as reduced production costs. The evaluation team would also like to comment once again on the appropriateness of the FFS approach in terms of knowledge transfer. It is likely that the models will be appropriate in similar coastal areas also affected by saline soils. Thus replicating these models using the FFS approach would be an appropriate intervention in such cases.

- Community-based construction and monitoring: The evaluation team appreciated the project’s participatory approach to involve local communities and households in the construction, monitoring and supervision of infrastructure projects agreed as priorities in the DRM planning process (result area 1) and subsequently implemented as mitigation measures in result area 4. During interviews it was clear that the community enjoyed this opportunity to shape their own future and indeed the fact that they were allowed to do so under the project, strategically encourages further participation and demonstrates the community’s capability to do so with similar interventions in the future. As such it represents a pilot implementation of the grassroots democracy decree which provides the legal space for communities to be involved in infrastructural planning and implementation. Through this approach, the project has provided another opportunity for local people to raise their voices and play an integral role in decisions which affect their lives as opposed to the business as usual top-down planning procedures. However consultations during the evaluation mission revealed that the planning and implementation of these mitigation measures (infrastructure projects) and in particular the roads took too long. It is likely that the administrative and procurement processes should be reviewed in order to improve this approach as overly complicated and drawn out procedures may threaten community interest and involvement.

# Recommendations

The evaluation team’s recommendations are logically focused on addressing weaknesses and replicating successes identified in the previous lessons learned section.

- Project Design

Positive aspects from the project design included the participatory needs assessment and the project implementation structure – these should be replicated in the design of future interventions of type. The evaluation team would only make one or two observations intended to improve this design process further.

- Firstly, to thoroughly research proposed interventions to ensure that they are both appropriate to local capacities and needs and that they are streamlined with other government and external assistance project interventions in order to harmonise and maximize all development actions.

- Secondly, for projects which are likely to focus on capacity building and awareness raising, the design or early implementation phase could incorporate a more quantitative assessment of the baseline situation. DRM projects in Vietnam need to balance the promotion of participatory planning processes, capacity building and awareness-raising with some tangible mitigation measures and community development/livelihood support. If this is known from the start then a standard household livelihoods survey incorporating KAB (in terms of disaster preparedness) aspects would also provide a useful baseline against which to measure project success and impact.

- Thirdly, given that this mix of humanitarian assistance and longer term development support is generally desired in the context of poor communities, whose livelihoods are vulnerable to shocks derived from natural disasters in Vietnam, a slightly longer timeframe of 2-2.5 years is advocated. Not only would this longer timeframe allow for the securing and observation of effectiveness and impact of community/livelihood mitigation measures but would also crucially allow for consolidating and improving DRM planning processes.

- The Participatory Planning Process

The project sponsored an independent documentation of lessons learned and evaluation of the CBDRM process. This study has identified a number of weaknesses in the participatory planning processes which need to be taken on board before replication elsewhere. The evaluation team believes that this aspect needs to receive considerable attention.

- The FSCB members at the grassroots (commune/village) levels require a greater amount of training and capacity development support in order to be able to fully and properly implement PRA and facilitation skills and tools in the field. Thus, this requires firstly restructuring the balance of training requirements for participants from provincial, district and commune/village levels i.e. district and provincial staff should receive an overview of the participatory process but most importantly how to use its results (in particular how to assimilate participatory plans within the top-down planning process from provincial down to district level), meanwhile longer and more detailed training on PRA and community facilitation techniques for grassroots practitioners. Secondly, the content of this training at the local levels needs to be more practical and focus on the transfer of skills/tools for participatory consultation with opportunities for practicing these skills rather than the existing training content which is more oriented towards classroom theory.

- The DRMPs need to better incorporate the needs of explicit vulnerable groups such as female headed households and other vulnerable groups. This should come from segregated consultation processes with specific focus groups.

- The DRMPs currently represent something of a wish list for external support for longer term socio-economic development needs as opposed to measures the community can implement for themselves. Future project’s need to try and resolve this dependency mentality and encourage a greater level of self-reliance in CBDRM planning and implementation.

- The CBDRM planning process could also have been improved by representatives from groups being involved at the second stage of DRMP review (as opposed to the whole community). This would streamline and facilitate a quicker process that would save time and maintain enthusiasm for the process. Inevitably this means that groups and their representative leaders must be identified in the CBDRM process which does not appear to have occurred this time around. One might anticipate the establishment of groups for poor farmers, female headed households, poor fishers and women.

- There is a need to review and clarify the HCVA and CBDRM process. It is probably necessary to develop a detailed format for the presentation of the resultant DRMP which clearly documents and reports on how the processes were implemented (as opposed to just the DRMP itself). In fact the process itself is almost as important as the DRMP itself and therefore the format might be something akin to a report with a detailed description of the methodology, the presentation of tables (and possibly graphs) illustrating different groups and their opinions, and finally how the agreed actions were ranked and/or prioritized. The central concept being to document how the DRMP evolved and in so doing it creates a clear guide to community-level practitioners.

- A major revelation from the CBDRM study was that the communes are still operating two DRM plans i.e. one developed by the communities and the top-down plan from provincial FSCB to district levels and then communes. If this persists then it is extremely likely that it will only be the formal government planning process that will prevail. Thus district and provincial level staff need to be able to integrate community level planning into their own planning processes to result in only one DRMP. Two plans will only lead to confusion and the inevitable result is that the formal government plan will be prioritized. Therefore this point relates to point (i) above i.e. the need for a restructuring of training contents at different government levels.

In order to integrate participatory plans into the SEDP it is necessary to be mindful of the government’s own development planning cycles. The evaluators would propose that village-level consultations and participatory planning should begin around April with a view towards prioritization and synthesis of CBDRM needs at the commune level by around June. Subsequently, the commune level plans would in turn be prioritized and synthesized at the district level by the end of July in good time for the development of provincial budgets for socio-economic development in the following year which generally occurs around August-September. Clearly this is only a basic overview and the evaluators would recommend a more detailed study and analysis of state DRM budgets and planning procedures in order to fit the two (top-down and bottom-up) planning processes together in the most logical manner. It should be stated however that such a process should in no way distill or dilute self-reliant interventions at the village level.

- Raising Awareness

The project has it would appear been extremely successful in raising the awareness of local communities of the importance of getting prepared. In particular the evaluation team would like to emphasize the success of adopting a ToT approach with commune health workers, school teachers (and importantly the DoET) and the WU. This is an extremely cost-efficient approach towards maximizing project impact and should be replicated elsewhere.

- Mitigation Measures

- The agricultural pilots involving saline tolerant rice varieties should continue to be monitored closely and shows excellent potential for further uptake and wider scale replication in either a follow on project intervention or with similar coastal communities in Thanh Hoa. The FFS approach is also an appropriate mechanism for knowledge transfer in this regard.

- Follow on projects or interventions of type should maintain the involvement of communities in planning, implementation, construction and monitoring of relevant infrastructure projects. However, the planning and procurement processes should be reviewed in order to streamline them and allowing for their efficient and timely completion in order to encourage and maintain community interest in these processes. It is suggested that future construction activities of type allocate payments on a milestone or output basis with a lump sum contract. This would be a much more straightforward contract and could reduce paperwork and speed up procedures significantly.

- CARE should consider conducting an ex-post evaluation of infrastructure projects and construction/distributed outputs. This is important due to the considerable amounts of investment in items such as evacuation centres or roads but need not be a costly exercise and could help to inform future projects and programmes on which types of outputs continue to be maintained and used for their intended purpose as well as other secondary or unintended benefits.

# Annex 1: Evaluation Work Plan

| Activity | Location | Person | Date |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Desk review | HN | All |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Methodology | HN | All |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Meet CARE/Check Method - Refine | HN | All |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Report Outline | HN | RR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output Tables | HN | RR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Design Training Course - Interviews | HN | Khoat |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Translation of materials | HN | Que |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Deploy to field | HN-TH | Khoat, Que |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provincial partners meeting | TH | Khoat |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Red Cross | TH | Que |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training Course | Hau Loc | Khoat, Que |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| HH interviews | Hai Loc | Que |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key informant – WU FSCB & CPC | Hai Loc | Khoat |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key informant - teachers | Hai Loc | Que |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| HH Interviews | Hung Loc | Khoat |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key informant – WU, FSCB & CPC | Hung Loc | Que |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key informant - teachers | Hung Loc | Khoat |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| HH Interviews | Da Loc | Que |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key informant – WU FSCB & CPC | Da Loc | Khoat |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key informant - teachers | Da Loc | Que |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DPC, DARD, FSCB & WU | Hau Loc District | Khoat, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Interview SRC | SRC Project Office | Que |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Rtn HN | TH-HN | Khoat, Que |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Compile Information | HN | Khoat, Que |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team meeting & Analysis | HN | All |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Preparation for Workshop | HN | Khoat/Que |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Workshop | TH | Khoat/Que |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft Report | HN | All |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Report | HN | RR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Annex 2:  TORs of the Evaluation

CARE INTERNATIONAL IN VIETNAM

DRAFT

TERMS OF REFERENCE

FOR

CONSULTANCY EVALUATION STUDY – THANH HOA PROVINCE

Project:	 Increase local Disaster Risk Management capacity in Thanh Hoa Province

Location:		THAH HOA Province, Vietnam

Duration:		20 days from October, 2009

Key counterparts:	Department of Agriculture and Rural Development, Committee for Flood and Storm Control, Women’s Union, Red Cross, District and Communes authorities.

Reporting to:	Project Manager

CARE in Vietnam is the representative of CARE International in Vietnam. CARE in Vietnam operates under the lead membership of CARE Australia. The laws and regulations of the Government of Vietnam apply to all staff, contractors and consultants.   Within CARE in Vietnam the Country Director has overall management authority as the representative of the lead member and of CARE International.

A. Background information

Communities in Thanh Hoa in general, especially in Hau Loc district, are vulnerable to multiple hazards. The combined impacts from floods, storm, storm surge, drought and salinity both hinder development and maintain very high poverty rates (Source; District government). The local governments at provincial, district and commune level have developed a storm and flood warning system and organise disaster response which transmits information and instructions downwards from higher levels of government.

However, the capacity of local government is insufficient to provide appropriate leadership within the disaster management of the area. Weaknesses have been identified in the areas of comprehensive disaster risk management planning and implementation, information management, and early warning systems that do not reflect the needs of local conditions.

Local mass organisations such as Red Cross and Women’s Union have been important actors in disaster risk management and emergency response, undertaking projects in disaster risk management, training in Community Based Disaster Risk Management (CBDRM) and public awareness campaigns. While active in the area, their technical and physical capacities and funding sources are the main constraints to their effectiveness.

Local communities are struggling to cope with these frequently recurring multiple hazards, which are often characterised by their long lasting impacts. They face the serious problems of lack of clean drinking water, salinity in arable land, loss of crops and illness from the disasters. Women headed poor households are among the worst affected from the disaster, having limited labour resources and lacking alterative income to make up the loss from the disasters.

This project aimed to reduce poverty and household vulnerability to natural disasters in Thanh Hoa Province through the enhancement of early warning systems, natural disaster preparedness, and by building the capacity of households, communities, mass organisations, local government (Provincial, District and Commune levels) to reduce the impact of recurrent disasters.

The project will be completed at the end of October 2009.  In order to verify and quantify the outcomes and affect (and potentially the impact) of the Project, CARE is commissioning a final project evaluation.  The evaluation shall be led by an external consultant with the full cooperation and support of the project team at CARE.

B. Scope of services:

The Consultant will work with CARE in Vietnam’s project team and local partners to conduct the evaluation study.  The main objective of the project evaluation is to assess the outcomes of the activities against the project objectives.

Objectives

The 15 month project aims to improve management capacity in early warning, information management and comprehensive planning in natural disaster risk management, targeting provincial, district and the commune government, as well as target local schools and mass organisations such as the Red Cross Vietnam Thanh Hoa branch and Women’s Unions at local level, to strengthen their capacity in DRM, especially in training and public awareness.

In addition, the proposed action will work with the targeted communes.  Special activities will be organized to meet the needs of vulnerable groups, enhance community based disaster preparedness and coping capacity to natural disasters in Thanh Hoa province

The project objectives are defined as follows:

- Overall objective: To reduce the vulnerability of coastal communities in Thanh Hoa Province.

- Specific objective: To improve Disaster Preparedness, Mitigation and Response of coastal communities in Thanh Hoa by enhancing capacities of communities, local government and mass organizations

The evaluation will have a participatory nature and is focused on the following key fields related to the project achievements:

- Relevance / appropriateness of the project design, to what extent the project is suited to the particular needs, expectations and priorities of the target communities, local authority, implementing partners and the donor

- Efficiency in use of resources, to what extent the project used the resources in the most economical manner to achieve its objectives?

- Effectiveness and quality of project interventions were the activities achieved satisfactory results in relation to stated objectives. Special focus on the DP measures during responding to the floods

- Impact, what are the results of the intervention - intended and unintended, positive and negative - including the social, economic, environmental effects on individuals, communities and institutions. In particularly, assessment of the project based on its usefulness during the recent emergency situation as results of the flooding.

- Sustainability, are the activities and their impact likely to continue when external support is withdrawn, and will it be more widely replicated or adapted

Key activities

- Background reading, briefing discussions with project team and preparation of resource materials

- Development of an evaluation study design (plan), identification of information needs, drafting data-gathering instruments

- Data-collection at the field level including participatory evaluation methods

- Data processing, analysis and draft report preparation

- Presentation of the evaluation results to project team and partners at a workshop

- Finalisation of evaluation report following comments received from CARE on the draft report

Methodologies

The final evaluation schedule will be determined following discussions between the consultant and the project team prior to the commencement of the evaluation study.  The evaluation study design (plan) and tools will be approved by CARE prior to implementation.

In working with partners, the consultant is expected to be proficient in using a range of participatory tools for data gathering and analysis, including quantitative and qualitative survey techniques, conducting key informant interviews and leading small group presentations.  The consultancy will also involve substantive documentation review, report writing, and workshop presentation.

Expected outputs

The evaluation will result in two products:

- Report containing a comprehensive presentation of the methodology, findings, lessons learnt and recommendations in English and covering, but not limited to:

Title Page

Executive Summary

Table of contents (with page numbers)

List of tables and figures (with page numbers)

- Background

- Description of the methodologies used

- Evaluation findings

- Lessons learned

- Recommendations

Annexes:

    - Evaluation work plan

    - TORs of the evaluation

    - List of those interviewed

- Concise presentation of the main findings, lessons learnt and recommendations to be presented during an evaluation workshop in February 2010

C. Selections criteria / qualifications

The consultant will have extensive experience, knowledge and skills in planning and implementing project evaluations.  In particular the consultant will be competent in quantitative and qualitative research, evaluation tools development, data collection and analysis, and have highly developed report writing skills.  Ideally, the consultant will have experience in review or evaluation of disaster preparedness projects and familiarity with the rural development context in Vietnam.

# Annex 3:  Lists of those Interviewed

### List of key informants from province

- Mr. Kim Ngọc Hiệp- Deputy Head of the External Relationship Affairs Office – Thanh Hoa Provincial People Committee

- Mr. Khương Anh Tấn- Deputy Head of Construction Management Office – Dyke and Dyke Maintenance Management Department in Thanh Hoa

- Mr. Lê Xuân Hảo – Standing commissioner of the Red Cross in Thanh Hoa

### List of key informants from district

- Mr. Trịnh Cao Sơn – Specialist from DARD in Hau Loc

- Mr. Lê Văn Đua - Specialist from DARD in Hau Loc

- Mr. Hoàng Việt Cường - Specialist from DoET in Hau Loc

- Mr. Lê Hữu Giỏi - Head of Health Department in Hau Loc

- Mr. Vũ Xuân Long - Specialist from Industry and Trade in Hau Loc

- Mr. Trịnh Quang Minh - Specialist from Industry and Trade in Hau Loc

### List of key informants from communes and villages

| No | Full name | Sex | Age | Ethnic | Wealth ranking | Village - Commune |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Dang Van Hung | Nam | 65 | Kinh | Poor | Hưng Bắc – Hung Loc commune |
| 2 | Nguyen Thi Phuong | Woman | 49 | Kinh | Poor | Tân Lộc- Hải Lộc |
| 3 | Nguyen Thi Hong | Woman | 50 | Kinh | Poor | Tân Lộc- Hải Lộc |
| 4 | Cao Thị Khue | Woman | 41 | Kinh | Poor | Vạn Thắng- Đa Lộc |
| 5 | Dinh Thi Tam | Woman | 38 | Kinh | Poor | Trường Nam- Hải Lộc |
| 6 | Tang Van Than | Man | 55 | Kinh | Poor | Phú Hòa- Hung Loc commune |
| 7 | Bui Minh Thuyet | Man | 45 | Kinh | Middle | Trường Nam- Hải Lộc |
| 8 | Mai Thuyet Minh | Man | 59 | Kinh | Middle | Tân Lộc- Hải Lộc |
| 9 | Nguyen Van Nam | Man | 50 | Kinh | Poor | Hưng Bắc- Hung Loc commune |
| 10 | Bui Van Muong | Man | 50 | Kinh | Poor | Hưng Bắc- Hung Loc commune |
| 11 | Nguyen Van Thay | Man | 60 | Kinh | Middle | Tây Hòa- Hung Loc commune |
| 12 | Bui Van Hai | Man | 47 | Kinh | Poor | Hưng Bắc- Hung Loc commune |
| 13 | Ngo Van Hoe | Man | 69 | Kinh | Middle | Hưng Bắc- Hung Loc commune |
| 14 | Dinh Thi Truy | Woman | 75 | Kinh | Poor | Đông Thành- Đa Lộc |
| 15 | Nguyen Thi Nhung | Woman | 55 | Kinh | Poor | Vạn Thắng- Đa Lộc |
| 16 | Nguyen Tien Dung | Man | 56 | Kinh | Poor | Trường Nam- Hải Lộc |
| 17 | Doai Ma Binh | Man | 51 | Kinh | Poor | Phú Hòa- Hung Loc commune |
| 18 | Doan Van Bich | Man | 63 | Kinh | Middle | Phú Hòa- Hung Loc commune |
| 19 | Bui Thi Loi | Woman | 47 | Kinh | Poor | Trường Nam- Hải Lộc |
| 20 | Le Van Cu | Man | 60 | Kinh | Poor | Tây Hòa- Hung Loc commune |
| 21 | Tang Thi Khanh | Woman | 61 | Kinh | Poor | Phù Hòa- Hung Loc commune |
| 22 | Vu Thi Thuy | Woman | 33 | Kinh | Poor | Đông Thành- Đa Lộc |
| 23 | Bui Quang Minh | Man | 51 | Kinh | Poor | Hùng Thành- Đa Lộc |
| 24 | Le Thi Mong | Woman | 55 | Kinh | Poor | Tây Hòa- Hung Loc commune |
| 25 | Le Thi Hoa | Woman | 50 | Kinh | Poor | Hưng Thái- Hải Lộc |
| 26 | Bui Thi Nhoi | Woman | 61 | Kinh | Poor | Đông Thành- Đa Lộc |
| 27 | Vu Thi Tuan | Woman | 55 | Kinh | Poor | Đông Thành- Đa Lộc |
| 28 | Nguyen Thi Dinh | Woman | 47 | Kinh | Poor | Trường Nam- Hải Lộc |
| 29 | Le Thi Thuan | Woman | 65 | Kinh | Poor | Y Bình- Hải Lộc |
| 30 | Tran Thi Thuc | Woman | 40 | Kinh | Poor | Đông Thành- Đa Lộc |
| 31 | Vu Thi Van | Woman | 53 | Kinh | Poor | Ninh Phú- Đa Lộc |
| 32 | Nguyen Thi Sieng | Woman | 51 | Kinh | Poor | Đông Thành- Đa Lộc |
| 33 | Nguyen Thi Quyen | Woman | 49 | Kinh | Poor | Trường Nam- Đa Lộc |
| 34 | Nguyen Thi Ly | Woman | 53 | Kinh | Poor | Ai Vích- Hải Lộc |
| 35 | Bui Thi Din | Woman | 54 | Kinh | Middle | Yên Lộc- Đa Lộc |
| 36 | Nguyen Thi Sinh | Woman | 48 | Kinh | Middle | Hưng Thành- Đa Lộc |
| 37 | Dong Thi Tinh | Woman | 62 | Kinh | Poor | Tân Lộc- Hải Lộc |
| 38 | Tran Thi Lan | Woman | 50 | Kinh | Poor | Hưng Thái- Hải Lộc |
| 39 | Le Van Doan | Man | 53 | Kinh | Middle | Tây Hòa- Hung Loc commune |

### List participants of first findings workshop in Hau Loc

| No | Fullname | Address | Sex |
| --- | --- | --- | --- |
| 1 | Hoàng Việt Cường | Hau Loc DoET | Male |
| 2 | Trịnh Cao Sơn | Hau Loc DARD | Male |
| 3 | Lê Văn Đua | Hau Loc DARD | Male |
| 4 | Trịnh Ngọc Minh | Hau Loc Industry and Trade | Male |
| 5 | Hoàng Sỹ Công | Hau Loc Red Cross | Male |
| 6 | Nguyễn Văn Mạnh | Hau Loc Health Department | Male |
| 7 | Trịnh Thị Huyên | Chairman – Hai Loc commune | Female |
| 8 | Đỗ Xuân Liên | Vice chairman – Hai Loc commune | Male |
| 9 | Đồng Công Binh | Chairman, Hai Loc Cooperative | Male |
| 10 | Đinh Trọng Tuấn | Secretary of Hai Loc Youth Union | Male |
| 11 | Nguyễn Thị Phương | Chair woman – Hai Loc commune | Female |
| 12 | Nguyễn Văn Hự | Village leader, Thắng Hùng - Hải Lộc | Male |
| 13 | Ngô Anh Tấn | Village leader, Trường Nam - Hải LỘc | Male |
| 14 | Đỗ Văn Thường | Secretary of communist party, Trường Nam - Hải Lộc | Male |
| 15 | Mai Văn Quyền | Village leader Lộc Tiên - Hải Lộc | Male |
| 16 | Lê Sinh Tuấn | Headmaster of Hải Lộc primary school | Male |
| 17 | Mai Thị Tập | Headmistress, kindergarten in Hai Loc | Female |
| 18 | Nguyễn Văn Đảng | Vice chairman of CPC Hung Loc commune | Male |
| 19 | Mai Văn Bền | Land management staff of Hung Loc commune | Male |
| 20 | Nguyễn Thị Sâm | Chairwoman of Hung Loc commune | Female |
| 21 | Vũ Thành Khuyên | Irrigation and transport staff Hung Loc commune | Male |
| 22 | Nguyễn Phan Anh | Head of Health clinic, Hung Loc commune | Male |
| 23 | Lê Văn Hong | Village leader Tây Hòa - Hung Loc commune | Male |
| 24 | Đoàn Bá Chưởng | Village leader Hưng Bắc - Hung Loc commune | Male |
| 25 | Tăng Xuân Thuận | Village leader Phú Hòa - Hung Loc commune | Male |
| 26 | Đoỗ Thị Tính | Headmistress, kindergarten Hung Loc commune 1 | Female |
| 27 | Nguyễn Thị Tuyết | Teacher of primary school, Hung Loc commune 2 | Female |
| 28 | Vũ Thanh Tâm | Headmaster of lower secondary school, Hung Loc commune | Female |
| 29 | Vũ Xuân Ngọc | Vice chairman CPC, Da Loc commune | Male |
| 30 | Trần Minh An | Irrigation and transport staff Da Loc commune | Male |
| 31 | Đinh Thị Khuyến | Da Loc commune | Female |
| 32 | Trần Thanh Duy | Chairperson of Farmer Union, Da Loc commune | Male |
| 33 | Vũ Việt Hồng | Staff of radio station, Da Loc commune | Male |
| 34 | Vũ Ngọc Vân | Chairperson of learning promotion, Da Loc commune | Male |
| 35 | Vũ Phương Đông | Chairperson, Veteran Union, Da Loc commune | Male |
| 36 | Nguyễn Xuân Nụ | Village leader Vạn Thắng Da Loc commune | Male |
| 37 | Kiều Danh Dự | Village leader Mỹ Điền Da Loc commune | Male |
| 38 | Đào Ngọc Thư | Village leader Đông Hải Da Loc commune | Male |
| 39 | Đỗ Công Nguyên | Secretary, Đông Hải Village, Da Loc commune | Male |
| 40 | Nguyễn Viết Xuân | Village leader Đông Tân Da Loc commune | Male |
| 41 | Vũ Văn Sử | Village leader Đông Thành Da Loc commune | Male |
| 42 | Nguyễn Thế Anh | Deputy head, Police office, Da Loc commune | Male |
| 43 | Bùi Tiến Dũng | Headmistress, kindergarten Đa Lộc | Male |
| 44 | Nguyễn Thị Vinh | Headmistress, kindergarten, Đa Lộc commune | Female |

### List participants of Validation Workshop

| No | Fullname | Address | Sex |
| --- | --- | --- | --- |
| 1 | Mai Thị Nhung | Red Cross Thanh Hóa | Female |
| 2 | Lê Xuân Hảo | Red Cross Thanh Hóa | Male |
| 3 | Nguyễn Văn Phượng | Vice chairman UBND Hau Loc district | Male |
| 4 | Lường Văn Thắng | Administrator, Hậu Lộc | Male |
| 5 | Trịnh Cao Sơn | DARD in Hau Loc district | Male |
| 6 | Hoàng Việt Cường | DoET in Hau Loc district | Male |
| 7 | Lê Hữu Giỏi | Health department, Hau Loc district | Male |
| 8 | Tạ Chí Thuông | Construction and Trade, Hau Loc district | Male |
| 9 | Hoàng Sĩ Công | Red Cross, Hau Loc district | Male |
| 10 | Trần Thanh San | Chairperson, CPC of Da Loc commune | Male |
| 11 | Vũ Xuân Ngọc | Vice chairman of CPC Đa Lộc | Male |
| 12 | Vũ Thị Lý | Chairwoman Đa Lộc | Male |
| 13 | Đinh Thị Khuyến | CPC staff, Da Loc commune | Female |
| 14 | Vũ Minh Thành | Head of health department, Da Loc commune | Male |
| 15 | Nguyễn Xuân Nụ | VILLAGE LEADER Vạn Thắng - Đa Lộc | Male |
| 16 | Lê Thanh Hải | VILLAGE LEADER Hùng Thành - Đa Lộc | Male |
| 17 | Vũ Quốc Sử | VILLAGE LEADER Đông Thành - Đa Lộc | Male |
| 18 | Bùi Văn Dũng | Primary school, Da Loc commune | Male |
| 19 | Nguyễn Văn Tín | Lower secondary school, Da Loc commune | Male |
| 20 | Nguyễn Thị Vinh | Headmistress, kindergarten in Da Loc commune | Female |
| 21 | Vũ Ngọc Phan | Vice chairperson, Đa Lộc agriculture cooperative | Male |
| 22 | Vũ Văn Liêm | CPC Chairperson Hung Loc commune | Male |
| 23 | Nguyễn Văn Đảng | Vice chairman of CPC Hung Loc commune | Male |
| 24 | Mai Văn Bền | CPC, Hung Loc commune | Male |
| 25 | Nguyễn Thị Sâm | Chairwoman Hung Loc commune | Female |
| 26 | Nguyễn Phan Anh | Head of health department, Hung Loc commune | Male |
| 27 | Đoàn Bá Chưởng | VILLAGE LEADER Hưng Bắc - Hung Loc commune | Male |
| 28 | Tăng Văn Thuận | VILLAGE LEADER Phú Hòa - Hưng Lôc | Male |
| 29 | Lê Văn Hong | VILLAGE LEADER Tây Hòa - Hung Loc commune | Male |
| 30 | Trần Văn Hậu | Chairperson, Agriculture cooperative Hung Loc commune | Male |
| 31 | Vũ Thanh Tâm | Headmaster of lower secondary school Hung Loc commune | Female |
| 32 | Phạm Thị Tính | Headmistress, kindergarten Hung Loc commune 1 | Female |
| 33 | Nguyễn Thị Duynh | Headmistress, kindergarten Hung Loc commune 2 | Female |
| 34 | Đinh Thị Tảo | Vice headmistress, kindergarten Hưng Lôc | Female |
| 35 | Trịnh Thị Huyên | CPC Chairperson Hải Lộc | Female |
| 36 | Đỗ Xuân Liên | Vice chairman of CPC Hải Lộc | Male |
| 37 | Đinh Trọng Tuấn | CPC, Hải Lộc | Male |
| 38 | Nguyễn Thị Phương | Chairwoman, Hải Lộc | Female |
| 39 | Vũ Tất Luyện | Head of health department Hải Lộc | Male |
| 40 | Ngô Anh Tấn | VILLAGE LEADER Trường Nam - Hải Lộc | Male |
| 41 | Nguyễn Văn Hự | VILLAGE LEADER Thắng Hùng - Hải Lộc | Male |
| 42 | Trần Văn Truyền | VILLAGE LEADER Đa Phạn - Hải Lộc | Male |
| 43 | Lê Sinh Tuấn | Headmistress, kindergarten Hải Lộc | Male |
| 44 | Nguyễn Thị Xuân | Headmaster of lower secondary school Hải Lộc | Female |
| 45 | Mai Thị Tập | Hiệu trưởng trường mầm non Hải Lộc | Female |
| 46 | Đồng Công Binh | Chairperson, Agriculture cooperative Hải Lộc | Male |
| 47 | Khương Anh Tấn | Provincial FSC, Thanh Hóa | Male |
| 48 | Nguyễn Hồng Vân | Television department, Thanh Hóa | Female |
| 49 | Trần Quốc An | Television department, Thanh Hóa | Male |
| 50 | Nguyễn Viết Nghị | CARE project manager | Male |
| 51 | Hoàng Văn Tuấn | CARE project staff | Male |
| 52 | Hoàng Sĩ Phượng | CARE project manager | Male |
| 53 | Nguyễn Văn Lân | VUSTA in Thanh Hóa | Male |
| 54 | Marten Mylius | DRR coordinator, CARE | Male |
| 55 | Trần Thanh Thùy | CARE project manager | Male |
| 56 | Phạm Văn Thương | CARE project staff | Male |
| 57 | Phan Thị Mùi | CARE project staff | Female |
| 58 | Nguyễn Văn Hồng | DARD in Thanh Hoa | Male |

These projects included The Thanh Hoa Emergency Response Project  (2005-06), GAP Foundation project (water and sanitation) (2007-08), GIFT project (2007-08), Thanh Hoa Mangrove Restoration and Rehabilitation Project  (2007-2010)

HH interviews to be conducted by 1 consultant + 6 partner agency staff