CARE International in Tanzania

TANZANIA NATIONAL VOUCHER SCHEME (TNVS) TRAINING

### ANNUAL IMPLEMENTATION REPORT

OCTOBER 2004 TO 31ST MARCH 2006.

# TANZANIA NATIONAL VOUCHER SCHEME (TNVS) TRAINING REPORT

# Executive Summary

Tanzania National Voucher Scheme - TNVS “HATI PUNGUZO” is a Public Private Partnership that enables groups most at risk from Malaria (pregnant women and infants) to have access to insecticide-treated nets (ITNs) at  a greatly reduced price, also providing free insecticides to the target group to promote re treatment of nets. This National Voucher Scheme will create a countrywide awareness and behavior change on use of ITNs, private sector development and growth of the ITN sector especially into the rural areas.

The Global Fund, funds the Tanzania National Voucher Scheme, and is a national program managed through the National Malaria Control Program. The implementing partners of the TNVS are:

- World Vision Tanzania with CARE – Training and Promotion Agent.

- MEDA – Logistics and Redemption Agent

- IHRDC/ LSHTM – Monitoring and Evaluation Agent

- KPMG - Auditor

CARE Tanzania is one of the partners participating in TNVS project with the component of training in half of the regions in Tanzania mainland together with WVT who also has the component of promotion activities in the whole country

This report presents the training activities implemented by CARE training team from  24th October 2004 to 31st March 2006.

- Goal of TNVS

60% of pregnant women and children under five are protected by ITN by the year 2007

- Training

3.1 Training areas

3.1.

| SN | REGIONS | DISTRICTS |
| --- | --- | --- |
| 1 | Morogoro | Morogoro urban, Morogoro rural, Mahenge, Kilombero, Ulanga, Ngerengere and Mvomero. |
| 2 | Dar Es Salaam | Temeke, Kinondoni and Ilala |
| 3 | Cost | Kibaha, Kisarawe,Mkuranga,Bagamoyo, Rufiji and Mafia |
| 4 | Lindi | Nachingwea, Liwale, Ruangwa and Kilwa |
| 5 | Mtwara | Mtwara urban,Mtwara rural, Newala, Tandahimba and Masasi |
| 6 | Mwanza | Nyamagana,Ilemela,Ukerewe,kwimba,Sengerema,Geita,Missungwiand Magu. |
| 7 | Kagera | Bukoba Municipal, Bukoba rural, karagwe, Muleba,Biharamulo and Ngara. |
| 8 | Kigoma | Kigoma Municipal Kigoma rural Kibondo and Kasulu, |
| 9 | Ruvuma | Songea municipal, Songea rural, Mbinga, Namtumbo and Tunduru |
| 10 | Iringa | Iringa urban, iringa rural, Kilolo,Mufindi, Njombe, Ludewa and Makete. |
| 11 | Mbeya | Rungwe,Kyela, Mbozi and Ileje. |

Activities covered

- Introducing and raising awareness of Hati Punguzo to DMOs and hospital officials in all ten and half regions in-------     districts.

- Training of Council Health Management Team members (CHMT) in the above-mentioned districts as per attached training details achievement.

All the district councils came up with the following strategies/ resolutions in implementing the program

- Mobilization of the scheme to be done in all the  regions at all levels, more emphasis at the family level to ensure use of the treated bed nets.

- The district committed to continue on job training to all other staff in all the facilities.

- The wholesalers and retailers to have clear guidelines in ensuring smooth running of the scheme.

- All CHMT members to do continuous supportive supervision to all facilities offering discount voucher to pregnant women.

- All CHMT agreed to purchase counter books to be supplied to   all the facilities for record keeping for the discount voucher and for the Insecticides re treatment kits as per given guidelines.

- The programme will be integrated into the comprehensive council health Plan (CCHP) of all the districts.

- The discount voucher focal person was assigned to coordinate all the scheme activities and do reporting per each quarter.

The CHMT and RCH staff raised the following issues,

    - Members showed their concern on availability of discount Voucher at the facility, this  issue was clarified by the MEDA regional managers of the respective regions that the initial supply will depend on the data of pregnant women  for the particular facility, but  for the other supplies will depend on each facility  report and requests as per how many vouchers have been given to pregnant women  and the number of stubs returned to the DMO.

    - Shortage of bed net at the shops which will delay women in purchasing bed net once they have their vouchers. It was also elaborated that the shopkeepers will be instructed to have adequate bed net all the time for women to access bed net.

    - The community around was reported to have strong belief on the use of bed net that the rectangular design appears to be like a coffin for them. This needs good methods of mobilization and right malaria messages and use of bed net .

    - The security on keeping the discount Voucher, the team was doubtful on the security of keeping the vouchers at the facility, this was clarified that the program is a government property and the facilities will need to ensure security of the vouchers as they do keep other government properties, the staff will need to follow all the procedures in receiving and issuing the vouchers.

    - The teams agreed to conduct an evaluation for their district after one year of implementation of the scheme, to assess the situation of malaria in their district for pregnant women and under five, and to document all challenges which have emerged during the implementation of the scheme.

    - The focal person to ensure proper reporting of the program activities for each quarter for the life od the programme.

    - To continue working with the community health workers in mobilizing the community and delivering clear messages regarding the discount voucher scheme.

    - To develop linkages with the community leaders in ensuring that the wholesalers and retailers sales the bed nets at the reasonable price as agreed under the market price of the particular area.

3.1.3 CARE had completed its training as planned, enabling Hati Punguzo to be launched in all 10 regions and half of mbeya region as mentioned above.

3.1.4 The CARE training team comprised of 3 trainers and one program support officer who did the initial planning for the training.

##### SUMMARY OF TRAINING OCTOBER – NOVEMBER TEMEKE DISTRICT DSM

|  |  |  |  | CHMT |  |  | RCH |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | # of Participants |  |  | # of | # of Staff Trained |
| Region | District | Date | Focal Person | # of Meetings | M | F | Total | Date | Division | Trainings | M | F | Total |
|  |  |  | Unice Mungure |  |  |  |  |  |  |  |  |  |  |
|  |  |  | District RCH Co. | 1 | 11 | 10 | 21 |  |  | 1 | 0 | 21 |  |
|  |  |  |  |  |  |  |  |  |  | 1 | 0 | 29 |  |
|  |  |  |  |  |  |  |  |  |  | 1 | 8 | 37 |  |
| Dar | Temeke |  | Total |  |  |  |  |  |  | 3 | 8 | 87 | 95 |
|  |  |  | Fanuel Kipesha |  |  |  |  |  |  |  |  |  |  |
|  |  | 20/9-22/9/04 | District Malaria Co. | 1 | 4 | 8 | 12 |  |  | 1 | 0 | 22 | 22 |
|  |  | 23-24/09/04 |  |  |  |  |  |  |  | 1 | 1 | 19 | 20 |
|  |  | 24-26/09/04 |  |  |  |  |  |  |  | 1 | 0 | 14 | 14 |
|  | Kinondoni |  | Total |  |  |  |  |  |  | 3 | 1 | 55 | 56 |
|  |  |  |  |  |  |  |  |  |  | 1 | 1 | 14 |  |
|  |  |  |  |  |  |  |  |  |  | 1 | 1 | 16 |  |
|  |  | 9/09/04-17/09/04 | Mary Kyando |  |  |  |  |  |  |  |  |  |  |
|  |  |  | District Cont. Ed. Co |  |  |  |  |  |  | 1 | 2 | 27 |  |
|  |  |  |  |  |  |  |  |  |  | 1 | 1 | 28 |  |
|  | Ilala |  | Total | 1 | 9 | 16 | 25 |  |  | 4 | 5 | 85 | 90 |
| Total | For Dar es Salaam |  |  | 3 | 24 | 34 | 58 |  |  | 20 | 20 | 367 | 297 |

SUMMARY OF TRAINING OCTOBER – NOVEMBER Morogoro urban

|  |  |  |  | CHMT |  | RCH |
| --- | --- | --- | --- | --- | --- | --- |
| Region | District | Date | Point Person | # of Meetings | # of Participants |  | # of | # of Staff Trained |
|  |  |  |  |  | M | F | Total |  | Trainings | M | F | Total |
| Morogoro | Urban | 18/10/04 | Immakilata Mhagama | 1 | 9 | 8 | 17 | ?? |  |  |  |  |
|  |  | 19/10/04 |  |  |  |  |  |  | 1 | 0 | 22 | 22 |
|  |  | 20/10/04 |  |  |  |  |  |  |  |  |  |  |
|  |  | 21/10/04 |  |  |  |  |  |  | 1 | 1 | 17 | 28 |
|  |  | 22/10/04 |  |  |  |  |  |  |  |  |  |  |
|  |  | 23/10/04 |  |  |  |  |  |  | 1 | 1 | 17 | 28 |
| Total |  |  |  |  |  |  |  |  | 3 | 2 | 76 | 78 |

SUMMARY OF TRAINING OCTOBER – NOVEMBER Morogoro rural

|  |  |  |  | CHMT | RCH |
| --- | --- | --- | --- | --- | --- |
| Region | District | Date | Point Person | # of Meetings | # of Participants | Division | # of | # of Staff Trained |
| Morogoro | Rural | 18/10/04 | Bayo Maro |  | M | F | Total |  | Trainings | M | F | Total |
|  |  | 25/10/04 |  |  |  |  |  | Ngerengere | 1 | 15 | 10 | 25 |
|  |  | 26/10/04 |  |  |  |  |  |  |  |  |  |  |
|  |  | 27/10/04 |  |  |  |  |  | Matombo | 1 | 7 | 14 | 21 |
|  |  | 28/10/04 |  |  |  |  |  |  |  |  |  |  |
|  |  | 29/10/04 |  |  |  |  |  | Dutumi | 1 | 14 | 15 | 29 |
|  |  | 30/10/04 |  |  |  |  |  |  |  |  |  |  |
|  |  | 31/10/04 |  |  |  |  |  | Turiani | 1 | 10 | 16 | 26 |
|  |  | 1/11/04 |  |  |  |  |  |  |  |  |  |  |
|  |  | 2/11/04 |  |  |  |  |  | Mvomero | 1 | 11 | 20 | 31 |
|  |  | 3/11/04 |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  | 5 | 57 | 75 | 132 |

There were only one CHMT member staff training for both Morogoro rural district and Morogoro Urban districts. The Morogoro Rural CHMT members joined the Morogoro Urban training

##### A: SUMMARY OF TRAINING JANUARY-MARCH

##### KISARAWE, MKURANGA, BAGAMOYO, MAFIA and RUFIJI DISTRICTS in Coast Region

|  |  |  |  | CHMT | RCH |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | # Meetings | # Participants | # of Trainings |
| Region | District | Date | Point Person |  | M | F |  |  | M | F | Total |
| Coast | Kisarawe | 17/1/05 | Dr.Hamza Mzige |  |  |  |  |  |  |  |  |
|  |  | 18//05 |  |  |  |  |  | 1 | 10 | 12 | 22 |
|  |  | 24/1/05 |  | 1 | 10 | 7 | 17 |  |  |  |  |
|  |  | 25/1/05 |  |  |  |  |  | 1 | 7 | 10 | 17 |
|  |  | 26/1/05 |  |  |  |  |  |  |  |  |  |
|  |  |  | Sub Total | 1 | 10 | 7 | 17 | 2 | 17 | 22 | 39 |
|  | Mkuranga | 1/2/05 | Twaha Mbaraka | 1 | 11 | 5 | 16 |  |  |  |  |
|  |  | 2/2/05 |  |  |  |  |  | 1 | 18 | 12 | 30 |
|  |  | 3/2/05 |  |  |  |  |  |  |  |  |  |
|  |  | 4/2/05 |  |  |  |  |  | 1 | 1 | 25 | 26 |
|  |  | 5/2/05 |  |  |  |  |  |  |  |  |  |
|  |  |  | Sub Total | 1 | 11 | 5 | 16 | 2 | 19 | 37 | 56 |
|  | Bagamoyo | 18/2/05 | Dr. Willy Mbawala | 1 | 18 | 2 | 20 | 1 | 3 | 23 | 26 |
|  |  | 21/2/05 |  |  |  |  |  |  |  |  |  |
|  |  | 22/2/05 |  |  |  |  |  |  |  |  |  |
|  |  | 23/2/05 |  |  |  |  |  | 1 | 10 | 12 | 22 |
|  |  | 24/2/05 |  |  |  |  |  | 1 | 8 | 24 | 32 |
|  |  |  | Sub Total | 1 | 18 |  | 20 | 3 | 21 | 59 | 80 |

|  | Mafia | 1/3/05 | Dr. Said Salihina | 1 | 10 | 2 | 12 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2/3/05 |  |  |  |  |  |  | 13 | 13 | 26 |
|  |  | 4/3/05 |  |  |  |  |  |  |  |  |  |
|  | Rufiji | 10/2/05 | Agatha Mkikima | 1 | 13 | 2 | 15 |  |  |  |  |
|  |  | 11/2/05 |  |  |  |  |  | 1 | 1 | 25 | 26 |
|  |  | 12/2/05 |  |  |  |  |  |  |  |  |  |
|  |  | 13/2/05 |  |  |  |  |  | 1 | 2 | 22 | 24 |
|  |  | 14/2/05 |  |  |  |  |  |  |  |  |  |
|  |  | 15/2/05 |  |  |  |  |  | 1 | 6 | 37 | 43 |
|  |  | 16/2/05 |  |  |  |  |  |  |  |  |  |
|  |  |  | Sub Total | 1 | 13 | 2 | 15 | 5 | 9 | 84 | 93 |
|  |  |  | GRANDTOTAL | 3 | 62 | 18 | 80 | 7 | 79 | 215 | 294 |

B: SUMMARY OF TRAINING JANUARY-MARCH 2005:

Lindi Urban, Lindi rural and Ruangwa districts in Lindi Region

|  |  |  |  | CHMT | RCH |
| --- | --- | --- | --- | --- | --- |
| Region | District | Date | Point Person | # of Meetings |  | Division | # of Trainings | # of Staff Trained |
|  |  |  |  |  | M | F | Total |  |  | M | F | Total |
| Lindi | Lindi Urban |  | District RCH Co | 1 | 3 | 7 | 10 |  | 1 | 5 | 11 | 16 |
|  | Lindi Rural |  | Magdalena Kalambo | 1 | 8 | 4 | 12 |  | 2 | 32 | 53 | 85 |
|  | Ruangwa | 21/03/05 | Gonsalva Nmbunga | 1 | 12 | 3 | 15 |  | 2 | 13 | 23 | 36 |
|  |  |  | District RCH Co |  |  |  |  |  |  |  |  |  |
|  |  |  | TOTAL | 3 | 23 | 14 | 37 |  | 5 | 50 | 87 | 137 |
| GRAND TOTAL – Coast and Lindi (January to March 2005) |  |  |  |  |  |  |  |  |  |  |
|  |  | CHMT | 85 | 32 | 117 | RCH |  | 129 | 302 | 431 |

# 3.2 Training Numbers

B: SUMMARY OF TRAINING APRIL-JUNE 2005:

|  |  |  |  | CHMT RCH |
| --- | --- | --- | --- | --- |
| Region | District | Date | Point Person | # of Meetings | # of Participants | Division | # of Trainings | # of Staff Trained |
|  |  |  |  |  | M | F | Total |  |  | M | F | Total |
|  | Nachingwea | 1/4/05 | Tumpe Mwakiposa | 1 | 9 | 5 | 14 |  | 2 | 25 | 38 | 63 |
|  |  |  | District Malaria co |  |  |  |  |  |  |  |  |  |
|  | Liwale | 8/4/05 | Maimuna H. Maokola | 1 | 9 | 6 | 15 |  |  | 20 | 22 | 42 |
|  |  |  | District RCH Co |  |  |  |  |  |  |  |  |  |
| Lindi | Kilwa |  | Innocencia Mangosongo | 1 | 6 | 3 | 9 |  | 2 | 20 | 57 | 77 |
|  |  |  | District RCH Co |  |  |  |  |  |  |  |  |  |
|  |  |  | TOTAL | 1 | 24 | 14 | 38 |  | 2 | 65 | 117 | 182 |

B: Mtwara Urban, Mtwara Rural, Newala, Tandahimba and Masasi in Mtwara region

|  |  |  |  | CHMT |  | RCH |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | # Meetings | # Participants |  | # of Trainings |
| Region | District | Date | Point Person |  | M | F | Total | Venue |  | M | F | Total |
| Mtwara | Mtwara Urban | 28/05/05 | Mwajuma Omari Abdul | 1 | 5 | 4 | 9 | DMO’s office |  |  |  |  |
|  |  |  | District Malaria co |  |  |  |  |  |  |  |  |  |
|  |  | 30/05/05 |  |  |  |  |  | Ushirika hall | 1 | 7 | 19 | 26 |
|  |  |  | Sub Total | 1 | 5 | 4 | 9 |  | 1 | 7 | 19 | 26 |
|  | Mtwara Rural | 2/04/05 | Hadija Ngotima | 1 | 10 | 8 | 18 | DMO’s office |  |  |  |  |
|  |  |  | District Malaria co |  |  |  |  |  |  |  |  |  |
|  |  | 7/04/05 |  |  |  |  |  | COTS | 1 | 25 | 50 | 75 |
|  |  |  | Sub Total | 1 | 10 | 8 | 18 |  | 1 | 25 | 50 | 75 |
|  | Newala | 10/05/05 | Lucy Millanzi | 1 | 10 | 1 | 11 | Hospital Hall |  |  |  |  |
|  |  | 10/05/05 |  |  |  |  |  | PHN School | 2 | 10 | 42 | 52 |
|  |  |  | District Malaria co |  |  |  |  | District council hall |  |  |  |  |
|  |  |  | Sub Total | 1 | 10 |  | 11 |  | 2 | 10 | 42 | 52 |

|  | Tandahimba | 16/05/05 | Scholastica Sowani |  |  |  |  | DMO’s office |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 17/05/05 | District RCH Co |  |  |  |  |  | 2 | 23 | 40 | 63 |
|  |  |  | Sub Total | 1 |  |  |  |  | 2 | 23 | 40 | 63 |
|  | Masasi | 23/05/05 | Dr. Josephine Millanzi | 1 | 13 | 2 | 15 | DMO’s office |  |  |  |  |
|  |  | 24/05/05 | District Malaria co |  |  |  |  | COTS | 3 | 39 | 72 | 111 |
|  |  |  | Sub Total | 1 | 13 | 2 | 15 |  | 3 | 39 | 72 | 111 |
|  |  |  | GRAND TOTAL | 3 | 62 | 18 | 80 |  | 7 | 104 | 223 | 327 |

GRAND TOTAL – Mtwara and Lindi (April  - June, 2005)

|  |  |  |  | CHMT |  | RCH |
| --- | --- | --- | --- | --- | --- | --- |
| GRAND TOTAL – Mtwara and Lindi (April - June, 2005) |  |  | M | F | TOTAL |  |  | M | F | TOTAL |
|  |  | CHMT | 86 | 32 | 118 | RCH |  | 169 | 340 | 509 |

##### SUMMARY OF TRAINING JULY – SEPTEMBER 2005: Mwanza, Kigoma and Kagera Regions

|  |  |  |  |  | CHMT |  |  | RCH |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Region | District | Date | Point Person | # of Meetings | # of Participants | Division | # of Trainings | # of Staff Trained |
|  |  |  |  |  | M | F | otal |  |  | M | F | Total |
| Mwanza | Nyamagana & Ilemela (Mwanza City) | 3/08/05 | Alodia Festo RCH coordinator | 1 | 16 | 3 | 19 |  | 3 | 22 | 45 | 67 |
|  | Ukerewe | 23/08/05 | Winston Nongwe, Malaria focal person | 1 | 16 | 9 | 25 |  | 3 | 13 | 52 | 65 |
|  | Kwimba | 30/08/05 | Rebecca Mashiri RCH coordinator | 1 | 18 | 5 | 23 |  | 3 | 25 | 48 | 73 |
|  | Sengerema | 06/09/05 | Mgonja, Malaria focal person | 1 | 14 | 2 | 16 |  | 4 | 36 | 78 | 114 |
|  | Geita | 17/09/05 | Nassoro Ramadhani, Malaria focal person | 1 | 9 | 3 | 12 |  | 4 | 27 | 81 | 108 |
|  | Missungwi | 16/08/05 | Bertha Yohana, RCH coordinator | 1 | 17 | 2 | 19 |  | 4 | 27 | 48 | 75 |
|  | Magu | 10/08/05 |  | 1 | 14 | 4 | 18 |  | 4 | 18 | 90 | 108 |
|  |  |  | TOTAL | 7 | 104 | 28 | 132 |  | 21 | 168 | 442 | 610 |

B: Kigoma region

|  |  |  |  |  | CHMT |  |  | RCH |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Region | District | Date | Point Person | # of Meetings | # of Participants | Division | # of Trainings | # of Staff Trained |
|  |  |  |  |  | M | F | Total |  |  | M | F | Total |
| Kigoma | Kibondo | 19/09/05 | Dafrosa Rweyongeza, RCH Coordinator | 1 | 16 | 7 | 23 |  | 4 | 32 | 72 | 104 |
|  | Kasulu | 26/09/05 | Godfrey Shija, Malaria Coordinator | 1 | 18 | 5 | 23 |  | 3 | 43 | 46 | 89 |
|  | Kigoma Municipal | 29/09/05 | Scolastica Mwakipiti, RCH Coordinator | 1 | 12 | 10 | 22 |  | 1 | 1 | 29 | 30 |
|  | Kigoma Rural | 03/010/05 | Martin Bhilontse, DCCO | 1 | 8 | 2 | 10 |  | 4 | 47 | 63 | 110 |
|  |  |  | TOTAL | 4 | 54 | 24 | 78 |  | 12 | 123 | 210 | 333 |

C: Kagera Region

|  |  |  |  |  | CHMT |  |  | RCH |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Region | District | Date | Point Person | # of Meetings | # of Participants | Division | # of Trainings | # of Staff Trained |
| Kagera |  |  |  |  | M | F | Total |  |  | M | F | Total |
|  | Bukoba Municipal | 22/08/05 | Fatuma Rashidi RCH coordinator | 1 | 11 | 2 | 13 |  | 1 | 0 | 20 | 20 |
|  | Bukoba Rural | 27/08/05 | Aisha Rugusha, RCH coordinator | 1 | 9 | 10 | 19 |  | 2 | 13 | 47 | 60 |
|  | Karagwe | 1/09/05 | Winfrida Kemilembe, RCH Coordinator | 1 | 10 | 3 | 13 |  | 3 | 20 | 67 | 87 |
|  | Muleba | 12/09/05 | Robinson Ntigererwa, | 1 | 9 | 8 | 17 |  | 2 | 20 | 48 | 68 |
|  | Biharamulo | 16/09/05 | Domina Ruigaiganisa, RCH Coordinator | 1 | 11 | 5 | 16 |  | 2 | 21 | 45 | 66 |
|  | Ngara | 19/09/05 | Stanley Galani, Malaria coordinator | 1 | 7 | 4 | 11 |  | 2 | 21 | 50 | 71 |
|  |  |  | TOTAL | 6 | 57 | 32 | 89 |  | 12 | 95 | 277 | 372 |

GRAND TOTAL – Mwanza Kagera and Kigoma (July  - September, 2005)

| GRAND TOTAL – Mwanza, Kagera and Kigoma July - Sep. 2005) |  | M | F | TOTAL |  |  | M | F | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CHMT | 215 | 84 | 299 | RCH |  | 386 | 929 | 1,315 |

SUMMARY OF TRAINING  October to December  2006  RUVUMA REGION

|  |  |  |  |  | CHMT |  | RCH |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Region | District | Date | Point Person | # of Meetings | # of Participants M F TOTAL | # of Trainings | # of Staff Trained M F |
| Ruvuma | Songea Rural | 7 Nov.2005 | Irmunda Komba DRCH coordinator | 1 | 12 | 2 | 14 | 4 | 9 | 72 | 81 |
|  | Songea Urban | 14 Nov. 2005 | Sarah Midas DRCH Coordinator | 1 | 11 | 4 | 15 | 1 | 1 | 19 | 20 |
|  | Mbinga | 18 Nov. 2005 | Felix Kinunda Malaria Focal Person | 1 | 16 | 2 | 18 | 6 | 18 | 126 | 144 |
|  | Namtumbo | 28 Nov. 2005 | Robert Njawa Malaria Focal person | 1 | 11 | 4 | 15 | 3 | 33 | 37 | 70 |
|  | Tunduru | 2 Dec. 2005 | Stella Mbocho DRCH coordinator | 1 | 15 | 2 | 17 | 4 | 24 | 69 | 93 |
|  | Bukoba rural | 7th to 10th Nov 2005 | Aisha Rugusha DRCHC | 0 | 0 | 0 | 0 | 2 | 10 | 43 | 53 |
|  |  |  | TOTAL |  | 65 | 14 | 79 | 20 | 95 | 366 | 461 |

GRAND TOTAL – Ruvuma (October - December, 2005)

| GRAND TOTAL – Ruvuma |  |  | M | F | TOTAL |  |  | M | F | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | CHMT | 66 | 13 | 79 | RCH |  | 95 | 366 | 461 |
| Bukoba Rural |  | CHMT | 0 | 0 |  |  |  | 10 | 43 | 53 |

##### SUMMARY OF TRAINING  Jan to March  2006 Iringa and Mbeya regions

|  |  |  |  |  | CHMT |  | RCH |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Region | District | Date | Point Person | # of Meetings | # of Participants M F TOTAL | # of Trainings | # of Staff Trained M F |
| Iringa | iringa urban | 09 Jan 2006 | Hamisi Nyabai Malaria Coordinator | 1 | 15 | 6 | 21 | 1 | 3 | 24 | 27 |
|  | Iringa rural | 10 Jan 2006 | Ezekiel Sanga Malaria Coordinator 0744051795 | 1 for both | 16 | 9 | 25 | 4 | 30 | 80 | 110 |
|  | Kilolo | 10 Jan 2006 | Nimrodi Chengulla Mal co 0748438445 |  |  |  |  | 2 | 18 | 63 | 81 |
|  | Mufindi | 16 Jan 2006 | Dr Peter Mwenda Mal co O745626398 | 1 | 14 | 3 | 17 | 3 | 29 | 53 | 82 |
|  | Njombe | 20 Jan 2006 | Anzinwise Duma DRCHC 0744404619 | 1 | 12 | 11 | 23 | 5 | 24 | 133 | 157 |
|  | Ludewa | 30 Jan 2006 | Imelda M Mnyagalla DRCHC | 1 | 13 | 1 | 14 | 3 | 33 | 57 | 90 |
|  | Makete | 6 Feb 2006 | Christopher Musika Malaria Coordinator 0748933542 | 1 | 13 | 7 | 20 | 2 | 16 | 44 | 60 |
|  |  |  | TOTAL FOR IRINGA REGION | 7 | 83 | 37 | 120 | 20 | 162 | 440 | 602 |
| Mbeya | Rungwe | 13 Feb 2006 | Felix Mwakapalila Mal Co | 1 | 11 | 4 | 15 | 3 | 40 | 37 | 77 |
|  | Kyela | 16 Feb 2006 | Tupoke Gidion Mal co 0744918415 | 1 | 15 | 3 | 18 | 3 | 20 | 43 | 63 |
|  | Mbozi | 22 Feb 2006 | Agnes Ng’ambi DRCHC 0744528198 | 1 | 11 | 2 | 13 | 3 | 33 | 54 | 87 |
|  | Ileje | 27 Feb 2006 | Monica kapuge DRCHC 0748414869 | 1 | 7 | 5 | 12 | 2 | 0 | 43 | 43 |
|  |  |  | TOTAL FOR MBEYA REGION | 4 | 44 | 14 | 58 | 11 | 93 | 177 | 270 |
|  |  |  | TOTAL FOR IRINGA AND MBEYA | 11 | 112 | 45 | 157 | 31 | 255 | 617 | 872 |

.

TRAINNING RESULTS;

CARE TNVS TRAINNING RESULTS   - OCT 2004 TO MARCH 2006

| S/N | REGION | CHMT MEETINGS | CHMT MEETING PARTICIPANTS | # RCH TRAININGS | # RCH STAFF TRAINED |
| --- | --- | --- | --- | --- | --- |
|  |  | TARGET | ACHIEVE MENT | % | TARGET | ACHIEVE MENT | % | TARGET | ACHIEVE MENT | % | TARGET | ACHIEVE MENT | % |
| 1. | Ruvuma | 4 | 5 | 125% | 100 | 79 | 79% | 14 | 18 | 128.% | 318 | 408 | 128% |
| 2. | Morogoro | 5 | 4 | 80% | 125 | 61 | 48.8% | 19 | 16 | 84% | 413 | 338 | 81% |
| 3. | Dar es Salaam | 3 | 3 | 100% | 75 | 58 | 77.3% | 13 | 13 | 100% | 290 | 438 | 151% |
| 4. | Coast | 6 | 5 | 83% | 125 | 79 | 63% | 13 | 13 | 92.% | 281 | 294 | 104% |
| 5. | Lindi | 6 | 3 | 50% | 150 | 37 | 24.7% | 13 | 5 | 38.5% | 281 | 431 | 152% |
| 6. | Mtwara | 5 | 5 | 100% | 125 | 80 | 64% | 13 | 9 | 69% | 286 | 327 | 114% |
| 7. | Mwanza | 7 | 7 | 100% | 175 | 132 | 75% | 25 | 21 | 84% | 558 | 610 | 109% |
| 8. | Kagera | 6 | 6 | 100% | 150 | 89 | 59% | 17 | 12 | 70% | 384 | 372 | 96.9% |
| 9. | Kigoma | 4 | 4 | 100% | 100 | 78 | 78% | 16 | 12 | 75% | 344 | 333 | 96.8% |
| 10 | Iringa | 6 | 7 | 116% | 150 | 120 | 80% | 22 | 20 | 91% | 475 | 602 | 127% |
| 11. | Mbeya | 4 | 4 | 100% | 100 | 58 | 58% | 12 | 11 | 92% | 269 | 270 | 100% |
|  | OVERAL | 56 | 53 | 100.3% | 1,090 | 851 | 78% | 177 | 150 | 84.7% | 3909 | 4422 | 113% |

ACHIEVEMENTS:

CARE organization completed the training in  all the regions assigned, the CHMT training was achieved at  78%, this is due to the fact that CHMT members in the plan were expected to be 25 members to attend for each session, but in reality  they were ranging from 17 to 20 participants.  The RCH training was achieved at 113%, as more facilities were found which were not captured in the initial plan.

# 3.0 Lesson learnt

- Some political figures have shown good cooperation in promoting awareness on Hati Punguzo, in most of the regions where the Regional Commissioner lobbied all the District Commissioners to give cooperation to the team, and to give full support, by making sure they officiate and participate in the CHMT training. The leaders also insisted on the fully participation of the community especially community leaders.

- The approach of implementing National government programs like TNVS through Public Private Partnership enhances sustainability and reaching the intended beneficiaries as each contracted partner puts effort to reach the goal

CHALLANGES

- The main challenge found in the period of training was health providers were not issuing discount Voucher to pregnant women when the retailer was not having bednets, this was observed in Kagera,   Mwanza, Mtwara, and Lindi.

RECCOMMENDATION.

The trainers recommend more trainers at an average of two trainers in one session for supporting each other and ensuring efficiency

# 4.0 Hati Punguzo with CARE’s Long Range Strategic Plan (LRSP)

- The CAREs LRSP is Good governance, Active citizenship for poverty reduction, policy analysis and advocacy and realignment.

- The goal of this program is that: 60% of pregnant women and children are protected by ITN by the year 2007.

- Hati Punguzo has been implemented in partnership between government (ministry of Heath and National Malaria Control program) with some other active stakeholders or NGOs contracted to do different components in the program of which CARE is one of them. CARE Tanzania together with WVT is contracted the component of training.

- This is one of the CAREs LRSP which is policy analysis and advocate, which insists on Care Tanzania to Working in partnership with others actors, advocate for development and effective implementation of policies at local, national and international levels that address the underlying causes of poverty and social justice.

- Malaria has been affecting and causing death to Tanzanian community, and the major group that has been affected more, is that of pregnancy women and children under five years.

Since CAREs Vision is to seek a world of hope, tolerance and social justice, where poverty has been overcome and people live in dignity and security. TNVS is gratefully to have the responsibilities to make sure that pregnant women and children get a chance to survive through prevention to malaria infestation.

.